## Master Mapping
SFS AI Readiness Assessment - Master Mapping
How Themes, Findings, Solutions, Recommendations, and Initiatives Connect
Finding # | Finding (Pain Point) | Theme(s) | Solution (Approach) | Recommendation (Tailored Advice) | Initiative(s) That Address | Phase
1 | Enterprise Data Foundation Incomplete | Theme 1: Knowledge Architecture Theme 5: Data Platform | Unified data foundation with API catalog, knowledge graph, data quality monitoring, data lineage visualization | Begin API catalog during Azure migration. Deploy knowledge graph. Implement Microsoft Purview for governance. | 1.3 Unified Metadata Schema 2.3 Content Inventory & Tagging 4.3 Knowledge Graph Implementation | Q1, Q2, Q4
2 | AI Governance Gap / Shadow IT | Theme 6: AI Governance Theme 2: Operational Enablement | Enterprise AI governance framework with CoE, usage monitoring, tiered approval, privacy standards, decision rubrics | Address unauthorized users. Establish AI CoE. Build token tracking. Create vendor evaluation framework. | 1.2 AI Governance Operationalization 2.4 AI Center of Excellence 3.1 AI Monitoring Dashboard | Q1, Q2, Q3
3 | Customer Service Highest ROI Opportunity | Theme 3: Customer Experience | Three-horizon customer AI: chatbot, Genesis activation, frustration detection → agent copilot → multi-modal agents | Prioritize payment automation (90% of calls). Activate Genesis. Prepare for End-of-Lease scaling to 100 agents. | 1.1 Genesis AI Activation 2.1 Payment Automation 3.2 End-of-Lease AI Prep 4.1 Collections AI | Q1, Q2, Q3, Q4
4 | Testing Bottleneck | Theme 4: Developer Productivity | AI augmentation across SDLC: self-healing locators, failure analysis, test generation, predictive selection | Reclaim 50% maintenance time. Deploy test generation from Gherkin. Expand API testing from 6 to 700+ endpoints. | 2.2 Test Automation Enhancement 3.3 GitHub Copilot Deployment | Q2, Q3
5 | BI Productivity Constrained | Theme 4: Developer Productivity Theme 5: Data Platform | AI-powered BI suite: SQL generation, report similarity detection, query optimization, code generation | Deploy schema-aware SQL generation. Target 30-50% productivity improvement. Extend agentic data analyst. | 1.4 BI Code Generation Pilot 3.4 Natural Language Query Expansion | Q1, Q3
6 | Remarketing Lacks Intelligence | Theme 3: Customer Experience Theme 5: Data Platform | Phased remarketing engine: next-best-action → VIN pricing → comprehensive multi-model decision engine | Build VIN-level pricing MVP. Implement repair ROI optimization. Target 2:1 reconditioning ROI. | 4.2 Einstein Activation (Future: Remarketing Decision Engine) | Q4, 2027
7 | Conversational AI Lacks Rigor | Theme 2: Operational Enablement Theme 3: Customer Experience | Conversational AI excellence framework: 75+ test evaluation, vector DB automation, multi-agent orchestration | Prevent 'GM $1 lease quote' incidents. Implement evaluation framework. Create platform portability strategy. | 1.1 Genesis AI Activation 2.1 Payment Automation 3.1 AI Monitoring Dashboard | Q1, Q2, Q3
8 | Cross-System Integration Barriers | Theme 1: Knowledge Architecture Theme 5: Data Platform | Integration excellence layer: API catalog, Sentinel observability, orchestration, customer 360 view | Complete API catalog during Azure migration. Implement unified data access. Ensure omnichannel consistency. | 1.3 Unified Metadata Schema 4.3 Knowledge Graph Implementation | Q1, Q4
9 | Document Intelligence Untapped | Theme 1: Knowledge Architecture Theme 3: Customer Experience | Document intelligence pipeline: credit report extraction, knowledge bot, SharePoint search, meeting transcription | Address underwriting bottleneck. Deploy enterprise knowledge bot. Implement AI-powered SharePoint search. | 2.3 Content Inventory & Tagging 4.3 Knowledge Graph Implementation | Q2, Q4
10 | Portfolio Growth Needs Predictive Analytics | Theme 5: Data Platform Theme 2: Operational Enablement | Advanced analytics infrastructure: ML Ops platform, predictive models, market intelligence, scenario analysis | Deploy ML Ops for bank compliance. Implement predictive models. Leverage 2,500+ credit attributes. | 3.4 Natural Language Query Expansion 4.4 ROI Validation & 2027 Planning | Q3, Q4
11 | Knowledge Management Inadequate | Theme 1: Knowledge Architecture Theme 6: AI Governance | AI-powered knowledge ecosystem: onboarding assistants, tribal knowledge capture, training programs, CoE | Create intelligent onboarding. Capture tribal knowledge before scaling. Build dealer education portal. | 2.3 Content Inventory & Tagging 2.4 AI Center of Excellence 4.3 Knowledge Graph | Q2, Q4
12 | Website/Digital Underperforms | Theme 3: Customer Experience | Transform digital to acquisition channel: search, chatbot, A/B testing, OEM integration, personalization | Implement missing search bar. Deploy customer chatbot. Establish A/B testing. Position for lease-end conversion. | 2.1 Payment Automation (chatbot) 4.2 Einstein Activation | Q2, Q4
13 | Resource Allocation Lacks Prioritization | Theme 6: AI Governance | AI-enhanced portfolio management: objective scoring, resource optimization, automated discovery, business case framework | Implement AI-powered portfolio analysis. Create resource optimization models. Automate discovery phase. | 2.4 AI Center of Excellence 4.4 ROI Validation & 2027 Planning | Q2, Q4
14 | Process Maturity Gap | Theme 2: Operational Enablement Theme 6: AI Governance | AI-assisted process maturity: automated documentation, DAP with monitoring, observability, KPI monitoring | Compress GMF's 12-year curve. Implement DAP for UX team. Automate process discovery from interviews. | 1.2 AI Governance Operationalization 3.1 AI Monitoring Dashboard | Q1, Q3
15 | Competitive Positioning Needs Strategy | Theme 6: AI Governance | Enterprise AI strategy: industry leadership positioning, reusable infrastructure, vendor-ready posture, ROI measurement | Move from cautionary to calculated innovation. Build competitive advantage through automation. Calculate ROI. | 2.4 AI Center of Excellence 4.4 ROI Validation & 2027 Planning | Q2, Q4

## Themes to Findings
Strategic Themes → Findings Mapping
Which pain points (findings) fall under each strategic capability area (theme)
Theme 1: Knowledge Architecture Foundation | Building the information infrastructure that enables AI to find and retrieve the right content | Findings: 1, 8, 9, 11
Finding 1 | Enterprise Data Foundation Incomplete
Finding 8 | Cross-System Integration Barriers
Finding 9 | Document Intelligence Untapped
Finding 11 | Knowledge Management Inadequate
Theme 2: Operational AI Enablement | Operationalizing AI governance and building monitoring/feedback infrastructure | Findings: 2, 7, 10, 14
Finding 2 | AI Governance Gap / Shadow IT
Finding 7 | Conversational AI Lacks Rigor
Finding 10 | Portfolio Needs Predictive Analytics
Finding 14 | Process Maturity Gap
Theme 3: Customer Experience Intelligence | AI-powered customer interactions across service, remarketing, and digital channels | Findings: 3, 6, 7, 9, 12
Finding 3 | Customer Service Highest ROI
Finding 6 | Remarketing Lacks Intelligence
Finding 7 | Conversational AI Lacks Rigor
Finding 9 | Document Intelligence Untapped
Finding 12 | Website/Digital Underperforms
Theme 4: Developer & Analyst Productivity | AI tools that accelerate development, testing, and analytics work | Findings: 4, 5
Finding 4 | Testing Bottleneck
Finding 5 | BI Productivity Constrained
Theme 5: Data Platform Modernization | Modern data infrastructure with classification, access patterns, and analytics | Findings: 1, 5, 6, 8, 10
Finding 1 | Enterprise Data Foundation Incomplete
Finding 5 | BI Productivity Constrained
Finding 6 | Remarketing Lacks Intelligence
Finding 8 | Cross-System Integration Barriers
Finding 10 | Portfolio Needs Predictive Analytics
Theme 6: AI Governance Operationalization | Moving governance from policy to practice with CoE and measurement | Findings: 2, 11, 13, 14, 15
Finding 2 | AI Governance Gap / Shadow IT
Finding 11 | Knowledge Management Inadequate
Finding 13 | Resource Allocation Lacks Prioritization
Finding 14 | Process Maturity Gap
Finding 15 | Competitive Positioning Needs Strategy

## Initiatives to Findings
Initiatives → Findings Mapping
Which pain points (findings) each project/initiative addresses
Initiative | Phase | Findings Addressed | Finding Names
1.1 Genesis AI Activation | Q1 | 3, 7 | Customer Service ROI, Conversational AI Rigor
1.2 AI Governance Operationalization | Q1 | 2, 14 | AI Governance Gap, Process Maturity
1.3 Unified Metadata Schema Design | Q1 | 1, 8 | Data Foundation, Integration Barriers
1.4 BI Code Generation Pilot | Q1 | 5 | BI Productivity
2.1 Payment Automation Deployment | Q2 | 3, 7, 12 | Customer Service, Conversational AI, Digital
2.2 Test Automation Enhancement | Q2 | 4 | Testing Bottleneck
2.3 Content Inventory & Tagging | Q2 | 1, 9, 11 | Data Foundation, Document Intel, Knowledge Mgmt
2.4 AI Center of Excellence Launch | Q2 | 2, 11, 13, 15 | Governance, Knowledge Mgmt, Resource Allocation, Competitive
3.1 AI Monitoring Dashboard | Q3 | 2, 7, 14 | Governance Gap, Conversational AI, Process Maturity
3.2 End-of-Lease AI Preparation | Q3 | 3 | Customer Service ROI (scaling to 100 agents)
3.3 GitHub Copilot Deployment | Q3 | 4, 5 | Testing Bottleneck, BI Productivity
3.4 Natural Language Query Expansion | Q3 | 5, 10 | BI Productivity, Predictive Analytics
4.1 Collections AI Augmentation | Q4 | 3 | Customer Service (400 FTE operation)
4.2 Einstein Activation | Q4 | 6, 12 | Remarketing Intelligence, Digital Properties
4.3 Knowledge Graph Implementation | Q4 | 1, 8, 9, 11 | Data Foundation, Integration, Document Intel, Knowledge Mgmt
4.4 ROI Validation & 2027 Planning | Q4 | 10, 13, 15 | Predictive Analytics, Resource Allocation, Competitive

## Terminology
SFS AI Readiness - Terminology & Hierarchy
TERM | DEFINITION | EXAMPLE
Theme | Strategic capability area - a way to group related problems and solutions. Themes represent the 'what we need to build' perspective. | Theme 1: Knowledge Architecture Foundation
Finding | Atomic pain point - the specific problems/symptoms we heard from stakeholders. Findings are the 'what's broken' evidence. | Finding 3: 90% of 50,000 monthly calls are payment-related
Solution | Conceptual approach - 'how it could be improved' in general terms. Platform-agnostic description of the fix. | Three-horizon customer AI: chatbot → agent copilot → multi-modal agents
Recommendation | Tailored advice - 'what we would do in your situation' considering SFS context, constraints, and priorities. | Prioritize payment automation. Activate Genesis immediately. Prepare for End-of-Lease scaling.
Initiative | Concrete project - the specific action/project that implements solutions. Has timing, owner, and deliverables. | 2.1 Payment Automation Deployment (Q2, High Impact)
HIERARCHY (How They Relate):
6 THEMES (Strategic Capability Areas)
↓ group
15 FINDINGS (Atomic Pain Points from Interviews)
↓ each finding has
SOLUTION (Conceptual Approach) + RECOMMENDATION (Tailored Advice)
↓ implemented by
16 INITIATIVES (Concrete Projects with Timing)
Note: The relationships are MANY-TO-MANY:
• One Finding can map to multiple Themes (Finding 5 → Theme 4 + Theme 5)
• One Initiative can address multiple Findings (Initiative 2.4 → Findings 2, 11, 13, 15)
• Multiple Initiatives may be needed for one Finding (Finding 1 → 1.3, 2.3, 4.3)

## Questions
QUESTIONS
'Why these 6 themes?' | Themes are capability areas we need to BUILD. They're organized by what we're creating, not what's broken. Use 'Themes to Findings' sheet to show how problems cluster.
'Why these 15 findings?' | Findings are atomic pain points we HEARD. They're organized by problem type. Each one traces back to specific interview sources.
'How do initiatives solve problems?' | Use 'Initiatives to Findings' sheet. Show that one initiative often addresses multiple findings, and some findings need multiple initiatives.
'What's the difference between Solution and Recommendation?' | Solution = general approach (vendor-agnostic). Recommendation = specific advice for SFS considering your context, constraints, and priorities.
'Where do I find the evidence?' | Every finding in the Excel 'Findings' sheet has source attribution. The 148 individual findings are grouped under the 15 themes.

## Documentation flow
How to Walk Through These Documents
RECOMMENDED FLOW
Step 1: Start with Executive Summary | Use the Word doc Executive Summary to set context. Show the 51% overall readiness score and the key metrics table. Explain the core challenge and strategic opportunity.
Step 2: Walk Through Findings by Theme | Use the Excel 'Themes to Findings' sheet to show how the 15 atomic findings cluster into 6 strategic themes. This helps the customer see patterns rather than a laundry list.
Step 3: Deep Dive on Priority Findings | Use the Excel 'Executive Summary' sheet for detailed view. Each row shows: What we heard → How to fix → What we'd do. Pick 3-5 highest priority findings to discuss in detail.
Step 4: Show the Implementation Path | Use the Word doc Section 5 (Roadmap) with initiative cards. Reference Excel 'Initiatives to Findings' to show which pain points each project addresses.
Step 5: Tie Back to ROI | Use Word doc Section 6 (Success Metrics) and industry benchmarks. Show how initiatives connect to measurable outcomes.