## 1. Executive Dashboard
SFS AI ROADMAP - EXECUTIVE DASHBOARD
112 Canonical Initiatives ¦ 29 Clusters ¦ 6 Strategic Themes ¦ 4 Phases ¦ C1-C51 Governance Components
PHASED TIMELINE OVERVIEW
Phase | Focus | Timeline | Initiatives | HIGH Priority | Key Outcomes
Phase 1: Governance & Foundation | Operationalize governance, activate purchased capabilities | Q1 2026 (Wks 1-12) | 39 | 29 | Three-tier governance active Genesys AI tokens deployed Agent registry v1 Shadow IT workflow BI code gen pilot
Phase 2: Quick Wins & Architecture | Payment automation, data classification, AI CoE | Q2 2026 (Wks 13-24) | 24 | 15 | Payment automation (30% deflection) Observe AI decision Purview classification Incident response playbook
Phase 3: Operational Maturity | AI monitoring, End-of-Lease, Copilot, NLP | Q3 2026 (Wks 25-36) | 46 | 5 | AI monitoring dashboard End-of-Lease AI GitHub Copilot Enterprise KM succession planning
Phase 4: Scale & Optimize | Collections voice AI, Remarketing, knowledge graph | Q4 2026 (Wks 37-48) | 3 | 1 | Collections analytics VIN-level pricing Knowledge graph 2027 roadmap
STRATEGIC THEME SUMMARY
Theme | Domain Focus | Clusters | Initiatives | Phase Emphasis
Theme 1: Knowledge Architecture | Knowledge capture, enterprise search, KCS | 15, 16 | 12 | Phase 1-3
Theme 2: Operational AI Enablement | ETL, APIs, MLOps, real-time, KG, ROI | 22-29 | 34 | Phase 2-4
Theme 3: Customer Experience Intel | Genesys, payments, chatbot, EoL, SF | 1-8 | 16 | Phase 1-3
Theme 4: Developer & Analyst | NLP, BI/SQL, Copilot, SDLC, QA | 17-21 | 37 | Phase 2-3
Theme 5: Data Platform Modern. | Classification, catalog, lineage, metadata | 12-14 | 6 | Phase 1-2
Theme 6: Governance Operations | Governance, risk, registry, shadow AI, CoE | 9a-11 | 17 | Phase 1
KEY DEFINITIONS
Cluster | A consolidated grouping of related AI opportunity items from across interviews, assessments, and source documents. The 391 raw items were deduplicated into 29 clusters, each representing a distinct capability or workstream assignable to a single owner.
Canonical Initiative | A deduplicated, actionable work item derived from one or more raw items. The 112 canonical initiatives represent the unique scope of work after removing duplicates across all source documents.
C-Code (C1-C51) | A governance component from the SFS AI Governance framework (Nader Afshar). Each C-code is a specific governance deliverable sequenced by maturity phase. EIS initiatives map to C-codes by functional alignment. See the Governance Maturity tab for full provenance.
Strategic Theme | One of six organizing categories that group clusters by strategic intent: Knowledge Architecture, Governance Operationalization, Customer Experience, Developer Productivity, Data Platform, and Advanced Analytics.
WORKBOOK NAVIGATION
1. Executive Dashboard | Macro overview, phase timeline, theme summary (this sheet)
2. Phased Timeline | All 112 initiatives organized by execution phase
3. By Theme & Cluster | 29 clusters under 6 strategic themes with initiative detail
4. Governance Maturity | C1-C51 components with provenance, category legend, EIS alignment methodology
5. Gantt - Strategic | 12-month Gantt by cluster (strategic view)
6. Gantt - Governance | 12-month Gantt by governance component
7. Canonical Initiatives | Complete 112-row reference with all fields
8. Issues & Actions | Unified issue register, resolution tracker, next steps
CLUSTER SUMMARY (29 CLUSTERS)
Domain | ID | Cluster Name | Initiatives | Dedup % | Theme
Customer-Facing AI | 1 | Genesys AI Platform Activation | 2 | 82% | Theme 3
| 2 | Genesys vs. Observe AI Resolution | 1 | 89% | Theme 3
| 3 | Payment & Voice Automation | 2 | 82% | Theme 3
| 4 | Customer Self-Service & Chatbot | 2 | 75% | Theme 3
| 5 | End-of-Lease AI Scaling | 1 | 67% | Theme 3
| 6 | Collections AI Augmentation | 2 | 50% | Theme 3
| 7 | Proactive Customer Engagement | 1 | 90% | Theme 3
| 8 | Salesforce Einstein / Agent Force | 3 | 62% | Theme 3
Governance & Organization | 9a | AI Governance Structure | 3 | 77% | Theme 6
| 9b | Risk Tiering & Agent Lifecycle | 2 | 78% | Theme 6
| 9c | Agent Registry & AI Inventory | 2 | 80% | Theme 6
| 9d | Shadow AI Remediation & Approved Tools | 4 | 69% | Theme 6
| 9e | AI Incident Response & Compliance | 3 | 40% | Theme 6
| 10 | AI Center of Excellence | 2 | 60% | Theme 6
| 11 | AI Cost Management & Metering | 1 | 93% | Theme 6
Data Foundation | 12 | Data Classification & Purview | 1 | 94% | Theme 5
| 13 | Data Catalog, Lineage & Quality | 3 | 84% | Theme 5
| 14 | Metadata, Taxonomy & Knowledge Architecture | 2 | 75% | Theme 5
Knowledge & Search | 15 | Knowledge Mgmt & Enterprise Search | 10 | 57% | Theme 1
| 16 | Knowledge Capture & Key Personnel Risk | 2 | 80% | Theme 1
Developer & Analyst Productivity | 17 | NLP Query & Conversational Analytics | 1 | 93% | Theme 4
| 18 | BI & SQL AI Productivity | 4 | 69% | Theme 4
| 19 | Developer AI Tools | 1 | 92% | Theme 4
| 20 | AI-SDLC Workflow Enhancement | 20 | 5% | Theme 4
| 21 | Test Automation & QA AI | 11 | 79% | Theme 4
Platform & Infrastructure | 22 | ETL & Data Pipeline Modernization | 4 | 64% | Theme 2
| 23 | API & Integration Architecture | 5 | 55% | Theme 2
| 24 | MLOps & Model Governance | 3 | 57% | Theme 2
| 25 | Real-Time Intelligence | 1 | 67% | Theme 2
Advanced Use Cases & Planning | 26 | Knowledge Graph & GraphRAG | 3 | 62% | Theme 2
| 27 | Remarketing, Research & Predictive Analytics | 5 | 38% | Theme 2
| 28 | AI Monitoring & Observability | 2 | 60% | Theme 2
| 29 | ROI Measurement & 2027 Planning | 3 | 79% | Theme 2
TOTAL |  |  | 112 | 71%

## 2. Phased Timeline
SFS AI ROADMAP - PHASED TIMELINE VIEW
112 Canonical Initiatives by Phase, Priority, and Timing
Phase | Strategic Theme | Cluster | Initiative | Priority | Timing | Owner(s) | Risk Tier | Gov Comp Ref | Source
Phase 1: Governance & Foundation (Q1 2026) | Theme 1: Knowledge Architecture Foundation | Knowledge Capture & Key Personnel Risk | #048: Document critical integrations and close documentation gaps | HIGH | Immediate (Wks 1-4) | AI Working Group |  | C19,C20 | EIS
Phase 1: Governance & Foundation (Q1 2026) | Theme 1: Knowledge Architecture Foundation | Knowledge Capture & Key Personnel Risk | #049: Knowledge capture from key personnel (Bobby, Adam, SMEs) | HIGH | Immediate (Wks 1-4) | AI Working Group |  | C19,C20 | EIS
Phase 1: Governance & Foundation (Q1 2026) | Theme 1: Knowledge Architecture Foundation | Knowledge Mgmt & Enterprise Search | #038: Deploy KCS methodology and content lifecycle management | MEDIUM | Months 1-16 | AI Working Group |  | C19,C20 | EIS
Phase 1: Governance & Foundation (Q1 2026) | Theme 1: Knowledge Architecture Foundation | Knowledge Mgmt & Enterprise Search | #039: Deploy unified enterprise knowledge repository | MEDIUM | Months 3-12 | AI Working Group |  | C19,C20 | EIS
Phase 1: Governance & Foundation (Q1 2026) | Theme 1: Knowledge Architecture Foundation | Knowledge Mgmt & Enterprise Search | #040: Document critical integrations and close documentation gaps | MEDIUM | Months 5-6 | AI Working Group |  | C19,C20 | EIS
Phase 1: Governance & Foundation (Q1 2026) | Theme 1: Knowledge Architecture Foundation | Knowledge Mgmt & Enterprise Search | #042: Implement federated/enterprise search (across SF, SharePoint, Tableau, Fabric) | MEDIUM | Months 3-10 | AI Working Group |  | C19,C20 | EIS
Phase 1: Governance & Foundation (Q1 2026) | Theme 2: Operational AI Enablement | API & Integration Architecture | #094: MuleSoft → Azure APIM migration | CRITICAL | TBD | Enterprise Architecture / IT Ops |  | C28,C42 | EIS
Phase 1: Governance & Foundation (Q1 2026) | Theme 2: Operational AI Enablement | ETL & Data Pipeline Modernization | #090: SSIS modernization with AI assistance (600+ packages → Fabric pipelines) | HIGH | Months 3-4 | Enterprise Data Mgmt |  | C39,C42 | EIS
Phase 1: Governance & Foundation (Q1 2026) | Theme 2: Operational AI Enablement | ROI Measurement & 2027 Planning | #110: 12-month roadmap phase summaries | HIGH | Weeks 1-36 | AI Working Group Committee |  | C26,C34 | EIS
Phase 1: Governance & Foundation (Q1 2026) | Theme 2: Operational AI Enablement | API & Integration Architecture | #093: MCP implementation (Model Context Protocol, phased rollout) | MEDIUM | Q1-Q4 2026 | Enterprise Architecture / IT Ops |  | C28,C42 | EIS
Phase 1: Governance & Foundation (Q1 2026) | Theme 3: Customer Experience Intelligence | Genesys AI Platform Activation | #001: Activate Genesys AI tokens (speech analytics, sentiment, agent copilot, predictive routing) | HIGH | Immediate (Wks 1-8) | Vic Chopra / Larry Burgess, Ryan Miller / IT Ops | Tier 2 | C14,C15,C16 | SFS + EIS
Phase 1: Governance & Foundation (Q1 2026) | Theme 3: Customer Experience Intelligence | Genesys vs. Observe AI Resolution | #003: Genesys vs. Observe AI evaluation and consolidation decision | HIGH | Immediate (Wks 1-16) | Working Group, Steering Committee |  | C14,C15 | SFS + EIS
Phase 1: Governance & Foundation (Q1 2026) | Theme 3: Customer Experience Intelligence | Payment & Voice Automation | #005: Payment voice automation (inbound/outbound, 30% call deflection) | HIGH | Weeks 13-24 | Greg Shreve, Customer Service/Genesys, Customer Service / Genesys | Tier 2 | C15,C16 | EIS
Phase 1: Governance & Foundation (Q1 2026) | Theme 3: Customer Experience Intelligence | Customer Self-Service & Chatbot | #006: Customer self-service chatbot (MySFS portal, FAQ, secured messaging) | HIGH | Months 13-14 | Customer Service |  | C15,C16 | EIS
Phase 1: Governance & Foundation (Q1 2026) | Theme 3: Customer Experience Intelligence | Proactive Customer Engagement | #011: Proactive customer engagement (predictive outreach, sentiment, payment risk) | HIGH | Immediate (Wks 1-8) | Collections / CS, Ryan Miller/IT Ops |  | C15,C16 | EIS
Phase 1: Governance & Foundation (Q1 2026) | Theme 4: Developer & Analyst Productivity | Test Automation & QA AI | #077: AI-driven test impact analysis (code→test mapping, risk-based regression) | CRITICAL | Immediate (Wks 1-12) | Dev Team / QA Lead |  | C40,C41,C42,C43 | EIS
Phase 1: Governance & Foundation (Q1 2026) | Theme 4: Developer & Analyst Productivity | Test Automation & QA AI | #082: Mandate data-test-id attributes | CRITICAL | Immediate (Wks 1-20) | QA / Dev Teams |  | C40,C41,C42,C43 | EIS
Phase 1: Governance & Foundation (Q1 2026) | Theme 4: Developer & Analyst Productivity | NLP Query & Conversational Analytics | #050: Expand NLP query / Data Agents (Treasury pilot → enterprise EDW) | HIGH | Immediate (Wks 1-36) | Adam Rufford, Data/AI CoE, Data / AI CoE | Tier 3 | C19 | EIS
Phase 1: Governance & Foundation (Q1 2026) | Theme 4: Developer & Analyst Productivity | BI & SQL AI Productivity | #051: AI-assisted SQL generation for BI team (schema-aware LLM) | HIGH | Weeks 4-12 | BI Team/EIS, BI Team | Tier 3 | C11 | EIS
Phase 1: Governance & Foundation (Q1 2026) | Theme 4: Developer & Analyst Productivity | BI & SQL AI Productivity | #053: Query performance analyzer | HIGH | Q1-Q2 2026 | Dev Team / QA Lead |  | C11 | EIS
Phase 1: Governance & Foundation (Q1 2026) | Theme 4: Developer & Analyst Productivity | Developer AI Tools | #055: GitHub Copilot enterprise deployment (IDE-integrated AI for all dev teams) | HIGH | Weeks 3-32 | Nader Afshar, Dev Teams/Security, Dev Teams / Security | Tier 3 | C8,C9 | EIS
Phase 1: Governance & Foundation (Q1 2026) | Theme 4: Developer & Analyst Productivity | Test Automation & QA AI | #076: AI-assisted test case generation (Jira→AI→Spira pipeline) | HIGH | Immediate (Wks 1-12) | Dev Team / QA Lead |  | C40,C41,C42,C43 | EIS
Phase 1: Governance & Foundation (Q1 2026) | Theme 4: Developer & Analyst Productivity | Test Automation & QA AI | #078: Bug pattern analysis and root cause analysis | HIGH | Immediate (Wks 1-1) | Dev Team / QA Lead |  | C40,C41,C42,C43 | EIS
Phase 1: Governance & Foundation (Q1 2026) | Theme 4: Developer & Analyst Productivity | Test Automation & QA AI | #081: Enhanced Copilot prompt template for test case generation | HIGH | Immediate (Wks 1-4) | QA / Corinne Anderson | Tier 4 | C40,C41,C42,C43 | EIS
Phase 1: Governance & Foundation (Q1 2026) | Theme 4: Developer & Analyst Productivity | BI & SQL AI Productivity | #052: BI migration support (Tableau→Power BI, legacy query translation) | MEDIUM | Q1-Q2 2026 | Dev Team / QA Lead |  | C11 | EIS
Phase 1: Governance & Foundation (Q1 2026) | Theme 4: Developer & Analyst Productivity | BI & SQL AI Productivity | #054: Report discovery and reuse engine (semantic search across existing reports) | MEDIUM | Weeks 4-9 | Dev Team / QA Lead |  | C11 | EIS
Phase 1: Governance & Foundation (Q1 2026) | Theme 5: Data Platform Modernization | Data Classification & Purview | #032: Deploy Purview for data classification (close 95% gap) | CRITICAL | Immediate (Wks 1-24) | Bobby Goodwin, Data Governance, Data Governance / Tony |  | C17,C18 | SFS + EIS
Phase 1: Governance & Foundation (Q1 2026) | Theme 5: Data Platform Modernization | Data Catalog, Lineage & Quality | #033: AI-powered data quality monitoring (anomaly detection, quality rules) | HIGH | Months 5-6 | Enterprise Data Mgmt |  | C17,C18,C19,C20 | SFS + EIS
Phase 1: Governance & Foundation (Q1 2026) | Theme 5: Data Platform Modernization | Data Catalog, Lineage & Quality | #034: Data catalog and discovery (Purview catalog, business glossary, searchable) | MEDIUM | Weeks 4-9 | Enterprise Architecture |  | C17,C18,C19,C20 | SFS + EIS
Phase 1: Governance & Foundation (Q1 2026) | Theme 5: Data Platform Modernization | Data Catalog, Lineage & Quality | #035: Data lineage tracking (automated, all EDW pipelines) | MEDIUM | Months 5-8 | Enterprise Architecture |  | C17,C18,C19,C20 | SFS + EIS
Phase 1: Governance & Foundation (Q1 2026) | Theme 5: Data Platform Modernization | Metadata, Taxonomy & Knowledge Architecture | #037: Unified metadata schema and enterprise taxonomy | MEDIUM | Weeks 4-12 | Bobby Goodwin/Data Team, Bobby Goodwin / Data |  | C17,C25 | SFS + EIS
Phase 1: Governance & Foundation (Q1 2026) | Theme 6: Governance Operationalization | AI Governance Structure | #015: AI Governance operationalization (policy→workflows, approval processes, enforcement) | CRITICAL | Weeks 1-12 | AI Governance Committee |  | C1,C2,C3,C4,C5,C6,C7 | SFS + EIS
Phase 1: Governance & Foundation (Q1 2026) | Theme 6: Governance Operationalization | AI Governance Structure | #016: Formalize three-tier governance structure (Steering Committee, Working Group, Task Forces) | HIGH | Immediate (Wks 1-2) | Ryan Miller / CDO |  | C1,C2,C3,C4,C5,C6,C7 | SFS + EIS
Phase 1: Governance & Foundation (Q1 2026) | Theme 6: Governance Operationalization | Risk Tiering & Agent Lifecycle | #018: Deploy risk tiering framework (Tier 1-4 with intake form) | HIGH | Weeks 3-6 | Working Group |  | C29,C31 | SFS + EIS
Phase 1: Governance & Foundation (Q1 2026) | Theme 6: Governance Operationalization | Agent Registry & AI Inventory | #020: Build agent registry (central catalog of all AI agents) | HIGH | Immediate (Wks 1-4) | Nader Afshar |  | C14 | SFS + EIS
Phase 1: Governance & Foundation (Q1 2026) | Theme 6: Governance Operationalization | Shadow AI Remediation & Approved Tools | #022: Design shadow IT request workflow | HIGH | Weeks 3-8 | Working Group / Tony |  | C8,C9,C10,C11 | SFS + EIS
Phase 1: Governance & Foundation (Q1 2026) | Theme 6: Governance Operationalization | Shadow AI Remediation & Approved Tools | #023: Provide sanctioned LLM access (replace shadow ChatGPT/Gemini) | HIGH | Immediate (Wks 1-2) | Enterprise Architecture |  | C8,C9,C10,C11 | SFS + EIS
Phase 1: Governance & Foundation (Q1 2026) | Theme 6: Governance Operationalization | Shadow AI Remediation & Approved Tools | #024: Publish approved AI tool list and establish intake process | HIGH | Immediate (Wks 1-2) | Enterprise Architecture |  | C8,C9,C10,C11 | SFS + EIS
Phase 1: Governance & Foundation (Q1 2026) | Theme 6: Governance Operationalization | AI Center of Excellence | #030: Establish AI Center of Excellence (structure, staffing, reusable components) | HIGH | Immediate (Wks 1-24) | CDO/Ryan Miller, Nader Afshar / CDO |  | C1,C5,C6,C7 | SFS + EIS
Phase 2: Quick Wins & Architecture (Q2 2026) | Theme 2: Operational AI Enablement | ETL & Data Pipeline Modernization | #087: Complete EDW migration to Fabric | MEDIUM | Q2 2026 | Enterprise Architecture / IT Ops |  | C39,C42 | EIS
Phase 2: Quick Wins & Architecture (Q2 2026) | Theme 2: Operational AI Enablement | ETL & Data Pipeline Modernization | #088: Enterprise migration coordination | MEDIUM | Months 7-8 | Enterprise Architecture / IT Ops |  | C39,C42 | EIS
Phase 2: Quick Wins & Architecture (Q2 2026) | Theme 2: Operational AI Enablement | MLOps & Model Governance | #098: Reopen/govern AI Foundry | MEDIUM | Q2-Q3 2026 | Enterprise Architecture / Eric G. (role TBD) |  | C31,C32,C33,C39 | SFS + EIS
Phase 2: Quick Wins & Architecture (Q2 2026) | Theme 2: Operational AI Enablement | Knowledge Graph & GraphRAG | #102: Knowledge graph implementation (data relationships, system dependencies) | MEDIUM | Weeks 40-48 | Data/AI CoE, Data / AI CoE | Tier 3 | C19,C20,C21 | EIS
Phase 2: Quick Wins & Architecture (Q2 2026) | Theme 2: Operational AI Enablement | AI Monitoring & Observability | #109: Agent/platform observability | MEDIUM | Months 11-12 | Enterprise Architecture / Eric G. (role TBD) |  | C31,C34,C37,C39 | SFS + EIS
Phase 2: Quick Wins & Architecture (Q2 2026) | Theme 3: Customer Experience Intelligence | Genesys AI Platform Activation | #002: Deploy Genesys Knowledge Workbench | MEDIUM | Q2-Q3 2026 | Customer Service |  | C14,C15,C16 | SFS + EIS
Phase 2: Quick Wins & Architecture (Q2 2026) | Theme 3: Customer Experience Intelligence | Salesforce Einstein / Agent Force | #014: Salesforce Einstein evaluation and activation | MEDIUM | Weeks 37-44 | Cassidy Hodge, Salesforce Team |  | C8,C9,C13 | EIS
Phase 2: Quick Wins & Architecture (Q2 2026) | Theme 4: Developer & Analyst Productivity | AI-SDLC Workflow Enhancement | #056: Data: AI-assisted data validation framework | HIGH | TBD | Mike Calaway |  | C28,C29,C30 | EIS
Phase 2: Quick Wins & Architecture (Q2 2026) | Theme 4: Developer & Analyst Productivity | AI-SDLC Workflow Enhancement | #057: Data: CI/CD pipeline standardization | HIGH | TBD | Mike Calaway |  | C28,C29,C30 | EIS
Phase 2: Quick Wins & Architecture (Q2 2026) | Theme 4: Developer & Analyst Productivity | AI-SDLC Workflow Enhancement | #060: Data: Dual-commit workflow automation (Fabric/SSDT) | HIGH | TBD | Mike Calaway |  | C28,C29,C30 | EIS
Phase 2: Quick Wins & Architecture (Q2 2026) | Theme 4: Developer & Analyst Productivity | AI-SDLC Workflow Enhancement | #063: Integration: AI coding assistants for new Azure API development | HIGH | TBD | Mike Calaway |  | C28,C29,C30 | EIS
Phase 2: Quick Wins & Architecture (Q2 2026) | Theme 4: Developer & Analyst Productivity | AI-SDLC Workflow Enhancement | #064: Integration: AI-assisted migration code generation (MuleSoft→Azure) | HIGH | TBD | Mike Calaway |  | C28,C29,C30 | EIS
Phase 2: Quick Wins & Architecture (Q2 2026) | Theme 4: Developer & Analyst Productivity | AI-SDLC Workflow Enhancement | #065: Integration: AI-generated APIM policies and config | HIGH | TBD | Mike Calaway |  | C28,C29,C30 | EIS
Phase 2: Quick Wins & Architecture (Q2 2026) | Theme 4: Developer & Analyst Productivity | AI-SDLC Workflow Enhancement | #070: Integration: Terraform/IaC generation | HIGH | TBD | Mike Calaway |  | C28,C29,C30 | EIS
Phase 2: Quick Wins & Architecture (Q2 2026) | Theme 4: Developer & Analyst Productivity | AI-SDLC Workflow Enhancement | #071: Salesforce: AI coding tools (Apex, LWC, Flows) | HIGH | TBD | Mike Calaway |  | C28,C29,C30 | EIS
Phase 2: Quick Wins & Architecture (Q2 2026) | Theme 4: Developer & Analyst Productivity | AI-SDLC Workflow Enhancement | #073: Salesforce: Code review against standards | HIGH | TBD | Mike Calaway |  | C28,C29,C30 | EIS
Phase 2: Quick Wins & Architecture (Q2 2026) | Theme 4: Developer & Analyst Productivity | AI-SDLC Workflow Enhancement | #075: Salesforce: Story quality validation | HIGH | TBD | Mike Calaway |  | C28,C29,C30 | EIS
Phase 2: Quick Wins & Architecture (Q2 2026) | Theme 4: Developer & Analyst Productivity | Test Automation & QA AI | #079: Continuous testing intelligence dashboard | HIGH | TBD | Dev Team / QA Lead |  | C40,C41,C42,C43 | EIS
Phase 2: Quick Wins & Architecture (Q2 2026) | Theme 4: Developer & Analyst Productivity | Test Automation & QA AI | #084: Pre-deployment merge validation | HIGH | TBD | Dev Team / QA Lead |  | C40,C41,C42,C43 | EIS
Phase 2: Quick Wins & Architecture (Q2 2026) | Theme 4: Developer & Analyst Productivity | Test Automation & QA AI | #085: Self-healing test locators | HIGH | Weeks 13-20 | QA/EIS |  | C40,C41,C42,C43 | EIS
Phase 2: Quick Wins & Architecture (Q2 2026) | Theme 4: Developer & Analyst Productivity | Test Automation & QA AI | #083: Measure time savings and quality impact | MEDIUM | Weeks 7-8 | Dev Team / QA Lead |  | C40,C41,C42,C43 | EIS
Phase 2: Quick Wins & Architecture (Q2 2026) | Theme 5: Data Platform Modernization | Metadata, Taxonomy & Knowledge Architecture | #036: Content inventory, tagging, and component model | MEDIUM | Months 9-10 | Enterprise Architecture |  | C17,C25 | SFS + EIS
Phase 2: Quick Wins & Architecture (Q2 2026) | Theme 6: Governance Operationalization | AI Incident Response & Compliance | #026: Bank/regulatory compliance preparation (FFIEC alignment) | HIGH | TBD | Enterprise Architecture |  | C27,C29 | SFS + EIS
Phase 2: Quick Wins & Architecture (Q2 2026) | Theme 6: Governance Operationalization | AI Incident Response & Compliance | #027: Draft AI incident response playbook (severity levels, escalation) | HIGH | Weeks 6-18 | Working Group / Security |  | C27,C29 | SFS + EIS
Phase 3: Operational Maturity (Q3 2026) | Theme 1: Knowledge Architecture Foundation | Knowledge Mgmt & Enterprise Search | #041: Governance velocity metric | MEDIUM | TBD | AI Working Group |  | C19,C20 | EIS
Phase 3: Operational Maturity (Q3 2026) | Theme 1: Knowledge Architecture Foundation | Knowledge Mgmt & Enterprise Search | #043: Knowledge RAG for agent assist | MEDIUM | TBD | AI Working Group |  | C19,C20 | EIS
Phase 3: Operational Maturity (Q3 2026) | Theme 1: Knowledge Architecture Foundation | Knowledge Mgmt & Enterprise Search | #044: Research automation for economics | MEDIUM | TBD | AI Working Group |  | C19,C20 | EIS
Phase 3: Operational Maturity (Q3 2026) | Theme 1: Knowledge Architecture Foundation | Knowledge Mgmt & Enterprise Search | #045: SME workflow integration | MEDIUM | TBD | AI Working Group |  | C19,C20 | EIS
Phase 3: Operational Maturity (Q3 2026) | Theme 1: Knowledge Architecture Foundation | Knowledge Mgmt & Enterprise Search | #046: Test/SDLC items (cross-ref Clusters 20/21) | MEDIUM | TBD | AI Working Group |  | C19,C20 | EIS
Phase 3: Operational Maturity (Q3 2026) | Theme 1: Knowledge Architecture Foundation | Knowledge Mgmt & Enterprise Search | #047: Vendor AI rationalization framework | MEDIUM | TBD | AI Working Group |  | C19,C20 | EIS
Phase 3: Operational Maturity (Q3 2026) | Theme 2: Operational AI Enablement | AI Monitoring & Observability | #108: AI monitoring dashboard (centralized performance, token consumption, cost allocation) | HIGH | Weeks 25-32 | AI CoE / IT Ops | Tier 3 | C31,C34,C37,C39 | SFS + EIS
Phase 3: Operational Maturity (Q3 2026) | Theme 2: Operational AI Enablement | ETL & Data Pipeline Modernization | #089: Platform integration (Snowflake mirroring) | MEDIUM | TBD | Enterprise Architecture / IT Ops |  | C39,C42 | EIS
Phase 3: Operational Maturity (Q3 2026) | Theme 2: Operational AI Enablement | API & Integration Architecture | #091: API integration documentation and unified data access | MEDIUM | TBD | Enterprise Architecture / IT Ops |  | C28,C42 | EIS
Phase 3: Operational Maturity (Q3 2026) | Theme 2: Operational AI Enablement | API & Integration Architecture | #092: Hybrid orchestration architecture (API gateway + event-driven) | MEDIUM | TBD | Enterprise Architecture / IT Ops |  | C28,C42 | EIS
Phase 3: Operational Maturity (Q3 2026) | Theme 2: Operational AI Enablement | API & Integration Architecture | #095: Unified agent desktop (Genesys + Salesforce single pane) | MEDIUM | TBD | Enterprise Architecture / IT Ops |  | C28,C42 | EIS
Phase 3: Operational Maturity (Q3 2026) | Theme 2: Operational AI Enablement | MLOps & Model Governance | #096: Drift detection framework | MEDIUM | TBD | Enterprise Architecture / Eric G. (role TBD) |  | C31,C32,C33,C39 | SFS + EIS
Phase 3: Operational Maturity (Q3 2026) | Theme 2: Operational AI Enablement | MLOps & Model Governance | #097: Formalize MLOps (ML Flow, Model Registry, experiment tracking) | MEDIUM | TBD | Enterprise Architecture / Eric G. (role TBD) |  | C31,C32,C33,C39 | SFS + EIS
Phase 3: Operational Maturity (Q3 2026) | Theme 2: Operational AI Enablement | Real-Time Intelligence | #099: Activate Fabric real-time intelligence (Eventstreams, KQL, Data Activator) | MEDIUM | TBD | Enterprise Architecture / IT Ops |  | C39 | EIS
Phase 3: Operational Maturity (Q3 2026) | Theme 2: Operational AI Enablement | Knowledge Graph & GraphRAG | #100: Fabric ontology features (evaluate as they mature) | MEDIUM | TBD | AI CoE / AI Working Group |  | C19,C20,C21 | EIS
Phase 3: Operational Maturity (Q3 2026) | Theme 2: Operational AI Enablement | Knowledge Graph & GraphRAG | #101: GraphRAG for document intelligence | MEDIUM | TBD | AI CoE / AI Working Group |  | C19,C20,C21 | EIS
Phase 3: Operational Maturity (Q3 2026) | Theme 2: Operational AI Enablement | Remarketing, Research & Predictive Analytics | #103: AI-powered project prioritization (40-50 project backlog) | MEDIUM | TBD | AI CoE / AI Working Group |  | C33,C34 | EIS
Phase 3: Operational Maturity (Q3 2026) | Theme 2: Operational AI Enablement | Remarketing, Research & Predictive Analytics | #104: Document intelligence (contract analysis, form recognition) | MEDIUM | TBD | AI CoE / AI Working Group |  | C33,C34 | EIS
Phase 3: Operational Maturity (Q3 2026) | Theme 2: Operational AI Enablement | Remarketing, Research & Predictive Analytics | #107: Research automation for economics team | MEDIUM | TBD | AI CoE / AI Working Group |  | C33,C34 | EIS
Phase 3: Operational Maturity (Q3 2026) | Theme 2: Operational AI Enablement | ROI Measurement & 2027 Planning | #111: Business outcome targets | MEDIUM | TBD | AI Working Group Committee |  | C26,C34 | EIS
Phase 3: Operational Maturity (Q3 2026) | Theme 3: Customer Experience Intelligence | End-of-Lease AI Scaling | #008: End-of-Lease AI preparation (14→80-100 agents, call classification, chatbot) | HIGH | Weeks 25-36 | Danny Rodriguez/AI CoE, Danny Rodriguez / AI CoE | Tier 2 | C15,C16 | EIS
Phase 3: Operational Maturity (Q3 2026) | Theme 3: Customer Experience Intelligence | Collections AI Augmentation | #009: Collections AI augmentation (voice AI, predictive analytics for 400 FTE) | HIGH | Weeks 37-48 | Greg Shreve/AI CoE, Greg Shreve / AI CoE | Tier 2 | C15,C16 | EIS
Phase 3: Operational Maturity (Q3 2026) | Theme 3: Customer Experience Intelligence | Payment & Voice Automation | #004: Conversational IVR (natural language payment processing) | MEDIUM | TBD | AI Working Group |  | C15,C16 | EIS
Phase 3: Operational Maturity (Q3 2026) | Theme 3: Customer Experience Intelligence | Customer Self-Service & Chatbot | #007: Internal conversational agent (HR/Benefits) | MEDIUM | TBD | AI Working Group |  | C15,C16 | EIS
Phase 3: Operational Maturity (Q3 2026) | Theme 3: Customer Experience Intelligence | Collections AI Augmentation | #010: Wrongful repo prevention (real-time monitoring) | MEDIUM | TBD | AI Working Group |  | C15,C16 | EIS
Phase 3: Operational Maturity (Q3 2026) | Theme 3: Customer Experience Intelligence | Salesforce Einstein / Agent Force | #012: Salesforce Agent Force implementation | MEDIUM | TBD | Enterprise Architecture |  | C8,C9,C13 | EIS
Phase 3: Operational Maturity (Q3 2026) | Theme 3: Customer Experience Intelligence | Salesforce Einstein / Agent Force | #013: Salesforce Data Cloud Analytics | MEDIUM | TBD | Enterprise Architecture |  | C8,C9,C13 | EIS
Phase 3: Operational Maturity (Q3 2026) | Theme 4: Developer & Analyst Productivity | Test Automation & QA AI | #086: Shift automation left (QA environment, sprint N+1) | HIGH | Weeks 13-16 | Dev Team / QA Lead |  | C40,C41,C42,C43 | EIS
Phase 3: Operational Maturity (Q3 2026) | Theme 4: Developer & Analyst Productivity | AI-SDLC Workflow Enhancement | #058: Data: Code review and standards enforcement | MEDIUM | TBD | Mike Calaway |  | C28,C29,C30 | EIS
Phase 3: Operational Maturity (Q3 2026) | Theme 4: Developer & Analyst Productivity | AI-SDLC Workflow Enhancement | #059: Data: Deployment governance and release management | MEDIUM | TBD | Mike Calaway |  | C28,C29,C30 | EIS
Phase 3: Operational Maturity (Q3 2026) | Theme 4: Developer & Analyst Productivity | AI-SDLC Workflow Enhancement | #061: Data: Migration parity validation (SSIS→Fabric) | MEDIUM | TBD | Mike Calaway |  | C28,C29,C30 | EIS
Phase 3: Operational Maturity (Q3 2026) | Theme 4: Developer & Analyst Productivity | AI-SDLC Workflow Enhancement | #062: Data: Work intake and requirements quality | MEDIUM | TBD | Mike Calaway |  | C28,C29,C30 | EIS
Phase 3: Operational Maturity (Q3 2026) | Theme 4: Developer & Analyst Productivity | AI-SDLC Workflow Enhancement | #066: Integration: API parity testing (MuleSoft vs Azure) | MEDIUM | TBD | Mike Calaway |  | C28,C29,C30 | EIS
Phase 3: Operational Maturity (Q3 2026) | Theme 4: Developer & Analyst Productivity | AI-SDLC Workflow Enhancement | #067: Integration: CI/CD pipeline YAML generation | MEDIUM | TBD | Mike Calaway |  | C28,C29,C30 | EIS
Phase 3: Operational Maturity (Q3 2026) | Theme 4: Developer & Analyst Productivity | AI-SDLC Workflow Enhancement | #068: Integration: Discovery and current-state documentation | MEDIUM | TBD | Mike Calaway |  | C28,C29,C30 | EIS
Phase 3: Operational Maturity (Q3 2026) | Theme 4: Developer & Analyst Productivity | AI-SDLC Workflow Enhancement | #069: Integration: Story quality for integration architects | MEDIUM | TBD | Mike Calaway |  | C28,C29,C30 | EIS
Phase 3: Operational Maturity (Q3 2026) | Theme 4: Developer & Analyst Productivity | AI-SDLC Workflow Enhancement | #072: Salesforce: Architecture diagrams generation | MEDIUM | TBD | Mike Calaway |  | C28,C29,C30 | EIS
Phase 3: Operational Maturity (Q3 2026) | Theme 4: Developer & Analyst Productivity | AI-SDLC Workflow Enhancement | #074: Salesforce: Documentation drift detection | MEDIUM | TBD | Mike Calaway |  | C28,C29,C30 | EIS
Phase 3: Operational Maturity (Q3 2026) | Theme 4: Developer & Analyst Productivity | Test Automation & QA AI | #080: Dedicated test data management | MEDIUM | Weeks 13-16 | Dev Team / QA Lead |  | C40,C41,C42,C43 | EIS
Phase 3: Operational Maturity (Q3 2026) | Theme 6: Governance Operationalization | AI Cost Management & Metering | #031: Build AI cost tracking and token metering infrastructure | HIGH | Weeks 6-32 | Architecture, AI CoE/IT Ops |  | C24,C26 | SFS + EIS
Phase 3: Operational Maturity (Q3 2026) | Theme 6: Governance Operationalization | AI Governance Structure | #017: Ongoing governance maintenance (quarterly reviews, framework refresh, risk register) | MEDIUM | TBD | AI Working Group Team AI Execution Team |  | C1,C2,C3,C4,C5,C6,C7 | SFS + EIS
Phase 3: Operational Maturity (Q3 2026) | Theme 6: Governance Operationalization | Risk Tiering & Agent Lifecycle | #019: Implement 6-stage agent lifecycle framework (Ideation→Decommission) | MEDIUM | TBD | Mike Calaway |  | C29,C31 | SFS + EIS
Phase 3: Operational Maturity (Q3 2026) | Theme 6: Governance Operationalization | Agent Registry & AI Inventory | #021: Inventory and activate licensed-but-dormant AI capabilities | MEDIUM | Weeks 3-12 | Enterprise Architecture |  | C14 | SFS + EIS
Phase 3: Operational Maturity (Q3 2026) | Theme 6: Governance Operationalization | Shadow AI Remediation & Approved Tools | #025: Quarterly governance effectiveness reviews | MEDIUM | TBD | Enterprise Architecture |  | C8,C9,C10,C11 | SFS + EIS
Phase 3: Operational Maturity (Q3 2026) | Theme 6: Governance Operationalization | AI Incident Response & Compliance | #028: Vendor lock-in mitigation (audit clauses, data portability) | MEDIUM | TBD | Enterprise Architecture |  | C27,C29 | SFS + EIS
Phase 3: Operational Maturity (Q3 2026) | Theme 6: Governance Operationalization | AI Center of Excellence | #029: AI training and enablement programs | MEDIUM | TBD | AI Working Group Team AI Execution Team |  | C1,C5,C6,C7 | SFS + EIS
Phase 4: Scale & Optimize (Q4 2026) | Theme 2: Operational AI Enablement | ROI Measurement & 2027 Planning | #112: ROI validation and 2027 planning | HIGH | Weeks 37-48 | AI Governance Committee |  | C26,C34 | EIS
Phase 4: Scale & Optimize (Q4 2026) | Theme 2: Operational AI Enablement | Remarketing, Research & Predictive Analytics | #105: Predictive analytics (lifecycle models, portfolio analysis) | MEDIUM | Weeks 40-48 | Data Science / Risk | Tier 1 | C33,C34 | EIS
Phase 4: Scale & Optimize (Q4 2026) | Theme 2: Operational AI Enablement | Remarketing, Research & Predictive Analytics | #106: Remarketing decision engine (VIN-level pricing, channel optimization) | MEDIUM | Weeks 37-44 | Remarketing / AI CoE | Tier 3 | C33,C34 | EIS

## 3. By Theme & Cluster
SFS AI ROADMAP - STRATEGIC THEMES AND CLUSTERS
29 Clusters grouped by 6 Strategic Themes
Domain | Cluster ID | Cluster Name | Canonical Count | Strategic Theme | Canonical Initiatives
Customer-Facing AI | 1 | Genesys AI Platform Activation | 2 | Theme 3: Customer Experience Intelligence | #001: Activate Genesys AI tokens (speech analytics, sentiment, agent copilot, predictive routing) #002: Deploy Genesys Knowledge Workbench
Customer-Facing AI | 2 | Genesys vs. Observe AI Resolution | 1 | Theme 3: Customer Experience Intelligence | #003: Genesys vs. Observe AI evaluation and consolidation decision
Customer-Facing AI | 3 | Payment & Voice Automation | 2 | Theme 3: Customer Experience Intelligence | #004: Conversational IVR (natural language payment processing) #005: Payment voice automation (inbound/outbound, 30% call deflection)
Customer-Facing AI | 4 | Customer Self-Service & Chatbot | 2 | Theme 3: Customer Experience Intelligence | #006: Customer self-service chatbot (MySFS portal, FAQ, secured messaging) #007: Internal conversational agent (HR/Benefits)
Customer-Facing AI | 5 | End-of-Lease AI Scaling | 1 | Theme 3: Customer Experience Intelligence | #008: End-of-Lease AI preparation (14→80-100 agents, call classification, chatbot)
Customer-Facing AI | 6 | Collections AI Augmentation | 2 | Theme 3: Customer Experience Intelligence | #009: Collections AI augmentation (voice AI, predictive analytics for 400 FTE) #010: Wrongful repo prevention (real-time monitoring)
Customer-Facing AI | 7 | Proactive Customer Engagement | 1 | Theme 3: Customer Experience Intelligence | #011: Proactive customer engagement (predictive outreach, sentiment, payment risk)
Customer-Facing AI | 8 | Salesforce Einstein / Agent Force | 3 | Theme 3: Customer Experience Intelligence | #012: Salesforce Agent Force implementation #013: Salesforce Data Cloud Analytics #014: Salesforce Einstein evaluation and activation
Governance & Organization | 9a | AI Governance Structure | 3 | Theme 6: Governance Operationalization | #015: AI Governance operationalization (policy→workflows, approval processes, enforcement) #016: Formalize three-tier governance structure (Steering Committee, Working Group, Task Forces) #017: Ongoing governance maintenance (quarterly reviews, framework refresh, risk register)
Governance & Organization | 9b | Risk Tiering & Agent Lifecycle | 2 | Theme 6: Governance Operationalization | #018: Deploy risk tiering framework (Tier 1-4 with intake form) #019: Implement 6-stage agent lifecycle framework (Ideation→Decommission)
Governance & Organization | 9c | Agent Registry & AI Inventory | 2 | Theme 6: Governance Operationalization | #020: Build agent registry (central catalog of all AI agents) #021: Inventory and activate licensed-but-dormant AI capabilities
Governance & Organization | 9d | Shadow AI Remediation & Approved Tools | 4 | Theme 6: Governance Operationalization | #022: Design shadow IT request workflow #023: Provide sanctioned LLM access (replace shadow ChatGPT/Gemini) #024: Publish approved AI tool list and establish intake process #025: Quarterly governance effectiveness reviews
Governance & Organization | 9e | AI Incident Response & Compliance | 3 | Theme 6: Governance Operationalization | #026: Bank/regulatory compliance preparation (FFIEC alignment) #027: Draft AI incident response playbook (severity levels, escalation) #028: Vendor lock-in mitigation (audit clauses, data portability)
Governance & Organization | 10 | AI Center of Excellence | 2 | Theme 6: Governance Operationalization | #029: AI training and enablement programs #030: Establish AI Center of Excellence (structure, staffing, reusable components)
Governance & Organization | 11 | AI Cost Management & Metering | 1 | Theme 6: Governance Operationalization | #031: Build AI cost tracking and token metering infrastructure
Data Foundation | 12 | Data Classification & Purview | 1 | Theme 5: Data Platform Modernization | #032: Deploy Purview for data classification (close 95% gap)
Data Foundation | 13 | Data Catalog, Lineage & Quality | 3 | Theme 5: Data Platform Modernization | #033: AI-powered data quality monitoring (anomaly detection, quality rules) #034: Data catalog and discovery (Purview catalog, business glossary, searchable) #035: Data lineage tracking (automated, all EDW pipelines)
Data Foundation | 14 | Metadata, Taxonomy & Knowledge Architecture | 2 | Theme 5: Data Platform Modernization | #036: Content inventory, tagging, and component model #037: Unified metadata schema and enterprise taxonomy
Knowledge & Search | 15 | Knowledge Mgmt & Enterprise Search | 10 | Theme 1: Knowledge Architecture Foundation | #038: Deploy KCS methodology and content lifecycle management #039: Deploy unified enterprise knowledge repository #040: Document critical integrations and close documentation gaps #041: Governance velocity metric #042: Implement federated/enterprise search (across SF, SharePoint, Tableau, Fabric) #043: Knowledge RAG for agent assist #044: Research automation for economics #045: SME workflow integration #046: Test/SDLC items (cross-ref Clusters 20/21) #047: Vendor AI rationalization framework
Knowledge & Search | 16 | Knowledge Capture & Key Personnel Risk | 2 | Theme 1: Knowledge Architecture Foundation | #048: Document critical integrations and close documentation gaps #049: Knowledge capture from key personnel (Bobby, Adam, SMEs)
Developer & Analyst Productivity | 17 | NLP Query & Conversational Analytics | 1 | Theme 4: Developer & Analyst Productivity | #050: Expand NLP query / Data Agents (Treasury pilot → enterprise EDW)
Developer & Analyst Productivity | 18 | BI & SQL AI Productivity | 4 | Theme 4: Developer & Analyst Productivity | #051: AI-assisted SQL generation for BI team (schema-aware LLM) #052: BI migration support (Tableau→Power BI, legacy query translation) #053: Query performance analyzer #054: Report discovery and reuse engine (semantic search across existing reports)
Developer & Analyst Productivity | 19 | Developer AI Tools | 1 | Theme 4: Developer & Analyst Productivity | #055: GitHub Copilot enterprise deployment (IDE-integrated AI for all dev teams)
Developer & Analyst Productivity | 20 | AI-SDLC Workflow Enhancement | 20 | Theme 4: Developer & Analyst Productivity | #056: Data: AI-assisted data validation framework #057: Data: CI/CD pipeline standardization #058: Data: Code review and standards enforcement #059: Data: Deployment governance and release management #060: Data: Dual-commit workflow automation (Fabric/SSDT) #061: Data: Migration parity validation (SSIS→Fabric) #062: Data: Work intake and requirements quality #063: Integration: AI coding assistants for new Azure API development #064: Integration: AI-assisted migration code generation (MuleSoft→Azure) #065: Integration: AI-generated APIM policies and config #066: Integration: API parity testing (MuleSoft vs Azure) #067: Integration: CI/CD pipeline YAML generation #068: Integration: Discovery and current-state documentation #069: Integration: Story quality for integration architects #070: Integration: Terraform/IaC generation #071: Salesforce: AI coding tools (Apex, LWC, Flows) #072: Salesforce: Architecture diagrams generation #073: Salesforce: Code review against standards #074: Salesforce: Documentation drift detection #075: Salesforce: Story quality validation
Developer & Analyst Productivity | 21 | Test Automation & QA AI | 11 | Theme 4: Developer & Analyst Productivity | #076: AI-assisted test case generation (Jira→AI→Spira pipeline) #077: AI-driven test impact analysis (code→test mapping, risk-based regression) #078: Bug pattern analysis and root cause analysis #079: Continuous testing intelligence dashboard #080: Dedicated test data management #081: Enhanced Copilot prompt template for test case generation #082: Mandate data-test-id attributes #083: Measure time savings and quality impact #084: Pre-deployment merge validation #085: Self-healing test locators #086: Shift automation left (QA environment, sprint N+1)
Platform & Infrastructure | 22 | ETL & Data Pipeline Modernization | 4 | Theme 2: Operational AI Enablement | #087: Complete EDW migration to Fabric #088: Enterprise migration coordination #089: Platform integration (Snowflake mirroring) #090: SSIS modernization with AI assistance (600+ packages → Fabric pipelines)
Platform & Infrastructure | 23 | API & Integration Architecture | 5 | Theme 2: Operational AI Enablement | #091: API integration documentation and unified data access #092: Hybrid orchestration architecture (API gateway + event-driven) #093: MCP implementation (Model Context Protocol, phased rollout) #094: MuleSoft → Azure APIM migration #095: Unified agent desktop (Genesys + Salesforce single pane)
Platform & Infrastructure | 24 | MLOps & Model Governance | 3 | Theme 2: Operational AI Enablement | #096: Drift detection framework #097: Formalize MLOps (ML Flow, Model Registry, experiment tracking) #098: Reopen/govern AI Foundry
Platform & Infrastructure | 25 | Real-Time Intelligence | 1 | Theme 2: Operational AI Enablement | #099: Activate Fabric real-time intelligence (Eventstreams, KQL, Data Activator)
Advanced Use Cases & Planning | 26 | Knowledge Graph & GraphRAG | 3 | Theme 2: Operational AI Enablement | #100: Fabric ontology features (evaluate as they mature) #101: GraphRAG for document intelligence #102: Knowledge graph implementation (data relationships, system dependencies)
Advanced Use Cases & Planning | 27 | Remarketing, Research & Predictive Analytics | 5 | Theme 2: Operational AI Enablement | #103: AI-powered project prioritization (40-50 project backlog) #104: Document intelligence (contract analysis, form recognition) #105: Predictive analytics (lifecycle models, portfolio analysis) #106: Remarketing decision engine (VIN-level pricing, channel optimization) #107: Research automation for economics team
Advanced Use Cases & Planning | 28 | AI Monitoring & Observability | 2 | Theme 2: Operational AI Enablement | #108: AI monitoring dashboard (centralized performance, token consumption, cost allocation) #109: Agent/platform observability
Advanced Use Cases & Planning | 29 | ROI Measurement & 2027 Planning | 3 | Theme 2: Operational AI Enablement | #110: 12-month roadmap phase summaries #111: Business outcome targets #112: ROI validation and 2027 planning
TOTAL |  |  | 112

## 4. Governance Maturity
SFS AI ROADMAP - GOVERNANCE MATURITY JOURNEY (C1-C51)
C1-C51 Components with EIS Cluster Alignment, Owners, and Timing
ABOUT THIS TAB: GOVERNANCE COMPONENTS (C-CODES)
The C1 through C51 designations originate from the SFS AI Governance Components framework developed by Nader Afshar (SFS). Each C-code represents a discrete governance deliverable or action item within SFS's internal AI maturity roadmap. The C-codes are sequenced by governance category (Operating Model, Financial/DevOps, Data Classification, Legal/Compliance, Monitoring, etc.) and phased by target due date, progressing from foundational governance setup (C1 through C5, February 2026) through advanced operational controls (C48 through C51, September/October 2026).
EIS Cluster Alignment: The column labeled "EIS Cluster Alignment" maps each C-code to one or more of the 29 EIS clusters by functional intent. The question applied was: "What EIS-identified work supports this governance component?" This mapping was performed manually by reading each C-code definition and each EIS cluster's scope, then aligning on shared functional purpose. For example, C17 ("Classify all Structured data") maps to EIS Cluster 12 (Data Classification & Purview) because both address the same need, even though the EIS initiative is scoped and timed differently than the SFS deliverable. The mapping is not 1:1; a single C-code may align to multiple EIS clusters, and a single EIS cluster may support multiple C-codes.
Pending Corrections: Four C-code mapping discrepancies are awaiting client confirmation (CC-1 through CC-4 on the Issues & Actions tab). Nader's Components sheet and Process sheet define C14, C17/C18, C29, and C31 differently. Until resolved, EIS cluster alignment for those codes should be treated as provisional. The "Source" column distinguishes SFS Internal components (Nader's framework) from SFS + EIS joint initiatives.
C-CODE CATEGORY LEGEND
C1-C5 | Operating Model & Oversight |  | C21-C23 | Legal, Compliance & Regulatory |  | C40-C41 | Model Validation
C6-C9 | Financial / DevOps |  | C24 | Financial (Cost Attribution) |  | C42-C44 | Configuration Management
C10-C16 | Financial Registry / Consolidation |  | C25 | Metadata Management |  | C45-C47 | Documentation
C17-C20 | Data Classification & Lineage |  | C26 | Vendor Management |  | C48-C51 | Access Control
|  |  | C27 | Incident Response
|  |  | C28-C30 | DevSecOps
|  |  | C31-C39 | Monitoring & Audit
Source: SFS AI Governance Components (Nader Afshar, February 2026). EIS cluster alignment by Earley Information Science.
Component | Gov Category | Key Actions | Deliverables | Due Date | EIS Cluster Alignment | Owner | Resolved Timing | Success Metric | Status | Source
Operating Model and Oversight
C1 | Operating Model and Oversight | Establish the AI Operational Working Group (AWG). | Ratify the Charter | 02/27/2026 | 9a: AI Governance Structure 10: AI Center of Excellence | AI Working Group Team AI Execution Team |  | 40% reduction in time-to-approval for low-risk AI projects | Not Started | SFS Internal
C2 | Operating Model and Oversight |  | Ratify Key members | 02/23/2026 | 9a: AI Governance Structure | Chair / Co-Chair |  | 40% reduction in time-to-approval for low-risk AI projects | Not Started | SFS Internal
C3 | Operating Model and Oversight |  | Establish exit criteria | TBD | 9a: AI Governance Structure | AI Working Group Team AI Execution Team |  | 40% reduction in time-to-approval for low-risk AI projects | Not Started | SFS Internal
C4 | Operating Model and Oversight |  | Determine process for standing up Execution Task Force (ETF) | 03/27/2026 | 9a: AI Governance Structure | Digital / Process |  | 40% reduction in time-to-approval for low-risk AI projects | Not Started | SFS Internal
C5 | Operating Model and Oversight |  | Define Documentation Requirements | TBD | 9a: AI Governance Structure 10: AI Center of Excellence | AI Working Group Team AI Execution Team |  | 40% reduction in time-to-approval for low-risk AI projects | Not Started | SFS Internal
Financial, DevOps
C6 | Financial, DevOps | Facilitate deployment of “Pricing Agent” from Risk Group | Short term budget for tokens | 03/06/2026 | 9a: AI Governance Structure 10: AI Center of Excellence | AI Working Group Team AI Execution Team |  | 40% reduction in time-to-approval for low-risk AI projects | Not Started | SFS Internal
C7 | Financial, DevOps |  | CBA on Hugging Face to save on tokens | 02/23/2026 | 9a: AI Governance Structure 10: AI Center of Excellence | Chair / Co-Chair |  | 40% reduction in time-to-approval for low-risk AI projects | Not Started | SFS Internal
C8 | Financial, DevOps | Address Shadow IT Root Causes and eliminate all. | Establish Tools for all forms of AI uses & plan to make them available over the course of the year | 03/27/2026 | 8: Salesforce Einstein / Agent Force 9d: Shadow AI Remediation & Approved Tools 19: Developer AI Tools | Enterprise Architecture |  | 40% reduction in time-to-approval for low-risk AI projects | Not Started | SFS Internal
C9 | Financial, DevOps |  | Define best platform for deployment of internal apps | 03/27/2026 | 8: Salesforce Einstein / Agent Force 9d: Shadow AI Remediation & Approved Tools 19: Developer AI Tools | Enterprise Architecture |  | 40% reduction in time-to-approval for low-risk AI projects | Not Started | SFS Internal
Financial Registery
C10 | Financial Registery | Save $4.5M on annual run-rate | Plan for tagging all PII and related data | 03/13/2026 | 9d: Shadow AI Remediation & Approved Tools | Enterprise Architecture |  | Recovery of $4.5M in redundant spend; 100% AI cost attributed | Not Started | SFS Internal
C11 | Financial Registery | Central Registry for Models & Tools | CBA on SLM vs LLM, on premise | TBD | 9d: Shadow AI Remediation & Approved Tools 18: BI & SQL AI Productivity | Enterprise Architecture |  | Recovery of $4.5M in redundant spend; 100% AI cost attributed | Not Started | SFS Internal
C12 | Financial Registery |  | Set-up an MCP for tools and A2A registry for Agents. | TBD |  |  |  | Recovery of $4.5M in redundant spend; 100% AI cost attributed | Not Started | SFS Internal
C13 | Financial Registery |  | A model registry will also be needed if we build our own. | 03/27/2026 | 8: Salesforce Einstein / Agent Force | Enterprise Architecture |  | Recovery of $4.5M in redundant spend; 100% AI cost attributed | Not Started | SFS Internal
C14 | Financial Registery |  | Begin discussion on consolidation of Genesys & Observe AI. | 04/24/2026 | 1: Genesys AI Platform Activation 2: Genesys vs. Observe AI Resolution 9c: Agent Registry & AI Inventory | Enterprise Architecture |  | Recovery of $4.5M in redundant spend; 100% AI cost attributed | Not Started | SFS Internal
Financial
C15 | Financial | Genesys & Observe AI | Finalize the decision | 03/20/2026 | 1: Genesys AI Platform Activation 2: Genesys vs. Observe AI Resolution 3: Payment & Voice Automation 4: Customer Self-Service & Chatbot 5: End-of-Lease AI Scaling 6: Collections AI Augmentation 7: Proactive Customer Engagement | Enterprise Architecture |  | Recovery of $4.5M in redundant spend; 100% AI cost attributed | Not Started | SFS Internal
C16 | Financial |  | Plan the transition | TBD | 1: Genesys AI Platform Activation 3: Payment & Voice Automation 4: Customer Self-Service & Chatbot 5: End-of-Lease AI Scaling 6: Collections AI Augmentation 7: Proactive Customer Engagement | Enterprise Architecture |  | Recovery of $4.5M in redundant spend; 100% AI cost attributed | Not Started | SFS Internal
Data Classification Data Lineage
C17 | Data Classification Data Lineage | Prepare data to be AI-Ready | Classify all Structured (90% currently untagged) | 03/27/2026 | 12: Data Classification & Purview 13: Data Catalog, Lineage & Quality 14: Metadata, Taxonomy & Knowledge Architecture | Enterprise Architecture |  | Zero "Unknown" AI agents; 70%+ data classified | Not Started | SFS Internal
C18 | Data Classification Data Lineage |  | Classify all Unstructured data (Nearly all untagged) | 04/24/2026 | 12: Data Classification & Purview 13: Data Catalog, Lineage & Quality | Enterprise Architecture |  | Zero "Unknown" AI agents; 70%+ data classified | Not Started | SFS Internal
C19 | Data Classification Data Lineage |  | Define framework for vectorization of all Unstructured data | TBD | 13: Data Catalog, Lineage & Quality 15: Knowledge Mgmt & Enterprise Search 16: Knowledge Capture & Key Personnel Risk 17: NLP Query & Conversational Analytics 26: Knowledge Graph & GraphRAG | Enterprise Architecture |  | Zero "Unknown" AI agents; 70%+ data classified | Not Started | SFS Internal
C20 | Data Classification Data Lineage |  | Setup a fund to implement RAG pipeline | TBD | 13: Data Catalog, Lineage & Quality 15: Knowledge Mgmt & Enterprise Search 16: Knowledge Capture & Key Personnel Risk 26: Knowledge Graph & GraphRAG | Enterprise Architecture |  | Zero "Unknown" AI agents; 70%+ data classified | Not Started | SFS Internal
Legal, Compliance & Regulatory Controls
C21 | Legal, Compliance & Regulatory Controls | Ensure Compliance with Regulatory Statutes. | Ensure encryption at rest and in transit. | 04/03/2026 | 26: Knowledge Graph & GraphRAG | AI CoE / AI Working Group |  | 100% AI incidents follow documented procedures within 4 hrs | Not Started | SFS Internal
C22 | Legal, Compliance & Regulatory Controls |  | Maintain audit logs for all data access and changes. | TBD |  |  |  | 100% AI incidents follow documented procedures within 4 hrs | Not Started | SFS Internal
C23 | Legal, Compliance & Regulatory Controls |  | Process to ensure compliance with Regulations. | TBD |  |  |  | 100% AI incidents follow documented procedures within 4 hrs | Not Started | SFS Internal
Financial
C24 | Financial | Cost Attribution | Assign each AI TCO to the sponsored BU. | 04/03/2026 | 11: AI Cost Management & Metering | AI Working Group Committee |  | Recovery of $4.5M in redundant spend; 100% AI cost attributed | Not Started | SFS Internal
Metadata Management
C25 | Metadata Management | Ensure all structured have associated metadata | Assign retention, classification, or compliance policy to all data. | 4/3 - 4/24/2026 | 14: Metadata, Taxonomy & Knowledge Architecture | Enterprise Architecture |  | Zero "Unknown" AI agents; complete asset visibility | Not Started | SFS Internal
Vendor Management Policies & Engagement process
C26 | Vendor Management Policies & Engagement process | Establish a clear process for Tool evaluation and Vendor Engagement. | Assess Vector Databases, Monitoring and logging tools, Model assessment tools, PII detection tools, Model Drift detection tools, etc. | 4/10 – 5/1/2026 | 11: AI Cost Management & Metering 29: ROI Measurement & 2027 Planning | AI Working Group Committee |  | 100% AI incidents follow documented procedures within 4 hrs | Not Started | SFS Internal
Incident Response
C27 | Incident Response | AI incident response playbook | Processes & Tools to manage model failures, bias incidents, hallucinations, data leakage, and adversarial attacks. | 4/17 – 5/8/2026 | 9e: AI Incident Response & Compliance | Enterprise Architecture |  | 100% AI incidents follow documented procedures within 4 hrs | Not Started | SFS Internal
DevSecOps
C28 | DevSecOps |  | Canary / Blue-Green deployment to limit blast radius. | 5/15 – 5/29/2026 | 20: AI-SDLC Workflow Enhancement 23: API & Integration Architecture | Mike Calaway |  | 100% AI incidents follow documented procedures within 4 hrs | Not Started | SFS Internal
C29 | DevSecOps | Estaboish Deployment Patterns | Rollback & Recovery Procedure. | 04/24/2026 | 9b: Risk Tiering & Agent Lifecycle 9e: AI Incident Response & Compliance 20: AI-SDLC Workflow Enhancement | Mike Calaway |  | 100% AI incidents follow documented procedures within 4 hrs | Not Started | SFS Internal
C30 | DevSecOps |  | Shadow mode deployment (run along side legacy before cutover) | 04/24/2026 | 20: AI-SDLC Workflow Enhancement | Mike Calaway |  | 100% AI incidents follow documented procedures within 4 hrs | Not Started | SFS Internal
Monitoring & Audit
C31 | Monitoring & Audit | Best Practices in Monitoring to ensure smooth auditing process | Accuracy & Quality Metrics. | 6/5 – 7/31/2026 | 9b: Risk Tiering & Agent Lifecycle 24: MLOps & Model Governance 28: AI Monitoring & Observability | Enterprise Architecture / Eric G. (role TBD) |  | Zero "Unknown" AI agents; complete token visibility | Not Started | SFS Internal
C32 | Monitoring & Audit |  | Data & Concept Drift Detection. | 04/24/2026 | 24: MLOps & Model Governance | Enterprise Architecture / Eric G. (role TBD) |  | Zero "Unknown" AI agents; complete token visibility | Not Started | SFS Internal
C33 | Monitoring & Audit |  | Prediction and Agentic Performance Monitoring | TBD | 24: MLOps & Model Governance 27: Remarketing, Research & Predictive Analytics | Enterprise Architecture / Eric G. (role TBD) |  | Zero "Unknown" AI agents; complete token visibility | Not Started | SFS Internal
Monitoring & Audit
C34 | Monitoring & Audit | Best Practices in Monitoring to ensure smooth auditing process | Ops & Infra Monitoring | 6/5 – 7/31/2026 | 27: Remarketing, Research & Predictive Analytics 28: AI Monitoring & Observability 29: ROI Measurement & 2027 Planning | AI CoE / AI Working Group |  | Zero "Unknown" AI agents; complete token visibility | Not Started | SFS Internal
C35 | Monitoring & Audit |  | Uptime, Latency & SLA monitoring | TBD |  | AI Working Group Committee |  | Zero "Unknown" AI agents; complete token visibility | Not Started | SFS Internal
C36 | Monitoring & Audit |  | Resource Utilization (CPU, GPU, Memory, etc.) | TBD |  |  |  | Zero "Unknown" AI agents; complete token visibility | Not Started | SFS Internal
Monitoring & Audit
C37 | Monitoring & Audit | Best Practices in Monitoring to ensure smooth auditing process | Token cost monitoring | 6/5 – 7/31/2026 | 28: AI Monitoring & Observability | Enterprise Architecture / Eric G. (role TBD) |  | Zero "Unknown" AI agents; complete token visibility | Not Started | SFS Internal
C38 | Monitoring & Audit |  | Autoscaling Governance | TBD |  |  |  | Zero "Unknown" AI agents; complete token visibility | Not Started | SFS Internal
C39 | Monitoring & Audit |  | Pipeline Monitoring | TBD | 22: ETL & Data Pipeline Modernization 24: MLOps & Model Governance 25: Real-Time Intelligence 28: AI Monitoring & Observability | Enterprise Architecture / IT Ops |  | Zero "Unknown" AI agents; complete token visibility | Not Started | SFS Internal
Model Validation
C40 | Model Validation | Enable live testing of systems for specific measures & threats. | Functional Testing, Adversarial Robustness Testing (Prompt Injection) | 8/7 – 8/28/2026 | 21: Test Automation & QA AI | Dev Team / QA Lead |  | Zero "Unknown" AI agents; complete asset visibility | Not Started | SFS Internal
C41 | Model Validation |  | Fairness & Bias assessment | TBD | 21: Test Automation & QA AI | Dev Team / QA Lead |  | Zero "Unknown" AI agents; complete asset visibility | Not Started | SFS Internal
Configuration Management
C42 | Configuration Management | Set up formal configuration management | Version-Controle | 8/7 – 8/28/2026 | 21: Test Automation & QA AI 22: ETL & Data Pipeline Modernization 23: API & Integration Architecture | Dev Team / QA Lead |  | Zero "Unknown" AI agents; complete asset visibility | Not Started | SFS Internal
C43 | Configuration Management |  | Infrastructure as Code (IaC) - Reproducibility | TBD | 21: Test Automation & QA AI | Dev Team / QA Lead |  | Zero "Unknown" AI agents; complete asset visibility | Not Started | SFS Internal
C44 | Configuration Management |  | Dependency & Library Pinning (requirements.txt files) | TBD |  |  |  | Zero "Unknown" AI agents; complete asset visibility | Not Started | SFS Internal
Documentation
C45 | Documentation | Documentation updated automatically | Model Cards, Agent Cards | 9/4 – 9/11/2026 |  |  |  | Zero "Unknown" AI agents; complete asset visibility | Not Started | SFS Internal
C46 | Documentation |  | Description, Intended Use | TBD |  |  |  | Zero "Unknown" AI agents; complete asset visibility | Not Started | SFS Internal
C47 | Documentation |  | Detailed Documentation with Version Control (ReadMe) | TBD |  |  |  | Zero "Unknown" AI agents; complete asset visibility | Not Started | SFS Internal
Access Control
C48 | Access Control | Enterprise-wide access control for all applications | Role-Based Access Control (RBAC), Attribute-Based Access Control (ABAC) | 9/18 – 10/11/2026 |  |  |  | Zero "Unknown" AI agents; complete asset visibility | Not Started | SFS Internal
C49 | Access Control |  | Azure RBAC (Fabric/OneLake). | TBD |  |  |  | Zero "Unknown" AI agents; complete asset visibility | Not Started | SFS Internal
EIS-RECOMMENDED INITIATIVES (Not in Original SFS Internal Roadmap)
C15,C16 | Customer-Facing AI | #004: Conversational IVR (natural language payment processing) | Implementation of: Conversational IVR (natural language payment processing) | TBD | 3: Payment & Voice Automation | AI Working Group | TBD |  | EIS Recommended | EIS Assessment
C15,C16 | Customer-Facing AI | #005: Payment voice automation (inbound/outbound, 30% call deflection) | $135K+/month potential savings (30K calls × $4.50/call × 50% automation) ¦ Offset significant portion of 200-person headcount growth through AI efficiency ¦ $295K+ annual value | Q2 2026 | 3: Payment & Voice Automation | Greg Shreve, Customer Service/Genesys, Customer Service / Genesys | Weeks 13-24 |  | EIS Recommended | EIS Assessment
C15,C16 | Customer-Facing AI | #006: Customer self-service chatbot (MySFS portal, FAQ, secured messaging) | Democratizes data access; reduces analyst bottleneck; enables faster business decisions | Q4 2026 | 4: Customer Self-Service & Chatbot | Customer Service | Months 13-14 |  | EIS Recommended | EIS Assessment
C15,C16 | Customer-Facing AI | #007: Internal conversational agent (HR/Benefits) | Implementation of: Internal conversational agent (HR/Benefits) | TBD | 4: Customer Self-Service & Chatbot | AI Working Group | TBD |  | EIS Recommended | EIS Assessment
C15,C16 | Customer-Facing AI | #008: End-of-Lease AI preparation (14→80-100 agents, call classification, chatbot) | Implementation of: End-of-Lease AI preparation (14→80-100 agents, call classification, chatbot) | Q3 2026 | 5: End-of-Lease AI Scaling | Danny Rodriguez/AI CoE, Danny Rodriguez / AI CoE | Weeks 25-36 |  | EIS Recommended | EIS Assessment
C15,C16 | Customer-Facing AI | #009: Collections AI augmentation (voice AI, predictive analytics for 400 FTE) | Implementation of: Collections AI augmentation (voice AI, predictive analytics for 400 FTE) | Q4 2026 | 6: Collections AI Augmentation | Greg Shreve/AI CoE, Greg Shreve / AI CoE | Weeks 37-48 |  | EIS Recommended | EIS Assessment
C15,C16 | Customer-Facing AI | #010: Wrongful repo prevention (real-time monitoring) | Implementation of: Wrongful repo prevention (real-time monitoring) | TBD | 6: Collections AI Augmentation | AI Working Group | TBD |  | EIS Recommended | EIS Assessment
C15,C16 | Customer-Facing AI | #011: Proactive customer engagement (predictive outreach, sentiment, payment risk) | Immediate ROI from sunk cost; enables real-time agent guidance and automated QA ¦ Enables autonomous agents for complex, high-value workflows ¦ $295K+ annual value from voice self-service | Q1 2026 | 7: Proactive Customer Engagement | Collections / CS, Ryan Miller/IT Ops | Immediate (Wks 1-8) |  | EIS Recommended | EIS Assessment
C8,C9,C13 | Customer-Facing AI | #012: Salesforce Agent Force implementation | Implementation of: Salesforce Agent Force implementation | TBD | 8: Salesforce Einstein / Agent Force | Enterprise Architecture | TBD |  | EIS Recommended | EIS Assessment
C8,C9,C13 | Customer-Facing AI | #013: Salesforce Data Cloud Analytics | Implementation of: Salesforce Data Cloud Analytics | TBD | 8: Salesforce Einstein / Agent Force | Enterprise Architecture | TBD |  | EIS Recommended | EIS Assessment
C8,C9,C13 | Customer-Facing AI | #014: Salesforce Einstein evaluation and activation | Enhanced agent productivity within Salesforce workflows; foundation for Agent Force | Q4 2026 | 8: Salesforce Einstein / Agent Force | Cassidy Hodge, Salesforce Team | Weeks 37-44 |  | EIS Recommended | EIS Assessment
C19,C20 | Knowledge & Search | #038: Deploy KCS methodology and content lifecycle management | Implementation of: Deploy KCS methodology and content lifecycle management | Q1 2026 | 15: Knowledge Mgmt & Enterprise Search | AI Working Group | Months 1-16 |  | EIS Recommended | EIS Assessment
C19,C20 | Knowledge & Search | #039: Deploy unified enterprise knowledge repository | Implementation of: Deploy unified enterprise knowledge repository | Q1 2026 | 15: Knowledge Mgmt & Enterprise Search | AI Working Group | Months 3-12 |  | EIS Recommended | EIS Assessment
C19,C20 | Knowledge & Search | #040: Document critical integrations and close documentation gaps | Implementation of: Document critical integrations and close documentation gaps | Q2 2026 | 15: Knowledge Mgmt & Enterprise Search | AI Working Group | Months 5-6 |  | EIS Recommended | EIS Assessment
C19,C20 | Knowledge & Search | #041: Governance velocity metric | Implementation of: Governance velocity metric | TBD | 15: Knowledge Mgmt & Enterprise Search | AI Working Group | TBD |  | EIS Recommended | EIS Assessment
C19,C20 | Knowledge & Search | #042: Implement federated/enterprise search (across SF, SharePoint, Tableau, Fabric) | Implementation of: Implement federated/enterprise search (across SF, SharePoint, Tableau, Fabric) | Q1 2026 | 15: Knowledge Mgmt & Enterprise Search | AI Working Group | Months 3-10 |  | EIS Recommended | EIS Assessment
C19,C20 | Knowledge & Search | #043: Knowledge RAG for agent assist | Genesys/Salesforce may suffice | TBD | 15: Knowledge Mgmt & Enterprise Search | AI Working Group | TBD |  | EIS Recommended | EIS Assessment
C19,C20 | Knowledge & Search | #044: Research automation for economics | High value but validation concerns | TBD | 15: Knowledge Mgmt & Enterprise Search | AI Working Group | TBD |  | EIS Recommended | EIS Assessment
C19,C20 | Knowledge & Search | #045: SME workflow integration | Implementation of: SME workflow integration | TBD | 15: Knowledge Mgmt & Enterprise Search | AI Working Group | TBD |  | EIS Recommended | EIS Assessment
C19,C20 | Knowledge & Search | #046: Test/SDLC items (cross-ref Clusters 20/21) | Medium impact, Medium effort | TBD | 15: Knowledge Mgmt & Enterprise Search | AI Working Group | TBD |  | EIS Recommended | EIS Assessment
C19,C20 | Knowledge & Search | #047: Vendor AI rationalization framework | Implementation of: Vendor AI rationalization framework | TBD | 15: Knowledge Mgmt & Enterprise Search | AI Working Group | TBD |  | EIS Recommended | EIS Assessment
C19,C20 | Knowledge & Search | #048: Document critical integrations and close documentation gaps | Implementation of: Document critical integrations and close documentation gaps | Q1 2026 | 16: Knowledge Capture & Key Personnel Risk | AI Working Group | Immediate (Wks 1-4) |  | EIS Recommended | EIS Assessment
C19,C20 | Knowledge & Search | #049: Knowledge capture from key personnel (Bobby, Adam, SMEs) | Implementation of: Knowledge capture from key personnel (Bobby, Adam, SMEs) | Q1 2026 | 16: Knowledge Capture & Key Personnel Risk | AI Working Group | Immediate (Wks 1-4) |  | EIS Recommended | EIS Assessment
C19 | Developer & Analyst Productivity | #050: Expand NLP query / Data Agents (Treasury pilot → enterprise EDW) | Democratizes data access; reduces simple query requests to BI team | Q1 2026 | 17: NLP Query & Conversational Analytics | Adam Rufford, Data/AI CoE, Data / AI CoE | Immediate (Wks 1-36) |  | EIS Recommended | EIS Assessment
C11 | Developer & Analyst Productivity | #051: AI-assisted SQL generation for BI team (schema-aware LLM) | 40-60% productivity gain | Q1 2026 | 18: BI & SQL AI Productivity | BI Team/EIS, BI Team | Weeks 4-12 |  | EIS Recommended | EIS Assessment
C11 | Developer & Analyst Productivity | #052: BI migration support (Tableau→Power BI, legacy query translation) | Implementation of: BI migration support (Tableau→Power BI, legacy query translation) | Q1-Q2 2026 | 18: BI & SQL AI Productivity | Dev Team / QA Lead | Q1-Q2 2026 |  | EIS Recommended | EIS Assessment
C11 | Developer & Analyst Productivity | #053: Query performance analyzer | Reduces IT alerts, infrastructure strain, troubleshooting time | Q1-Q2 2026 | 18: BI & SQL AI Productivity | Dev Team / QA Lead | Q1-Q2 2026 |  | EIS Recommended | EIS Assessment
C11 | Developer & Analyst Productivity | #054: Report discovery and reuse engine (semantic search across existing reports) | Eliminates duplicate work; accelerates new report development | Q1 2026 | 18: BI & SQL AI Productivity | Dev Team / QA Lead | Weeks 4-9 |  | EIS Recommended | EIS Assessment
C8,C9 | Developer & Analyst Productivity | #055: GitHub Copilot enterprise deployment (IDE-integrated AI for all dev teams) | $204K+ from auto-summarization | Q1 2026 | 19: Developer AI Tools | Nader Afshar, Dev Teams/Security, Dev Teams / Security | Weeks 3-32 |  | EIS Recommended | EIS Assessment
C28,C29,C30 | Developer & Analyst Productivity | #056: Data: AI-assisted data validation framework | Implementation of: Data: AI-assisted data validation framework | TBD | 20: AI-SDLC Workflow Enhancement | Mike Calaway | TBD |  | EIS Recommended | EIS Assessment
C28,C29,C30 | Developer & Analyst Productivity | #057: Data: CI/CD pipeline standardization | Implementation of: Data: CI/CD pipeline standardization | TBD | 20: AI-SDLC Workflow Enhancement | Mike Calaway | TBD |  | EIS Recommended | EIS Assessment
C28,C29,C30 | Developer & Analyst Productivity | #058: Data: Code review and standards enforcement | Implementation of: Data: Code review and standards enforcement | TBD | 20: AI-SDLC Workflow Enhancement | Mike Calaway | TBD |  | EIS Recommended | EIS Assessment
C28,C29,C30 | Developer & Analyst Productivity | #059: Data: Deployment governance and release management | Implementation of: Data: Deployment governance and release management | TBD | 20: AI-SDLC Workflow Enhancement | Mike Calaway | TBD |  | EIS Recommended | EIS Assessment
C28,C29,C30 | Developer & Analyst Productivity | #060: Data: Dual-commit workflow automation (Fabric/SSDT) | Implementation of: Data: Dual-commit workflow automation (Fabric/SSDT) | TBD | 20: AI-SDLC Workflow Enhancement | Mike Calaway | TBD |  | EIS Recommended | EIS Assessment
C28,C29,C30 | Developer & Analyst Productivity | #061: Data: Migration parity validation (SSIS→Fabric) | Implementation of: Data: Migration parity validation (SSIS→Fabric) | TBD | 20: AI-SDLC Workflow Enhancement | Mike Calaway | TBD |  | EIS Recommended | EIS Assessment
C28,C29,C30 | Developer & Analyst Productivity | #062: Data: Work intake and requirements quality | Implementation of: Data: Work intake and requirements quality | TBD | 20: AI-SDLC Workflow Enhancement | Mike Calaway | TBD |  | EIS Recommended | EIS Assessment
C28,C29,C30 | Developer & Analyst Productivity | #063: Integration: AI coding assistants for new Azure API development | Implementation of: Integration: AI coding assistants for new Azure API development | TBD | 20: AI-SDLC Workflow Enhancement | Mike Calaway | TBD |  | EIS Recommended | EIS Assessment
C28,C29,C30 | Developer & Analyst Productivity | #064: Integration: AI-assisted migration code generation (MuleSoft→Azure) | Implementation of: Integration: AI-assisted migration code generation (MuleSoft→Azure) | TBD | 20: AI-SDLC Workflow Enhancement | Mike Calaway | TBD |  | EIS Recommended | EIS Assessment
C28,C29,C30 | Developer & Analyst Productivity | #065: Integration: AI-generated APIM policies and config | Implementation of: Integration: AI-generated APIM policies and config | TBD | 20: AI-SDLC Workflow Enhancement | Mike Calaway | TBD |  | EIS Recommended | EIS Assessment
C28,C29,C30 | Developer & Analyst Productivity | #066: Integration: API parity testing (MuleSoft vs Azure) | Implementation of: Integration: API parity testing (MuleSoft vs Azure) | TBD | 20: AI-SDLC Workflow Enhancement | Mike Calaway | TBD |  | EIS Recommended | EIS Assessment
C28,C29,C30 | Developer & Analyst Productivity | #067: Integration: CI/CD pipeline YAML generation | Implementation of: Integration: CI/CD pipeline YAML generation | TBD | 20: AI-SDLC Workflow Enhancement | Mike Calaway | TBD |  | EIS Recommended | EIS Assessment
C28,C29,C30 | Developer & Analyst Productivity | #068: Integration: Discovery and current-state documentation | Implementation of: Integration: Discovery and current-state documentation | TBD | 20: AI-SDLC Workflow Enhancement | Mike Calaway | TBD |  | EIS Recommended | EIS Assessment
C28,C29,C30 | Developer & Analyst Productivity | #069: Integration: Story quality for integration architects | Implementation of: Integration: Story quality for integration architects | TBD | 20: AI-SDLC Workflow Enhancement | Mike Calaway | TBD |  | EIS Recommended | EIS Assessment
C28,C29,C30 | Developer & Analyst Productivity | #070: Integration: Terraform/IaC generation | Implementation of: Integration: Terraform/IaC generation | TBD | 20: AI-SDLC Workflow Enhancement | Mike Calaway | TBD |  | EIS Recommended | EIS Assessment
C28,C29,C30 | Developer & Analyst Productivity | #071: Salesforce: AI coding tools (Apex, LWC, Flows) | Implementation of: Salesforce: AI coding tools (Apex, LWC, Flows) | TBD | 20: AI-SDLC Workflow Enhancement | Mike Calaway | TBD |  | EIS Recommended | EIS Assessment
C28,C29,C30 | Developer & Analyst Productivity | #072: Salesforce: Architecture diagrams generation | Implementation of: Salesforce: Architecture diagrams generation | TBD | 20: AI-SDLC Workflow Enhancement | Mike Calaway | TBD |  | EIS Recommended | EIS Assessment
C28,C29,C30 | Developer & Analyst Productivity | #073: Salesforce: Code review against standards | Implementation of: Salesforce: Code review against standards | TBD | 20: AI-SDLC Workflow Enhancement | Mike Calaway | TBD |  | EIS Recommended | EIS Assessment
C28,C29,C30 | Developer & Analyst Productivity | #074: Salesforce: Documentation drift detection | Implementation of: Salesforce: Documentation drift detection | TBD | 20: AI-SDLC Workflow Enhancement | Mike Calaway | TBD |  | EIS Recommended | EIS Assessment
C28,C29,C30 | Developer & Analyst Productivity | #075: Salesforce: Story quality validation | Implementation of: Salesforce: Story quality validation | TBD | 20: AI-SDLC Workflow Enhancement | Mike Calaway | TBD |  | EIS Recommended | EIS Assessment
C40,C41,C42,C43 | Developer & Analyst Productivity | #076: AI-assisted test case generation (Jira→AI→Spira pipeline) | 'Significant productivity gain' per testing team; enables scaling without proportional headcount ¦ Medium impact, Low effort ¦ High impact, High effort | Q1 2026 | 21: Test Automation & QA AI | Dev Team / QA Lead | Immediate (Wks 1-12) |  | EIS Recommended | EIS Assessment
C40,C41,C42,C43 | Developer & Analyst Productivity | #077: AI-driven test impact analysis (code→test mapping, risk-based regression) | High impact, Medium effort ¦ High impact, High effort ¦ Very High impact, Very High effort | Q1 2026 | 21: Test Automation & QA AI | Dev Team / QA Lead | Immediate (Wks 1-12) |  | EIS Recommended | EIS Assessment
C40,C41,C42,C43 | Developer & Analyst Productivity | #078: Bug pattern analysis and root cause analysis | Medium impact, Low effort ¦ Medium impact, Medium effort ¦ High impact, High effort | Q1 2026 | 21: Test Automation & QA AI | Dev Team / QA Lead | Immediate (Wks 1-1) |  | EIS Recommended | EIS Assessment
C40,C41,C42,C43 | Developer & Analyst Productivity | #079: Continuous testing intelligence dashboard | High impact, High effort | TBD | 21: Test Automation & QA AI | Dev Team / QA Lead | TBD |  | EIS Recommended | EIS Assessment
C40,C41,C42,C43 | Developer & Analyst Productivity | #080: Dedicated test data management | Prevents false failures and debugging waste | Q2 2026 | 21: Test Automation & QA AI | Dev Team / QA Lead | Weeks 13-16 |  | EIS Recommended | EIS Assessment
C40,C41,C42,C43 | Developer & Analyst Productivity | #081: Enhanced Copilot prompt template for test case generation | High impact, Low effort ¦ Low-effort, high-impact; no procurement needed ¦ 30-50% improvement in output consistency | Q1 2026 | 21: Test Automation & QA AI | QA / Corinne Anderson | Immediate (Wks 1-4) |  | EIS Recommended | EIS Assessment
C40,C41,C42,C43 | Developer & Analyst Productivity | #082: Mandate data-test-id attributes | Reduce automation maintenance overhead by ~50% | Q1 2026 | 21: Test Automation & QA AI | QA / Dev Teams | Immediate (Wks 1-20) |  | EIS Recommended | EIS Assessment
C40,C41,C42,C43 | Developer & Analyst Productivity | #083: Measure time savings and quality impact | Implementation of: Measure time savings and quality impact | Q1 2026 | 21: Test Automation & QA AI | Dev Team / QA Lead | Weeks 7-8 |  | EIS Recommended | EIS Assessment
C40,C41,C42,C43 | Developer & Analyst Productivity | #084: Pre-deployment merge validation | High impact, Medium effort | TBD | 21: Test Automation & QA AI | Dev Team / QA Lead | TBD |  | EIS Recommended | EIS Assessment
C40,C41,C42,C43 | Developer & Analyst Productivity | #085: Self-healing test locators | 41% → 70%+ test automation coverage ¦ Very High impact, Very High effort | Q2 2026 | 21: Test Automation & QA AI | QA/EIS | Weeks 13-20 |  | EIS Recommended | EIS Assessment
C40,C41,C42,C43 | Developer & Analyst Productivity | #086: Shift automation left (QA environment, sprint N+1) | Earlier defect detection reduces cost of fixes | Q2 2026 | 21: Test Automation & QA AI | Dev Team / QA Lead | Weeks 13-16 |  | EIS Recommended | EIS Assessment
C39,C42 | Platform & Infrastructure | #087: Complete EDW migration to Fabric | Implementation of: Complete EDW migration to Fabric | Q2 2026 | 22: ETL & Data Pipeline Modernization | Enterprise Architecture / IT Ops | Q2 2026 |  | EIS Recommended | EIS Assessment
C39,C42 | Platform & Infrastructure | #088: Enterprise migration coordination | Implementation of: Enterprise migration coordination | Q3 2026 | 22: ETL & Data Pipeline Modernization | Enterprise Architecture / IT Ops | Months 7-8 |  | EIS Recommended | EIS Assessment
C39,C42 | Platform & Infrastructure | #089: Platform integration (Snowflake mirroring) | Implementation of: Platform integration (Snowflake mirroring) | TBD | 22: ETL & Data Pipeline Modernization | Enterprise Architecture / IT Ops | TBD |  | EIS Recommended | EIS Assessment
C39,C42 | Platform & Infrastructure | #090: SSIS modernization with AI assistance (600+ packages → Fabric pipelines) | Accelerates legacy modernization; reduces manual coding effort by 50%+ | Q1 2026 | 22: ETL & Data Pipeline Modernization | Enterprise Data Mgmt | Months 3-4 |  | EIS Recommended | EIS Assessment
C28,C42 | Platform & Infrastructure | #091: API integration documentation and unified data access | Implementation of: API integration documentation and unified data access | TBD | 23: API & Integration Architecture | Enterprise Architecture / IT Ops | TBD |  | EIS Recommended | EIS Assessment
C28,C42 | Platform & Infrastructure | #092: Hybrid orchestration architecture (API gateway + event-driven) | Implementation of: Hybrid orchestration architecture (API gateway + event-driven) | TBD | 23: API & Integration Architecture | Enterprise Architecture / IT Ops | TBD |  | EIS Recommended | EIS Assessment
C28,C42 | Platform & Infrastructure | #093: MCP implementation (Model Context Protocol, phased rollout) | Implementation of: MCP implementation (Model Context Protocol, phased rollout) | Q1-Q4 2026 | 23: API & Integration Architecture | Enterprise Architecture / IT Ops | Q1-Q4 2026 |  | EIS Recommended | EIS Assessment
C28,C42 | Platform & Infrastructure | #094: MuleSoft → Azure APIM migration | Implementation of: MuleSoft → Azure APIM migration | TBD | 23: API & Integration Architecture | Enterprise Architecture / IT Ops | TBD |  | EIS Recommended | EIS Assessment
C28,C42 | Platform & Infrastructure | #095: Unified agent desktop (Genesys + Salesforce single pane) | Implementation of: Unified agent desktop (Genesys + Salesforce single pane) | TBD | 23: API & Integration Architecture | Enterprise Architecture / IT Ops | TBD |  | EIS Recommended | EIS Assessment
C39 | Platform & Infrastructure | #099: Activate Fabric real-time intelligence (Eventstreams, KQL, Data Activator) | Implementation of: Activate Fabric real-time intelligence (Eventstreams, KQL, Data Activator) | TBD | 25: Real-Time Intelligence | Enterprise Architecture / IT Ops | TBD |  | EIS Recommended | EIS Assessment
C19,C20,C21 | Advanced Use Cases & Planning | #100: Fabric ontology features (evaluate as they mature) | Implementation of: Fabric ontology features (evaluate as they mature) | TBD | 26: Knowledge Graph & GraphRAG | AI CoE / AI Working Group | TBD |  | EIS Recommended | EIS Assessment
C19,C20,C21 | Advanced Use Cases & Planning | #101: GraphRAG for document intelligence | Implementation of: GraphRAG for document intelligence | TBD | 26: Knowledge Graph & GraphRAG | AI CoE / AI Working Group | TBD |  | EIS Recommended | EIS Assessment
C19,C20,C21 | Advanced Use Cases & Planning | #102: Knowledge graph implementation (data relationships, system dependencies) | Implementation of: Knowledge graph implementation (data relationships, system dependencies) | Q4 2026 | 26: Knowledge Graph & GraphRAG | Data/AI CoE, Data / AI CoE | Weeks 40-48 |  | EIS Recommended | EIS Assessment
C33,C34 | Advanced Use Cases & Planning | #103: AI-powered project prioritization (40-50 project backlog) | Implementation of: AI-powered project prioritization (40-50 project backlog) | TBD | 27: Remarketing, Research & Predictive Analytics | AI CoE / AI Working Group | TBD |  | EIS Recommended | EIS Assessment
C33,C34 | Advanced Use Cases & Planning | #104: Document intelligence (contract analysis, form recognition) | Depends on DMS maturity | TBD | 27: Remarketing, Research & Predictive Analytics | AI CoE / AI Working Group | TBD |  | EIS Recommended | EIS Assessment
C33,C34 | Advanced Use Cases & Planning | #105: Predictive analytics (lifecycle models, portfolio analysis) | Implementation of: Predictive analytics (lifecycle models, portfolio analysis) | Q4 2026 | 27: Remarketing, Research & Predictive Analytics | Data Science / Risk | Weeks 40-48 |  | EIS Recommended | EIS Assessment
C33,C34 | Advanced Use Cases & Planning | #106: Remarketing decision engine (VIN-level pricing, channel optimization) | Implementation of: Remarketing decision engine (VIN-level pricing, channel optimization) | Q4 2026 | 27: Remarketing, Research & Predictive Analytics | Remarketing / AI CoE | Weeks 37-44 |  | EIS Recommended | EIS Assessment
C33,C34 | Advanced Use Cases & Planning | #107: Research automation for economics team | Implementation of: Research automation for economics team | TBD | 27: Remarketing, Research & Predictive Analytics | AI CoE / AI Working Group | TBD |  | EIS Recommended | EIS Assessment
C26,C34 | Advanced Use Cases & Planning | #110: 12-month roadmap phase summaries | Implementation of: 12-month roadmap phase summaries | Q1 2026 | 29: ROI Measurement & 2027 Planning | AI Working Group Committee | Weeks 1-36 |  | EIS Recommended | EIS Assessment
C26,C34 | Advanced Use Cases & Planning | #111: Business outcome targets | 30%+ call deflection ¦ $204K+ annual value ¦ 50% reduction | TBD | 29: ROI Measurement & 2027 Planning | AI Working Group Committee | TBD |  | EIS Recommended | EIS Assessment
C26,C34 | Advanced Use Cases & Planning | #112: ROI validation and 2027 planning | Implementation of: ROI validation and 2027 planning | Q4 2026 | 29: ROI Measurement & 2027 Planning | AI Governance Committee | Weeks 37-48 |  | EIS Recommended | EIS Assessment

## 5. Gantt - Strategic
SFS AI ROADMAP - 12-MONTH GANTT (STRATEGIC VIEW)
Cluster | Phase | Source | Mar | Apr | May | Jun | Jul | Aug | Sep | Oct | Nov
Customer-Facing AI
Genesys AI Platform Activation | Phase 1 | SFS + EIS | 2 init.
Genesys vs. Observe AI Resolution | Phase 1 | SFS + EIS | 1 init.
Payment & Voice Automation | Phase 3 | EIS | [6 empty] | 2 init.
Customer Self-Service & Chatbot | Phase 1 | EIS | 2 init.
End-of-Lease AI Scaling | Phase 3 | EIS | [6 empty] | 1 init.
Collections AI Augmentation | Phase 3 | EIS | [6 empty] | 2 init.
Proactive Customer Engagement | Phase 1 | EIS | 1 init.
Salesforce Einstein / Agent Force | Phase 3 | EIS | [6 empty] | 3 init.
Governance & Organization
AI Governance Structure | Phase 1 | SFS + EIS | 3 init.
Risk Tiering & Agent Lifecycle | Phase 1 | SFS + EIS | 2 init.
Agent Registry & AI Inventory | Phase 1 | SFS + EIS | 2 init.
Shadow AI Remediation & Approved Tools | Phase 1 | SFS + EIS | 4 init.
AI Incident Response & Compliance | Phase 2 | SFS + EIS |  |  |  | 3 init.
AI Center of Excellence | Phase 3 | SFS + EIS | [6 empty] | 2 init.
AI Cost Management & Metering | Phase 3 | SFS + EIS | [6 empty] | 1 init.
Data Foundation
Data Classification & Purview | Phase 1 | SFS + EIS | 1 init.
Data Catalog, Lineage & Quality | Phase 1 | SFS + EIS | 3 init.
Metadata, Taxonomy & Knowledge Architecture | Phase 2 | SFS + EIS |  |  |  | 2 init.
Knowledge & Search
Knowledge Mgmt & Enterprise Search | Phase 1 | EIS | 10 init.
Knowledge Capture & Key Personnel Risk | Phase 1 | EIS | 2 init.
Developer & Analyst Productivity
NLP Query & Conversational Analytics | Phase 1 | EIS | 1 init.
BI & SQL AI Productivity | Phase 1 | EIS | 4 init.
Developer AI Tools | Phase 1 | EIS | 1 init.
AI-SDLC Workflow Enhancement | Phase 2 | EIS |  |  |  | 20 init.
Test Automation & QA AI | Phase 1 | EIS | 11 init.
Platform & Infrastructure
ETL & Data Pipeline Modernization | Phase 2 | EIS |  |  |  | 4 init.
API & Integration Architecture | Phase 3 | EIS | [6 empty] | 5 init.
MLOps & Model Governance | Phase 3 | SFS + EIS | [6 empty] | 3 init.
Real-Time Intelligence | Phase 3 | EIS | [6 empty] | 1 init.
Advanced Use Cases & Planning
Knowledge Graph & GraphRAG | Phase 3 | EIS | [6 empty] | 3 init.
Remarketing, Research & Predictive Analytics | Phase 3 | EIS | [6 empty] | 5 init.
AI Monitoring & Observability | Phase 3 | SFS + EIS | [6 empty] | 2 init.
ROI Measurement & 2027 Planning | Phase 1 | EIS | 3 init.

## 6. Gantt - Governance
SFS AI ROADMAP - GOVERNANCE MATURITY GANTT
Phase | Components | Source | Feb | Mar | Apr | May | Jun | Jul | Aug | Sep | Oct | Nov
Operating Model & Oversight | C1-C7 | SFS Internal | C1-C7
Financial Engineering | C8-C13 | SFS Internal |  | C8-C13
Genesys/Observe AI | C14-C16 | SFS + EIS |  | C14-C16
Data Classification | C17-C20 | SFS + EIS |  | C17-C20
Compliance & Cost | C21-C25 | SFS Internal |  |  | C21-C25
Vendor Management | C26 | SFS Internal |  |  | C26
Incident Response | C27 | SFS + EIS |  |  | C27
DevSecOps | C28-C30 | SFS Internal |  |  |  | C28-C30
Monitoring & Audit | C31-C39 | SFS + EIS |  |  |  |  | C31-C39
Model Validation | C40-C41 | SFS Internal | [6 empty] | C40-C41
Config Management | C42-C44 | SFS Internal | [6 empty] | C42-C44
Documentation | C45-C47 | SFS Internal | [7 empty] | C45-C47
Access Control | C48-C51 | SFS Internal | [7 empty] | C48-C51
EIS-Recommended Initiatives (by cluster)
Payment & Voice Automation | Cluster 3 | EIS | [6 empty] | 2 init.
Customer Self-Service & Chatbot | Cluster 4 | EIS | 2 init.
End-of-Lease AI Scaling | Cluster 5 | EIS | [6 empty] | 1 init.
Collections AI Augmentation | Cluster 6 | EIS | [6 empty] | 2 init.
Proactive Customer Engagement | Cluster 7 | EIS | 1 init.
Salesforce Einstein / Agent Force | Cluster 8 | EIS | [6 empty] | 3 init.
Knowledge Mgmt & Enterprise Search | Cluster 15 | EIS | 10 init.
Knowledge Capture & Key Personnel Risk | Cluster 16 | EIS | 2 init.
NLP Query & Conversational Analytics | Cluster 17 | EIS | 1 init.
BI & SQL AI Productivity | Cluster 18 | EIS | 4 init.
Developer AI Tools | Cluster 19 | EIS | 1 init.
AI-SDLC Workflow Enhancement | Cluster 20 | EIS |  |  |  | 20 init.
Test Automation & QA AI | Cluster 21 | EIS | 11 init.
ETL & Data Pipeline Modernization | Cluster 22 | EIS |  |  |  | 4 init.
API & Integration Architecture | Cluster 23 | EIS | [6 empty] | 5 init.
Real-Time Intelligence | Cluster 25 | EIS | [6 empty] | 1 init.
Knowledge Graph & GraphRAG | Cluster 26 | EIS | [6 empty] | 3 init.
Remarketing, Research & Predictive Analytics | Cluster 27 | EIS | [6 empty] | 5 init.
ROI Measurement & 2027 Planning | Cluster 29 | EIS | 3 init.

## 7. Canonical Initiatives
SFS AI ROADMAP - 112 CANONICAL INITIATIVES (COMPLETE REFERENCE)
Full detail: source documents, section refs, raw timing, governance mapping
Phase | Strategic Theme | Cluster ID | Cluster Name | Canonical Initiative | Priority | Source Documents | Section Refs | Timing | Owner(s) | Risk Tier | Gov Component Ref | Source
Phase 1: Governance & Foundation (Q1 2026) | Theme 1: Knowledge Architecture Foundation | 16 | Knowledge Capture & Key Personnel Risk | #048: Document critical integrations and close documentation gaps | HIGH | 1.1.4: EIS-SFS-1.1.4-Infrastructure-MLOps-Assessment 1.5: EIS-SFS-1.5-KM-Framework AI Opps (Data): EIS-SFS-Data-AI-Opportunities | 1.1.4 §1.1.3 1.5 §1.5 AI Opps (Data) | Immediate (Wks 1-4) | AI Working Group |  | C19,C20 | EIS
Phase 1: Governance & Foundation (Q1 2026) | Theme 1: Knowledge Architecture Foundation | 16 | Knowledge Capture & Key Personnel Risk | #049: Knowledge capture from key personnel (Bobby, Adam, SMEs) | HIGH | 1.1.1: EIS-SFS-1.1.1-Fabric-Azure-AI-Analysis 1.1.4: EIS-SFS-1.1.4-Infrastructure-MLOps-Assessment 1.5: EIS-SFS-1.5-KM-Framework Recs Master: SFS-Final-Delivery-Recommendations-Master | 1.1.1 1.1.4 §1.1.3 1.5 §1.5 Recs Master | Immediate (Wks 1-4) | AI Working Group |  | C19,C20 | EIS
Phase 1: Governance & Foundation (Q1 2026) | Theme 1: Knowledge Architecture Foundation | 15 | Knowledge Mgmt & Enterprise Search | #038: Deploy KCS methodology and content lifecycle management | MEDIUM | 1.2: EIS-SFS-1.2-AI-Readiness-Assessment 1.5: EIS-SFS-1.5-KM-Framework | 1.2 §1.2 1.5 §1.5 | Months 1-16 | AI Working Group |  | C19,C20 | EIS
Phase 1: Governance & Foundation (Q1 2026) | Theme 1: Knowledge Architecture Foundation | 15 | Knowledge Mgmt & Enterprise Search | #039: Deploy unified enterprise knowledge repository | MEDIUM | 1.5: EIS-SFS-1.5-KM-Framework | 1.5 §1.5 | Months 3-12 | AI Working Group |  | C19,C20 | EIS
Phase 1: Governance & Foundation (Q1 2026) | Theme 1: Knowledge Architecture Foundation | 15 | Knowledge Mgmt & Enterprise Search | #040: Document critical integrations and close documentation gaps | MEDIUM | 1.5: EIS-SFS-1.5-KM-Framework | 1.1.4 §1.1.3 1.5 §1.5 AI Opps (Data) | Months 5-6 | AI Working Group |  | C19,C20 | EIS
Phase 1: Governance & Foundation (Q1 2026) | Theme 1: Knowledge Architecture Foundation | 15 | Knowledge Mgmt & Enterprise Search | #042: Implement federated/enterprise search (across SF, SharePoint, Tableau, Fabric) | MEDIUM | 1.5: EIS-SFS-1.5-KM-Framework | 1.5 §1.5 | Months 3-10 | AI Working Group |  | C19,C20 | EIS
Phase 1: Governance & Foundation (Q1 2026) | Theme 2: Operational AI Enablement | 23 | API & Integration Architecture | #094: MuleSoft → Azure APIM migration | CRITICAL | 1.2: EIS-SFS-1.2-AI-Readiness-Assessment 3.2: EIS-SFS-3.2-Technology-Recommendations Recs Master: SFS-Final-Delivery-Recommendations-Master | 1.2 §1.2 3.2 §3.2 Recs Master | TBD | Enterprise Architecture / IT Ops |  | C28,C42 | EIS
Phase 1: Governance & Foundation (Q1 2026) | Theme 2: Operational AI Enablement | 22 | ETL & Data Pipeline Modernization | #090: SSIS modernization with AI assistance (600+ packages → Fabric pipelines) | HIGH | 1.1.1: EIS-SFS-1.1.1-Fabric-Azure-AI-Analysis 1.1.2: EIS-SFS-1.1.2-Tech-Stack-Evaluation 1.1.3: EIS-SFS-1.1.3-Platform-Access-Gap-Analysis 1.5: EIS-SFS-1.5-KM-Framework Recs Master: SFS-Final-Delivery-Recommendations-Master | 1.1.1 1.1.2 §1.1.1 1.1.3 §1.1.2 1.5 §1.5 Recs Master | Months 3-4 | Enterprise Data Mgmt |  | C39,C42 | EIS
Phase 1: Governance & Foundation (Q1 2026) | Theme 2: Operational AI Enablement | 29 | ROI Measurement & 2027 Planning | #110: 12-month roadmap phase summaries | HIGH | Recs Master: SFS-Final-Delivery-Recommendations-Master | Recs Master | Weeks 1-36 | AI Working Group Committee |  | C26,C34 | EIS
Phase 1: Governance & Foundation (Q1 2026) | Theme 2: Operational AI Enablement | 23 | API & Integration Architecture | #093: MCP implementation (Model Context Protocol, phased rollout) | MEDIUM | 1.1.4: EIS-SFS-1.1.4-Infrastructure-MLOps-Assessment 3.2: EIS-SFS-3.2-Technology-Recommendations | 1.1.4 §1.1.3 3.2 §3.2 | Q1-Q4 2026 | Enterprise Architecture / IT Ops |  | C28,C42 | EIS
Phase 1: Governance & Foundation (Q1 2026) | Theme 3: Customer Experience Intelligence | 1 | Genesys AI Platform Activation | #001: Activate Genesys AI tokens (speech analytics, sentiment, agent copilot, predictive routing) | HIGH | 1.1.2: EIS-SFS-1.1.2-Tech-Stack-Evaluation 1.1.3: EIS-SFS-1.1.3-Platform-Access-Gap-Analysis 1.1.4: EIS-SFS-1.1.4-Infrastructure-MLOps-Assessment 3.1: EIS-SFS-3.1-Executive-Synthesis | 1.1.2 §1.1.1 1.1.3 §1.1.2 1.1.4 §1.1.3 3.1 §3.1 | Immediate (Wks 1-8) | Vic Chopra / Larry Burgess, Ryan Miller / IT Ops | Tier 2 | C14,C15,C16 | SFS + EIS
Phase 1: Governance & Foundation (Q1 2026) | Theme 3: Customer Experience Intelligence | 2 | Genesys vs. Observe AI Resolution | #003: Genesys vs. Observe AI evaluation and consolidation decision | HIGH | 1.1.2: EIS-SFS-1.1.2-Tech-Stack-Evaluation 1.1.4: EIS-SFS-1.1.4-Infrastructure-MLOps-Assessment 1.3: EIS-SFS-1.3-AI-Governance-Framework 3.1: EIS-SFS-3.1-Executive-Synthesis | 1.1.2 §1.1.1 1.1.4 §1.1.3 1.3 §1.3 3.1 §3.1 | Immediate (Wks 1-16) | Working Group, Steering Committee |  | C14,C15 | SFS + EIS
Phase 1: Governance & Foundation (Q1 2026) | Theme 3: Customer Experience Intelligence | 3 | Payment & Voice Automation | #005: Payment voice automation (inbound/outbound, 30% call deflection) | HIGH | 1.1.3: EIS-SFS-1.1.3-Platform-Access-Gap-Analysis 1.1.4: EIS-SFS-1.1.4-Infrastructure-MLOps-Assessment 1.2: EIS-SFS-1.2-AI-Readiness-Assessment 1.5: EIS-SFS-1.5-KM-Framework 3.1: EIS-SFS-3.1-Executive-Synthesis | 1.1.3 §1.1.2 1.1.4 §1.1.3 1.2 §1.2 1.5 §1.5 3.1 §3.1 | Weeks 13-24 | Greg Shreve, Customer Service/Genesys, Customer Service / Genesys | Tier 2 | C15,C16 | EIS
Phase 1: Governance & Foundation (Q1 2026) | Theme 3: Customer Experience Intelligence | 4 | Customer Self-Service & Chatbot | #006: Customer self-service chatbot (MySFS portal, FAQ, secured messaging) | HIGH | 1.1.3: EIS-SFS-1.1.3-Platform-Access-Gap-Analysis 1.2: EIS-SFS-1.2-AI-Readiness-Assessment 1.5: EIS-SFS-1.5-KM-Framework Recs Master: SFS-Final-Delivery-Recommendations-Master | 1.1.3 §1.1.2 1.2 §1.2 1.5 §1.5 Recs Master | Months 13-14 | Customer Service |  | C15,C16 | EIS
Phase 1: Governance & Foundation (Q1 2026) | Theme 3: Customer Experience Intelligence | 7 | Proactive Customer Engagement | #011: Proactive customer engagement (predictive outreach, sentiment, payment risk) | HIGH | 1.1.3: EIS-SFS-1.1.3-Platform-Access-Gap-Analysis 1.2: EIS-SFS-1.2-AI-Readiness-Assessment 1.5: EIS-SFS-1.5-KM-Framework 3.1: EIS-SFS-3.1-Executive-Synthesis | 1.1.3 §1.1.2 1.2 §1.2 1.5 §1.5 3.1 §3.1 | Immediate (Wks 1-8) | Collections / CS, Ryan Miller/IT Ops |  | C15,C16 | EIS
Phase 1: Governance & Foundation (Q1 2026) | Theme 4: Developer & Analyst Productivity | 21 | Test Automation & QA AI | #077: AI-driven test impact analysis (code→test mapping, risk-based regression) | CRITICAL | 1.1.3: EIS-SFS-1.1.3-Platform-Access-Gap-Analysis 2.2: EIS-SFS-2.2-Testing-AI-Optimization AI Opps (Salesforce): EIS-SFS-SF-AI-Opportunities | 1.1.3 §1.1.2 2.2 §2.2 AI Opps (Salesforce) | Immediate (Wks 1-12) | Dev Team / QA Lead |  | C40,C41,C42,C43 | EIS
Phase 1: Governance & Foundation (Q1 2026) | Theme 4: Developer & Analyst Productivity | 21 | Test Automation & QA AI | #082: Mandate data-test-id attributes | CRITICAL | 2.2: EIS-SFS-2.2-Testing-AI-Optimization 3.1: EIS-SFS-3.1-Executive-Synthesis | 2.2 §2.2 3.1 §3.1 | Immediate (Wks 1-20) | QA / Dev Teams |  | C40,C41,C42,C43 | EIS
Phase 1: Governance & Foundation (Q1 2026) | Theme 4: Developer & Analyst Productivity | 17 | NLP Query & Conversational Analytics | #050: Expand NLP query / Data Agents (Treasury pilot → enterprise EDW) | HIGH | 1.1.1: EIS-SFS-1.1.1-Fabric-Azure-AI-Analysis 1.1.3: EIS-SFS-1.1.3-Platform-Access-Gap-Analysis 1.1.4: EIS-SFS-1.1.4-Infrastructure-MLOps-Assessment 1.2: EIS-SFS-1.2-AI-Readiness-Assessment 1.5: EIS-SFS-1.5-KM-Framework 2.1: EIS-SFS-2.1-BI-Code-Creation-Optimization 3.1: EIS-SFS-3.1-Executive-Synthesis 3.2: EIS-SFS-3.2-Technology-Recommendations | 1.1.1 1.1.3 §1.1.2 1.1.4 §1.1.3 1.2 §1.2 1.5 §1.5 2.1 §2.1 3.1 §3.1 3.2 §3.2 | Immediate (Wks 1-36) | Adam Rufford, Data/AI CoE, Data / AI CoE | Tier 3 | C19 | EIS
Phase 1: Governance & Foundation (Q1 2026) | Theme 4: Developer & Analyst Productivity | 18 | BI & SQL AI Productivity | #051: AI-assisted SQL generation for BI team (schema-aware LLM) | HIGH | 1.1.4: EIS-SFS-1.1.4-Infrastructure-MLOps-Assessment 1.2: EIS-SFS-1.2-AI-Readiness-Assessment 1.5: EIS-SFS-1.5-KM-Framework 2.1: EIS-SFS-2.1-BI-Code-Creation-Optimization 3.1: EIS-SFS-3.1-Executive-Synthesis Recs Master: SFS-Final-Delivery-Recommendations-Master | 1.1.4 §1.1.3 1.2 §1.2 1.5 §1.5 2.1 §2.1 3.1 §3.1 Recs Master | Weeks 4-12 | BI Team/EIS, BI Team | Tier 3 | C11 | EIS
Phase 1: Governance & Foundation (Q1 2026) | Theme 4: Developer & Analyst Productivity | 18 | BI & SQL AI Productivity | #053: Query performance analyzer | HIGH | 2.1: EIS-SFS-2.1-BI-Code-Creation-Optimization | 2.1 §2.1 | Q1-Q2 2026 | Dev Team / QA Lead |  | C11 | EIS
Phase 1: Governance & Foundation (Q1 2026) | Theme 4: Developer & Analyst Productivity | 19 | Developer AI Tools | #055: GitHub Copilot enterprise deployment (IDE-integrated AI for all dev teams) | HIGH | 1.1.3: EIS-SFS-1.1.3-Platform-Access-Gap-Analysis 1.1.4: EIS-SFS-1.1.4-Infrastructure-MLOps-Assessment 1.2: EIS-SFS-1.2-AI-Readiness-Assessment 1.3: EIS-SFS-1.3-AI-Governance-Framework 1.5: EIS-SFS-1.5-KM-Framework 2.1: EIS-SFS-2.1-BI-Code-Creation-Optimization 3.1: EIS-SFS-3.1-Executive-Synthesis AI Opps (Data): EIS-SFS-Data-AI-Opportunities AI Opps (Integration): EIS-SFS-Integration-AI-Opportunities | 1.1.3 §1.1.2 1.1.4 §1.1.3 1.2 §1.2 1.3 §1.3 1.5 §1.5 2.1 §2.1 3.1 §3.1 AI Opps (Data) AI Opps (Integration) | Weeks 3-32 | Nader Afshar, Dev Teams/Security, Dev Teams / Security | Tier 3 | C8,C9 | EIS
Phase 1: Governance & Foundation (Q1 2026) | Theme 4: Developer & Analyst Productivity | 21 | Test Automation & QA AI | #076: AI-assisted test case generation (Jira→AI→Spira pipeline) | HIGH | 1.1.3: EIS-SFS-1.1.3-Platform-Access-Gap-Analysis 2.2: EIS-SFS-2.2-Testing-AI-Optimization AI Opps (Salesforce): EIS-SFS-SF-AI-Opportunities | 1.1.3 §1.1.2 2.2 §2.2 AI Opps (Salesforce) | Immediate (Wks 1-12) | Dev Team / QA Lead |  | C40,C41,C42,C43 | EIS
Phase 1: Governance & Foundation (Q1 2026) | Theme 4: Developer & Analyst Productivity | 21 | Test Automation & QA AI | #078: Bug pattern analysis and root cause analysis | HIGH | 1.1.3: EIS-SFS-1.1.3-Platform-Access-Gap-Analysis 2.2: EIS-SFS-2.2-Testing-AI-Optimization AI Opps (Salesforce): EIS-SFS-SF-AI-Opportunities | 1.1.3 §1.1.2 2.2 §2.2 AI Opps (Salesforce) | Immediate (Wks 1-1) | Dev Team / QA Lead |  | C40,C41,C42,C43 | EIS
Phase 1: Governance & Foundation (Q1 2026) | Theme 4: Developer & Analyst Productivity | 21 | Test Automation & QA AI | #081: Enhanced Copilot prompt template for test case generation | HIGH | 2.2: EIS-SFS-2.2-Testing-AI-Optimization 3.1: EIS-SFS-3.1-Executive-Synthesis | 2.2 §2.2 3.1 §3.1 | Immediate (Wks 1-4) | QA / Corinne Anderson | Tier 4 | C40,C41,C42,C43 | EIS
Phase 1: Governance & Foundation (Q1 2026) | Theme 4: Developer & Analyst Productivity | 18 | BI & SQL AI Productivity | #052: BI migration support (Tableau→Power BI, legacy query translation) | MEDIUM | 1.1.1: EIS-SFS-1.1.1-Fabric-Azure-AI-Analysis 2.1: EIS-SFS-2.1-BI-Code-Creation-Optimization | 1.1.1 2.1 §2.1 | Q1-Q2 2026 | Dev Team / QA Lead |  | C11 | EIS
Phase 1: Governance & Foundation (Q1 2026) | Theme 4: Developer & Analyst Productivity | 18 | BI & SQL AI Productivity | #054: Report discovery and reuse engine (semantic search across existing reports) | MEDIUM | 1.2: EIS-SFS-1.2-AI-Readiness-Assessment 2.1: EIS-SFS-2.1-BI-Code-Creation-Optimization | 1.2 §1.2 2.1 §2.1 | Weeks 4-9 | Dev Team / QA Lead |  | C11 | EIS
Phase 1: Governance & Foundation (Q1 2026) | Theme 5: Data Platform Modernization | 12 | Data Classification & Purview | #032: Deploy Purview for data classification (close 95% gap) | CRITICAL | 1.1.1: EIS-SFS-1.1.1-Fabric-Azure-AI-Analysis 1.1.2: EIS-SFS-1.1.2-Tech-Stack-Evaluation 1.1.3: EIS-SFS-1.1.3-Platform-Access-Gap-Analysis 1.1.4: EIS-SFS-1.1.4-Infrastructure-MLOps-Assessment 1.2: EIS-SFS-1.2-AI-Readiness-Assessment 1.3: EIS-SFS-1.3-AI-Governance-Framework 1.5: EIS-SFS-1.5-KM-Framework 3.1: EIS-SFS-3.1-Executive-Synthesis 3.2: EIS-SFS-3.2-Technology-Recommendations | 1.1.1 1.1.2 §1.1.1 1.1.3 §1.1.2 1.1.4 §1.1.3 1.2 §1.2 1.3 §1.3 1.5 §1.5 3.1 §3.1 3.2 §3.2 | Immediate (Wks 1-24) | Bobby Goodwin, Data Governance, Data Governance / Tony |  | C17,C18 | SFS + EIS
Phase 1: Governance & Foundation (Q1 2026) | Theme 5: Data Platform Modernization | 13 | Data Catalog, Lineage & Quality | #033: AI-powered data quality monitoring (anomaly detection, quality rules) | HIGH | 1.1.1: EIS-SFS-1.1.1-Fabric-Azure-AI-Analysis 1.1.3: EIS-SFS-1.1.3-Platform-Access-Gap-Analysis 1.2: EIS-SFS-1.2-AI-Readiness-Assessment 1.5: EIS-SFS-1.5-KM-Framework 2.1: EIS-SFS-2.1-BI-Code-Creation-Optimization | 1.1.1 1.1.3 §1.1.2 1.2 §1.2 1.5 §1.5 2.1 §2.1 | Months 5-6 | Enterprise Data Mgmt |  | C17,C18,C19,C20 | SFS + EIS
Phase 1: Governance & Foundation (Q1 2026) | Theme 5: Data Platform Modernization | 13 | Data Catalog, Lineage & Quality | #034: Data catalog and discovery (Purview catalog, business glossary, searchable) | MEDIUM | 1.1.1: EIS-SFS-1.1.1-Fabric-Azure-AI-Analysis 1.2: EIS-SFS-1.2-AI-Readiness-Assessment 1.5: EIS-SFS-1.5-KM-Framework 2.1: EIS-SFS-2.1-BI-Code-Creation-Optimization | 1.1.1 1.2 §1.2 1.5 §1.5 2.1 §2.1 | Weeks 4-9 | Enterprise Architecture |  | C17,C18,C19,C20 | SFS + EIS
Phase 1: Governance & Foundation (Q1 2026) | Theme 5: Data Platform Modernization | 13 | Data Catalog, Lineage & Quality | #035: Data lineage tracking (automated, all EDW pipelines) | MEDIUM | 1.5: EIS-SFS-1.5-KM-Framework | 1.5 §1.5 | Months 5-8 | Enterprise Architecture |  | C17,C18,C19,C20 | SFS + EIS
Phase 1: Governance & Foundation (Q1 2026) | Theme 5: Data Platform Modernization | 14 | Metadata, Taxonomy & Knowledge Architecture | #037: Unified metadata schema and enterprise taxonomy | MEDIUM | 1.2: EIS-SFS-1.2-AI-Readiness-Assessment 1.5: EIS-SFS-1.5-KM-Framework 3.1: EIS-SFS-3.1-Executive-Synthesis | 1.2 §1.2 1.5 §1.5 3.1 §3.1 | Weeks 4-12 | Bobby Goodwin/Data Team, Bobby Goodwin / Data |  | C17,C25 | SFS + EIS
Phase 1: Governance & Foundation (Q1 2026) | Theme 6: Governance Operationalization | 9a | AI Governance Structure | #015: AI Governance operationalization (policy→workflows, approval processes, enforcement) | CRITICAL | 1.1.4: EIS-SFS-1.1.4-Infrastructure-MLOps-Assessment 1.2: EIS-SFS-1.2-AI-Readiness-Assessment 3.2: EIS-SFS-3.2-Technology-Recommendations | 1.1.4 §1.1.3 1.2 §1.2 3.2 §3.2 | Weeks 1-12 | AI Governance Committee |  | C1,C2,C3,C4,C5,C6,C7 | SFS + EIS
Phase 1: Governance & Foundation (Q1 2026) | Theme 6: Governance Operationalization | 9a | AI Governance Structure | #016: Formalize three-tier governance structure (Steering Committee, Working Group, Task Forces) | HIGH | 1.3: EIS-SFS-1.3-AI-Governance-Framework 3.1: EIS-SFS-3.1-Executive-Synthesis | 1.3 §1.3 3.1 §3.1 | Immediate (Wks 1-2) | Ryan Miller / CDO |  | C1,C2,C3,C4,C5,C6,C7 | SFS + EIS
Phase 1: Governance & Foundation (Q1 2026) | Theme 6: Governance Operationalization | 9b | Risk Tiering & Agent Lifecycle | #018: Deploy risk tiering framework (Tier 1-4 with intake form) | HIGH | 1.3: EIS-SFS-1.3-AI-Governance-Framework 3.1: EIS-SFS-3.1-Executive-Synthesis Recs Master: SFS-Final-Delivery-Recommendations-Master | 1.3 §1.3 3.1 §3.1 Recs Master | Weeks 3-6 | Working Group |  | C29,C31 | SFS + EIS
Phase 1: Governance & Foundation (Q1 2026) | Theme 6: Governance Operationalization | 9c | Agent Registry & AI Inventory | #020: Build agent registry (central catalog of all AI agents) | HIGH | 1.1.4: EIS-SFS-1.1.4-Infrastructure-MLOps-Assessment 1.3: EIS-SFS-1.3-AI-Governance-Framework 3.1: EIS-SFS-3.1-Executive-Synthesis Recs Master: SFS-Final-Delivery-Recommendations-Master | 1.1.4 §1.1.3 1.3 §1.3 3.1 §3.1 Recs Master | Immediate (Wks 1-4) | Nader Afshar |  | C14 | SFS + EIS
Phase 1: Governance & Foundation (Q1 2026) | Theme 6: Governance Operationalization | 9d | Shadow AI Remediation & Approved Tools | #022: Design shadow IT request workflow | HIGH | 1.3: EIS-SFS-1.3-AI-Governance-Framework 3.1: EIS-SFS-3.1-Executive-Synthesis | 1.3 §1.3 3.1 §3.1 | Weeks 3-8 | Working Group / Tony |  | C8,C9,C10,C11 | SFS + EIS
Phase 1: Governance & Foundation (Q1 2026) | Theme 6: Governance Operationalization | 9d | Shadow AI Remediation & Approved Tools | #023: Provide sanctioned LLM access (replace shadow ChatGPT/Gemini) | HIGH | 1.1.1: EIS-SFS-1.1.1-Fabric-Azure-AI-Analysis 1.1.4: EIS-SFS-1.1.4-Infrastructure-MLOps-Assessment | 1.1.1 1.1.4 §1.1.3 | Immediate (Wks 1-2) | Enterprise Architecture |  | C8,C9,C10,C11 | SFS + EIS
Phase 1: Governance & Foundation (Q1 2026) | Theme 6: Governance Operationalization | 9d | Shadow AI Remediation & Approved Tools | #024: Publish approved AI tool list and establish intake process | HIGH | 1.1.2: EIS-SFS-1.1.2-Tech-Stack-Evaluation 1.1.4: EIS-SFS-1.1.4-Infrastructure-MLOps-Assessment 3.1: EIS-SFS-3.1-Executive-Synthesis | 1.1.2 §1.1.1 1.1.4 §1.1.3 3.1 §3.1 | Immediate (Wks 1-2) | Enterprise Architecture |  | C8,C9,C10,C11 | SFS + EIS
Phase 1: Governance & Foundation (Q1 2026) | Theme 6: Governance Operationalization | 10 | AI Center of Excellence | #030: Establish AI Center of Excellence (structure, staffing, reusable components) | HIGH | 1.1.1: EIS-SFS-1.1.1-Fabric-Azure-AI-Analysis 1.2: EIS-SFS-1.2-AI-Readiness-Assessment 1.5: EIS-SFS-1.5-KM-Framework 3.1: EIS-SFS-3.1-Executive-Synthesis | 1.1.1 1.2 §1.2 1.5 §1.5 3.1 §3.1 | Immediate (Wks 1-24) | CDO/Ryan Miller, Nader Afshar / CDO |  | C1,C5,C6,C7 | SFS + EIS
Phase 2: Quick Wins & Architecture (Q2 2026) | Theme 2: Operational AI Enablement | 22 | ETL & Data Pipeline Modernization | #087: Complete EDW migration to Fabric | MEDIUM | 3.2: EIS-SFS-3.2-Technology-Recommendations | 3.2 §3.2 | Q2 2026 | Enterprise Architecture / IT Ops |  | C39,C42 | EIS
Phase 2: Quick Wins & Architecture (Q2 2026) | Theme 2: Operational AI Enablement | 22 | ETL & Data Pipeline Modernization | #088: Enterprise migration coordination | MEDIUM | 1.5: EIS-SFS-1.5-KM-Framework | 1.5 §1.5 | Months 7-8 | Enterprise Architecture / IT Ops |  | C39,C42 | EIS
Phase 2: Quick Wins & Architecture (Q2 2026) | Theme 2: Operational AI Enablement | 24 | MLOps & Model Governance | #098: Reopen/govern AI Foundry | MEDIUM | 1.1.3: EIS-SFS-1.1.3-Platform-Access-Gap-Analysis | 1.1.3 §1.1.2 | Q2-Q3 2026 | Enterprise Architecture / Eric G. (role TBD) |  | C31,C32,C33,C39 | SFS + EIS
Phase 2: Quick Wins & Architecture (Q2 2026) | Theme 2: Operational AI Enablement | 26 | Knowledge Graph & GraphRAG | #102: Knowledge graph implementation (data relationships, system dependencies) | MEDIUM | 1.1.3: EIS-SFS-1.1.3-Platform-Access-Gap-Analysis 1.1.4: EIS-SFS-1.1.4-Infrastructure-MLOps-Assessment 1.2: EIS-SFS-1.2-AI-Readiness-Assessment 3.1: EIS-SFS-3.1-Executive-Synthesis | 1.1.3 §1.1.2 1.1.4 §1.1.3 1.2 §1.2 3.1 §3.1 | Weeks 40-48 | Data/AI CoE, Data / AI CoE | Tier 3 | C19,C20,C21 | EIS
Phase 2: Quick Wins & Architecture (Q2 2026) | Theme 2: Operational AI Enablement | 28 | AI Monitoring & Observability | #109: Agent/platform observability | MEDIUM | 1.1.1: EIS-SFS-1.1.1-Fabric-Azure-AI-Analysis 1.5: EIS-SFS-1.5-KM-Framework | 1.1.1 1.5 §1.5 | Months 11-12 | Enterprise Architecture / Eric G. (role TBD) |  | C31,C34,C37,C39 | SFS + EIS
Phase 2: Quick Wins & Architecture (Q2 2026) | Theme 3: Customer Experience Intelligence | 1 | Genesys AI Platform Activation | #002: Deploy Genesys Knowledge Workbench | MEDIUM | 1.1.3: EIS-SFS-1.1.3-Platform-Access-Gap-Analysis 1.1.4: EIS-SFS-1.1.4-Infrastructure-MLOps-Assessment | 1.1.3 §1.1.2 1.1.4 §1.1.3 | Q2-Q3 2026 | Customer Service |  | C14,C15,C16 | SFS + EIS
Phase 2: Quick Wins & Architecture (Q2 2026) | Theme 3: Customer Experience Intelligence | 8 | Salesforce Einstein / Agent Force | #014: Salesforce Einstein evaluation and activation | MEDIUM | 1.1.2: EIS-SFS-1.1.2-Tech-Stack-Evaluation 1.1.3: EIS-SFS-1.1.3-Platform-Access-Gap-Analysis 1.1.4: EIS-SFS-1.1.4-Infrastructure-MLOps-Assessment 1.2: EIS-SFS-1.2-AI-Readiness-Assessment | 1.1.2 §1.1.1 1.1.3 §1.1.2 1.1.4 §1.1.3 1.2 §1.2 | Weeks 37-44 | Cassidy Hodge, Salesforce Team |  | C8,C9,C13 | EIS
Phase 2: Quick Wins & Architecture (Q2 2026) | Theme 4: Developer & Analyst Productivity | 20 | AI-SDLC Workflow Enhancement | #056: Data: AI-assisted data validation framework | HIGH | AI Opps (Data): EIS-SFS-Data-AI-Opportunities | AI Opps (Data) | TBD | Mike Calaway |  | C28,C29,C30 | EIS
Phase 2: Quick Wins & Architecture (Q2 2026) | Theme 4: Developer & Analyst Productivity | 20 | AI-SDLC Workflow Enhancement | #057: Data: CI/CD pipeline standardization | HIGH | AI Opps (Data): EIS-SFS-Data-AI-Opportunities | AI Opps (Data) | TBD | Mike Calaway |  | C28,C29,C30 | EIS
Phase 2: Quick Wins & Architecture (Q2 2026) | Theme 4: Developer & Analyst Productivity | 20 | AI-SDLC Workflow Enhancement | #060: Data: Dual-commit workflow automation (Fabric/SSDT) | HIGH | AI Opps (Data): EIS-SFS-Data-AI-Opportunities | AI Opps (Data) | TBD | Mike Calaway |  | C28,C29,C30 | EIS
Phase 2: Quick Wins & Architecture (Q2 2026) | Theme 4: Developer & Analyst Productivity | 20 | AI-SDLC Workflow Enhancement | #063: Integration: AI coding assistants for new Azure API development | HIGH | AI Opps (Integration): EIS-SFS-Integration-AI-Opportunities | AI Opps (Integration) | TBD | Mike Calaway |  | C28,C29,C30 | EIS
Phase 2: Quick Wins & Architecture (Q2 2026) | Theme 4: Developer & Analyst Productivity | 20 | AI-SDLC Workflow Enhancement | #064: Integration: AI-assisted migration code generation (MuleSoft→Azure) | HIGH | AI Opps (Integration): EIS-SFS-Integration-AI-Opportunities | AI Opps (Integration) | TBD | Mike Calaway |  | C28,C29,C30 | EIS
Phase 2: Quick Wins & Architecture (Q2 2026) | Theme 4: Developer & Analyst Productivity | 20 | AI-SDLC Workflow Enhancement | #065: Integration: AI-generated APIM policies and config | HIGH | AI Opps (Integration): EIS-SFS-Integration-AI-Opportunities | AI Opps (Integration) | TBD | Mike Calaway |  | C28,C29,C30 | EIS
Phase 2: Quick Wins & Architecture (Q2 2026) | Theme 4: Developer & Analyst Productivity | 20 | AI-SDLC Workflow Enhancement | #070: Integration: Terraform/IaC generation | HIGH | AI Opps (Integration): EIS-SFS-Integration-AI-Opportunities | AI Opps (Integration) | TBD | Mike Calaway |  | C28,C29,C30 | EIS
Phase 2: Quick Wins & Architecture (Q2 2026) | Theme 4: Developer & Analyst Productivity | 20 | AI-SDLC Workflow Enhancement | #071: Salesforce: AI coding tools (Apex, LWC, Flows) | HIGH | AI Opps (Salesforce): EIS-SFS-SF-AI-Opportunities | AI Opps (Salesforce) | TBD | Mike Calaway |  | C28,C29,C30 | EIS
Phase 2: Quick Wins & Architecture (Q2 2026) | Theme 4: Developer & Analyst Productivity | 20 | AI-SDLC Workflow Enhancement | #073: Salesforce: Code review against standards | HIGH | AI Opps (Salesforce): EIS-SFS-SF-AI-Opportunities | AI Opps (Salesforce) | TBD | Mike Calaway |  | C28,C29,C30 | EIS
Phase 2: Quick Wins & Architecture (Q2 2026) | Theme 4: Developer & Analyst Productivity | 20 | AI-SDLC Workflow Enhancement | #075: Salesforce: Story quality validation | HIGH | AI Opps (Salesforce): EIS-SFS-SF-AI-Opportunities | AI Opps (Salesforce) | TBD | Mike Calaway |  | C28,C29,C30 | EIS
Phase 2: Quick Wins & Architecture (Q2 2026) | Theme 4: Developer & Analyst Productivity | 21 | Test Automation & QA AI | #079: Continuous testing intelligence dashboard | HIGH | 2.2: EIS-SFS-2.2-Testing-AI-Optimization | 2.2 §2.2 | TBD | Dev Team / QA Lead |  | C40,C41,C42,C43 | EIS
Phase 2: Quick Wins & Architecture (Q2 2026) | Theme 4: Developer & Analyst Productivity | 21 | Test Automation & QA AI | #084: Pre-deployment merge validation | HIGH | 2.2: EIS-SFS-2.2-Testing-AI-Optimization | 2.2 §2.2 | TBD | Dev Team / QA Lead |  | C40,C41,C42,C43 | EIS
Phase 2: Quick Wins & Architecture (Q2 2026) | Theme 4: Developer & Analyst Productivity | 21 | Test Automation & QA AI | #085: Self-healing test locators | HIGH | 1.1.3: EIS-SFS-1.1.3-Platform-Access-Gap-Analysis 1.2: EIS-SFS-1.2-AI-Readiness-Assessment 2.2: EIS-SFS-2.2-Testing-AI-Optimization AI Opps (Salesforce): EIS-SFS-SF-AI-Opportunities Recs Master: SFS-Final-Delivery-Recommendations-Master | 1.1.3 §1.1.2 1.2 §1.2 2.2 §2.2 AI Opps (Salesforce) Recs Master | Weeks 13-20 | QA/EIS |  | C40,C41,C42,C43 | EIS
Phase 2: Quick Wins & Architecture (Q2 2026) | Theme 4: Developer & Analyst Productivity | 21 | Test Automation & QA AI | #083: Measure time savings and quality impact | MEDIUM | 2.2: EIS-SFS-2.2-Testing-AI-Optimization | 2.2 §2.2 | Weeks 7-8 | Dev Team / QA Lead |  | C40,C41,C42,C43 | EIS
Phase 2: Quick Wins & Architecture (Q2 2026) | Theme 5: Data Platform Modernization | 14 | Metadata, Taxonomy & Knowledge Architecture | #036: Content inventory, tagging, and component model | MEDIUM | 1.2: EIS-SFS-1.2-AI-Readiness-Assessment 1.5: EIS-SFS-1.5-KM-Framework | 1.2 §1.2 1.5 §1.5 | Months 9-10 | Enterprise Architecture |  | C17,C25 | SFS + EIS
Phase 2: Quick Wins & Architecture (Q2 2026) | Theme 6: Governance Operationalization | 9e | AI Incident Response & Compliance | #026: Bank/regulatory compliance preparation (FFIEC alignment) | HIGH | 1.1.4: EIS-SFS-1.1.4-Infrastructure-MLOps-Assessment | 1.1.4 §1.1.3 | TBD | Enterprise Architecture |  | C27,C29 | SFS + EIS
Phase 2: Quick Wins & Architecture (Q2 2026) | Theme 6: Governance Operationalization | 9e | AI Incident Response & Compliance | #027: Draft AI incident response playbook (severity levels, escalation) | HIGH | 1.3: EIS-SFS-1.3-AI-Governance-Framework 3.1: EIS-SFS-3.1-Executive-Synthesis AI Opps (Data): EIS-SFS-Data-AI-Opportunities | 1.3 §1.3 3.1 §3.1 AI Opps (Data) | Weeks 6-18 | Working Group / Security |  | C27,C29 | SFS + EIS
Phase 3: Operational Maturity (Q3 2026) | Theme 1: Knowledge Architecture Foundation | 15 | Knowledge Mgmt & Enterprise Search | #041: Governance velocity metric | MEDIUM | 1.3: EIS-SFS-1.3-AI-Governance-Framework | 1.3 §1.3 | TBD | AI Working Group |  | C19,C20 | EIS
Phase 3: Operational Maturity (Q3 2026) | Theme 1: Knowledge Architecture Foundation | 15 | Knowledge Mgmt & Enterprise Search | #043: Knowledge RAG for agent assist | MEDIUM | 1.1.1: EIS-SFS-1.1.1-Fabric-Azure-AI-Analysis Recs Master: SFS-Final-Delivery-Recommendations-Master | 1.1.1 Recs Master | TBD | AI Working Group |  | C19,C20 | EIS
Phase 3: Operational Maturity (Q3 2026) | Theme 1: Knowledge Architecture Foundation | 15 | Knowledge Mgmt & Enterprise Search | #044: Research automation for economics | MEDIUM | 1.1.1: EIS-SFS-1.1.1-Fabric-Azure-AI-Analysis | 1.1.1 | TBD | AI Working Group |  | C19,C20 | EIS
Phase 3: Operational Maturity (Q3 2026) | Theme 1: Knowledge Architecture Foundation | 15 | Knowledge Mgmt & Enterprise Search | #045: SME workflow integration | MEDIUM | 1.2: EIS-SFS-1.2-AI-Readiness-Assessment | 1.2 §1.2 | TBD | AI Working Group |  | C19,C20 | EIS
Phase 3: Operational Maturity (Q3 2026) | Theme 1: Knowledge Architecture Foundation | 15 | Knowledge Mgmt & Enterprise Search | #046: Test/SDLC items (cross-ref Clusters 20/21) | MEDIUM | 2.2: EIS-SFS-2.2-Testing-AI-Optimization 3.2: EIS-SFS-3.2-Technology-Recommendations AI Opps (Data): EIS-SFS-Data-AI-Opportunities AI Opps (Integration): EIS-SFS-Integration-AI-Opportunities AI Opps (Salesforce): EIS-SFS-SF-AI-Opportunities | 2.2 §2.2 3.2 §3.2 AI Opps (Data) AI Opps (Integration) AI Opps (Salesforce) | TBD | AI Working Group |  | C19,C20 | EIS
Phase 3: Operational Maturity (Q3 2026) | Theme 1: Knowledge Architecture Foundation | 15 | Knowledge Mgmt & Enterprise Search | #047: Vendor AI rationalization framework | MEDIUM | Recs Master: SFS-Final-Delivery-Recommendations-Master | Recs Master | TBD | AI Working Group |  | C19,C20 | EIS
Phase 3: Operational Maturity (Q3 2026) | Theme 2: Operational AI Enablement | 28 | AI Monitoring & Observability | #108: AI monitoring dashboard (centralized performance, token consumption, cost allocation) | HIGH | 1.2: EIS-SFS-1.2-AI-Readiness-Assessment 3.1: EIS-SFS-3.1-Executive-Synthesis | 1.2 §1.2 3.1 §3.1 | Weeks 25-32 | AI CoE / IT Ops | Tier 3 | C31,C34,C37,C39 | SFS + EIS
Phase 3: Operational Maturity (Q3 2026) | Theme 2: Operational AI Enablement | 22 | ETL & Data Pipeline Modernization | #089: Platform integration (Snowflake mirroring) | MEDIUM | 1.1.1: EIS-SFS-1.1.1-Fabric-Azure-AI-Analysis | 1.1.1 | TBD | Enterprise Architecture / IT Ops |  | C39,C42 | EIS
Phase 3: Operational Maturity (Q3 2026) | Theme 2: Operational AI Enablement | 23 | API & Integration Architecture | #091: API integration documentation and unified data access | MEDIUM | 1.2: EIS-SFS-1.2-AI-Readiness-Assessment | 1.2 §1.2 | TBD | Enterprise Architecture / IT Ops |  | C28,C42 | EIS
Phase 3: Operational Maturity (Q3 2026) | Theme 2: Operational AI Enablement | 23 | API & Integration Architecture | #092: Hybrid orchestration architecture (API gateway + event-driven) | MEDIUM | 1.1.4: EIS-SFS-1.1.4-Infrastructure-MLOps-Assessment 3.2: EIS-SFS-3.2-Technology-Recommendations | 1.1.4 §1.1.3 3.2 §3.2 | TBD | Enterprise Architecture / IT Ops |  | C28,C42 | EIS
Phase 3: Operational Maturity (Q3 2026) | Theme 2: Operational AI Enablement | 23 | API & Integration Architecture | #095: Unified agent desktop (Genesys + Salesforce single pane) | MEDIUM | 1.1.3: EIS-SFS-1.1.3-Platform-Access-Gap-Analysis | 1.1.3 §1.1.2 | TBD | Enterprise Architecture / IT Ops |  | C28,C42 | EIS
Phase 3: Operational Maturity (Q3 2026) | Theme 2: Operational AI Enablement | 24 | MLOps & Model Governance | #096: Drift detection framework | MEDIUM | 1.2: EIS-SFS-1.2-AI-Readiness-Assessment | 1.2 §1.2 | TBD | Enterprise Architecture / Eric G. (role TBD) |  | C31,C32,C33,C39 | SFS + EIS
Phase 3: Operational Maturity (Q3 2026) | Theme 2: Operational AI Enablement | 24 | MLOps & Model Governance | #097: Formalize MLOps (ML Flow, Model Registry, experiment tracking) | MEDIUM | 1.1.1: EIS-SFS-1.1.1-Fabric-Azure-AI-Analysis 1.1.4: EIS-SFS-1.1.4-Infrastructure-MLOps-Assessment 3.2: EIS-SFS-3.2-Technology-Recommendations Recs Master: SFS-Final-Delivery-Recommendations-Master | 1.1.1 1.1.4 §1.1.3 3.2 §3.2 Recs Master | TBD | Enterprise Architecture / Eric G. (role TBD) |  | C31,C32,C33,C39 | SFS + EIS
Phase 3: Operational Maturity (Q3 2026) | Theme 2: Operational AI Enablement | 25 | Real-Time Intelligence | #099: Activate Fabric real-time intelligence (Eventstreams, KQL, Data Activator) | MEDIUM | 1.1.1: EIS-SFS-1.1.1-Fabric-Azure-AI-Analysis 1.1.3: EIS-SFS-1.1.3-Platform-Access-Gap-Analysis 1.2: EIS-SFS-1.2-AI-Readiness-Assessment | 1.1.1 1.1.3 §1.1.2 1.2 §1.2 | TBD | Enterprise Architecture / IT Ops |  | C39 | EIS
Phase 3: Operational Maturity (Q3 2026) | Theme 2: Operational AI Enablement | 26 | Knowledge Graph & GraphRAG | #100: Fabric ontology features (evaluate as they mature) | MEDIUM | 1.1.3: EIS-SFS-1.1.3-Platform-Access-Gap-Analysis | 1.1.3 §1.1.2 | TBD | AI CoE / AI Working Group |  | C19,C20,C21 | EIS
Phase 3: Operational Maturity (Q3 2026) | Theme 2: Operational AI Enablement | 26 | Knowledge Graph & GraphRAG | #101: GraphRAG for document intelligence | MEDIUM | Recs Master: SFS-Final-Delivery-Recommendations-Master | Recs Master | TBD | AI CoE / AI Working Group |  | C19,C20,C21 | EIS
Phase 3: Operational Maturity (Q3 2026) | Theme 2: Operational AI Enablement | 27 | Remarketing, Research & Predictive Analytics | #103: AI-powered project prioritization (40-50 project backlog) | MEDIUM | Recs Master: SFS-Final-Delivery-Recommendations-Master | Recs Master | TBD | AI CoE / AI Working Group |  | C33,C34 | EIS
Phase 3: Operational Maturity (Q3 2026) | Theme 2: Operational AI Enablement | 27 | Remarketing, Research & Predictive Analytics | #104: Document intelligence (contract analysis, form recognition) | MEDIUM | 1.1.1: EIS-SFS-1.1.1-Fabric-Azure-AI-Analysis | 1.1.1 | TBD | AI CoE / AI Working Group |  | C33,C34 | EIS
Phase 3: Operational Maturity (Q3 2026) | Theme 2: Operational AI Enablement | 27 | Remarketing, Research & Predictive Analytics | #107: Research automation for economics team | MEDIUM | 1.1.1: EIS-SFS-1.1.1-Fabric-Azure-AI-Analysis 1.1.3: EIS-SFS-1.1.3-Platform-Access-Gap-Analysis | 1.1.1 1.1.3 §1.1.2 | TBD | AI CoE / AI Working Group |  | C33,C34 | EIS
Phase 3: Operational Maturity (Q3 2026) | Theme 2: Operational AI Enablement | 29 | ROI Measurement & 2027 Planning | #111: Business outcome targets | MEDIUM | Recs Master: SFS-Final-Delivery-Recommendations-Master | Recs Master | TBD | AI Working Group Committee |  | C26,C34 | EIS
Phase 3: Operational Maturity (Q3 2026) | Theme 3: Customer Experience Intelligence | 5 | End-of-Lease AI Scaling | #008: End-of-Lease AI preparation (14→80-100 agents, call classification, chatbot) | HIGH | 1.2: EIS-SFS-1.2-AI-Readiness-Assessment 3.1: EIS-SFS-3.1-Executive-Synthesis Recs Master: SFS-Final-Delivery-Recommendations-Master | 1.2 §1.2 3.1 §3.1 Recs Master | Weeks 25-36 | Danny Rodriguez/AI CoE, Danny Rodriguez / AI CoE | Tier 2 | C15,C16 | EIS
Phase 3: Operational Maturity (Q3 2026) | Theme 3: Customer Experience Intelligence | 6 | Collections AI Augmentation | #009: Collections AI augmentation (voice AI, predictive analytics for 400 FTE) | HIGH | 1.2: EIS-SFS-1.2-AI-Readiness-Assessment 1.5: EIS-SFS-1.5-KM-Framework 3.1: EIS-SFS-3.1-Executive-Synthesis | 1.2 §1.2 1.5 §1.5 3.1 §3.1 | Weeks 37-48 | Greg Shreve/AI CoE, Greg Shreve / AI CoE | Tier 2 | C15,C16 | EIS
Phase 3: Operational Maturity (Q3 2026) | Theme 3: Customer Experience Intelligence | 3 | Payment & Voice Automation | #004: Conversational IVR (natural language payment processing) | MEDIUM | 1.1.3: EIS-SFS-1.1.3-Platform-Access-Gap-Analysis | 1.1.3 §1.1.2 | TBD | AI Working Group |  | C15,C16 | EIS
Phase 3: Operational Maturity (Q3 2026) | Theme 3: Customer Experience Intelligence | 4 | Customer Self-Service & Chatbot | #007: Internal conversational agent (HR/Benefits) | MEDIUM | 1.1.3: EIS-SFS-1.1.3-Platform-Access-Gap-Analysis | 1.1.3 §1.1.2 | TBD | AI Working Group |  | C15,C16 | EIS
Phase 3: Operational Maturity (Q3 2026) | Theme 3: Customer Experience Intelligence | 6 | Collections AI Augmentation | #010: Wrongful repo prevention (real-time monitoring) | MEDIUM | 1.1.3: EIS-SFS-1.1.3-Platform-Access-Gap-Analysis | 1.1.3 §1.1.2 | TBD | AI Working Group |  | C15,C16 | EIS
Phase 3: Operational Maturity (Q3 2026) | Theme 3: Customer Experience Intelligence | 8 | Salesforce Einstein / Agent Force | #012: Salesforce Agent Force implementation | MEDIUM | 1.1.3: EIS-SFS-1.1.3-Platform-Access-Gap-Analysis | 1.1.3 §1.1.2 | TBD | Enterprise Architecture |  | C8,C9,C13 | EIS
Phase 3: Operational Maturity (Q3 2026) | Theme 3: Customer Experience Intelligence | 8 | Salesforce Einstein / Agent Force | #013: Salesforce Data Cloud Analytics | MEDIUM | 1.1.3: EIS-SFS-1.1.3-Platform-Access-Gap-Analysis | 1.1.3 §1.1.2 | TBD | Enterprise Architecture |  | C8,C9,C13 | EIS
Phase 3: Operational Maturity (Q3 2026) | Theme 4: Developer & Analyst Productivity | 21 | Test Automation & QA AI | #086: Shift automation left (QA environment, sprint N+1) | HIGH | 2.2: EIS-SFS-2.2-Testing-AI-Optimization | 2.2 §2.2 | Weeks 13-16 | Dev Team / QA Lead |  | C40,C41,C42,C43 | EIS
Phase 3: Operational Maturity (Q3 2026) | Theme 4: Developer & Analyst Productivity | 20 | AI-SDLC Workflow Enhancement | #058: Data: Code review and standards enforcement | MEDIUM | AI Opps (Data): EIS-SFS-Data-AI-Opportunities | AI Opps (Data) | TBD | Mike Calaway |  | C28,C29,C30 | EIS
Phase 3: Operational Maturity (Q3 2026) | Theme 4: Developer & Analyst Productivity | 20 | AI-SDLC Workflow Enhancement | #059: Data: Deployment governance and release management | MEDIUM | AI Opps (Data): EIS-SFS-Data-AI-Opportunities | AI Opps (Data) | TBD | Mike Calaway |  | C28,C29,C30 | EIS
Phase 3: Operational Maturity (Q3 2026) | Theme 4: Developer & Analyst Productivity | 20 | AI-SDLC Workflow Enhancement | #061: Data: Migration parity validation (SSIS→Fabric) | MEDIUM | AI Opps (Data): EIS-SFS-Data-AI-Opportunities | AI Opps (Data) | TBD | Mike Calaway |  | C28,C29,C30 | EIS
Phase 3: Operational Maturity (Q3 2026) | Theme 4: Developer & Analyst Productivity | 20 | AI-SDLC Workflow Enhancement | #062: Data: Work intake and requirements quality | MEDIUM | AI Opps (Data): EIS-SFS-Data-AI-Opportunities | AI Opps (Data) | TBD | Mike Calaway |  | C28,C29,C30 | EIS
Phase 3: Operational Maturity (Q3 2026) | Theme 4: Developer & Analyst Productivity | 20 | AI-SDLC Workflow Enhancement | #066: Integration: API parity testing (MuleSoft vs Azure) | MEDIUM | AI Opps (Integration): EIS-SFS-Integration-AI-Opportunities | AI Opps (Integration) | TBD | Mike Calaway |  | C28,C29,C30 | EIS
Phase 3: Operational Maturity (Q3 2026) | Theme 4: Developer & Analyst Productivity | 20 | AI-SDLC Workflow Enhancement | #067: Integration: CI/CD pipeline YAML generation | MEDIUM | AI Opps (Integration): EIS-SFS-Integration-AI-Opportunities | AI Opps (Integration) | TBD | Mike Calaway |  | C28,C29,C30 | EIS
Phase 3: Operational Maturity (Q3 2026) | Theme 4: Developer & Analyst Productivity | 20 | AI-SDLC Workflow Enhancement | #068: Integration: Discovery and current-state documentation | MEDIUM | AI Opps (Integration): EIS-SFS-Integration-AI-Opportunities AI Opps (Salesforce): EIS-SFS-SF-AI-Opportunities | AI Opps (Integration) AI Opps (Salesforce) | TBD | Mike Calaway |  | C28,C29,C30 | EIS
Phase 3: Operational Maturity (Q3 2026) | Theme 4: Developer & Analyst Productivity | 20 | AI-SDLC Workflow Enhancement | #069: Integration: Story quality for integration architects | MEDIUM | AI Opps (Integration): EIS-SFS-Integration-AI-Opportunities | AI Opps (Integration) | TBD | Mike Calaway |  | C28,C29,C30 | EIS
Phase 3: Operational Maturity (Q3 2026) | Theme 4: Developer & Analyst Productivity | 20 | AI-SDLC Workflow Enhancement | #072: Salesforce: Architecture diagrams generation | MEDIUM | AI Opps (Salesforce): EIS-SFS-SF-AI-Opportunities | AI Opps (Salesforce) | TBD | Mike Calaway |  | C28,C29,C30 | EIS
Phase 3: Operational Maturity (Q3 2026) | Theme 4: Developer & Analyst Productivity | 20 | AI-SDLC Workflow Enhancement | #074: Salesforce: Documentation drift detection | MEDIUM | AI Opps (Salesforce): EIS-SFS-SF-AI-Opportunities | AI Opps (Salesforce) | TBD | Mike Calaway |  | C28,C29,C30 | EIS
Phase 3: Operational Maturity (Q3 2026) | Theme 4: Developer & Analyst Productivity | 21 | Test Automation & QA AI | #080: Dedicated test data management | MEDIUM | 2.2: EIS-SFS-2.2-Testing-AI-Optimization | 2.2 §2.2 | Weeks 13-16 | Dev Team / QA Lead |  | C40,C41,C42,C43 | EIS
Phase 3: Operational Maturity (Q3 2026) | Theme 6: Governance Operationalization | 11 | AI Cost Management & Metering | #031: Build AI cost tracking and token metering infrastructure | HIGH | 1.1.2: EIS-SFS-1.1.2-Tech-Stack-Evaluation 1.1.3: EIS-SFS-1.1.3-Platform-Access-Gap-Analysis 1.1.4: EIS-SFS-1.1.4-Infrastructure-MLOps-Assessment 1.2: EIS-SFS-1.2-AI-Readiness-Assessment 1.3: EIS-SFS-1.3-AI-Governance-Framework 3.2: EIS-SFS-3.2-Technology-Recommendations AI Opps (Integration): EIS-SFS-Integration-AI-Opportunities | 1.1.2 §1.1.1 1.1.3 §1.1.2 1.1.4 §1.1.3 1.2 §1.2 1.3 §1.3 3.2 §3.2 AI Opps (Integration) | Weeks 6-32 | Architecture, AI CoE/IT Ops |  | C24,C26 | SFS + EIS
Phase 3: Operational Maturity (Q3 2026) | Theme 6: Governance Operationalization | 9a | AI Governance Structure | #017: Ongoing governance maintenance (quarterly reviews, framework refresh, risk register) | MEDIUM | 1.3: EIS-SFS-1.3-AI-Governance-Framework | 1.3 §1.3 | TBD | AI Working Group Team AI Execution Team |  | C1,C2,C3,C4,C5,C6,C7 | SFS + EIS
Phase 3: Operational Maturity (Q3 2026) | Theme 6: Governance Operationalization | 9b | Risk Tiering & Agent Lifecycle | #019: Implement 6-stage agent lifecycle framework (Ideation→Decommission) | MEDIUM | 1.1.4: EIS-SFS-1.1.4-Infrastructure-MLOps-Assessment | 1.1.4 §1.1.3 | TBD | Mike Calaway |  | C29,C31 | SFS + EIS
Phase 3: Operational Maturity (Q3 2026) | Theme 6: Governance Operationalization | 9c | Agent Registry & AI Inventory | #021: Inventory and activate licensed-but-dormant AI capabilities | MEDIUM | 1.3: EIS-SFS-1.3-AI-Governance-Framework | 1.3 §1.3 | Weeks 3-12 | Enterprise Architecture |  | C14 | SFS + EIS
Phase 3: Operational Maturity (Q3 2026) | Theme 6: Governance Operationalization | 9d | Shadow AI Remediation & Approved Tools | #025: Quarterly governance effectiveness reviews | MEDIUM | 1.3: EIS-SFS-1.3-AI-Governance-Framework | 1.3 §1.3 | TBD | Enterprise Architecture |  | C8,C9,C10,C11 | SFS + EIS
Phase 3: Operational Maturity (Q3 2026) | Theme 6: Governance Operationalization | 9e | AI Incident Response & Compliance | #028: Vendor lock-in mitigation (audit clauses, data portability) | MEDIUM | 1.1.4: EIS-SFS-1.1.4-Infrastructure-MLOps-Assessment | 1.1.4 §1.1.3 | TBD | Enterprise Architecture |  | C27,C29 | SFS + EIS
Phase 3: Operational Maturity (Q3 2026) | Theme 6: Governance Operationalization | 10 | AI Center of Excellence | #029: AI training and enablement programs | MEDIUM | 1.3: EIS-SFS-1.3-AI-Governance-Framework | 1.3 §1.3 | TBD | AI Working Group Team AI Execution Team |  | C1,C5,C6,C7 | SFS + EIS
Phase 4: Scale & Optimize (Q4 2026) | Theme 2: Operational AI Enablement | 29 | ROI Measurement & 2027 Planning | #112: ROI validation and 2027 planning | HIGH | 1.2: EIS-SFS-1.2-AI-Readiness-Assessment 3.1: EIS-SFS-3.1-Executive-Synthesis Recs Master: SFS-Final-Delivery-Recommendations-Master | 1.2 §1.2 3.1 §3.1 Recs Master | Weeks 37-48 | AI Governance Committee |  | C26,C34 | EIS
Phase 4: Scale & Optimize (Q4 2026) | Theme 2: Operational AI Enablement | 27 | Remarketing, Research & Predictive Analytics | #105: Predictive analytics (lifecycle models, portfolio analysis) | MEDIUM | 3.1: EIS-SFS-3.1-Executive-Synthesis | 3.1 §3.1 | Weeks 40-48 | Data Science / Risk | Tier 1 | C33,C34 | EIS
Phase 4: Scale & Optimize (Q4 2026) | Theme 2: Operational AI Enablement | 27 | Remarketing, Research & Predictive Analytics | #106: Remarketing decision engine (VIN-level pricing, channel optimization) | MEDIUM | 3.1: EIS-SFS-3.1-Executive-Synthesis Recs Master: SFS-Final-Delivery-Recommendations-Master | 3.1 §3.1 Recs Master | Weeks 37-44 | Remarketing / AI CoE | Tier 3 | C33,C34 | EIS

## 8. Issues & Actions
SFS AI ROADMAP - UNIFIED ISSUE REGISTER AND RESOLUTION TRACKER
Consolidated from cross-document evaluation (v2, 2026-02-26)
ID | Category | Issue | Detail | Affected Docs | Resolution | Status | Priority
CC-1 | C-Code | C29 dual definition | Components: DevSecOps Rollback. Process: 3-Tier Risk Framework. EIS: Cluster 9b, 9e. | ST, GM, Nader | Client to confirm corrected version | Pending Client | HIGH
CC-2 | C-Code | C31 dual definition | Components: Accuracy Metrics. Process: Fast-Track approval. EIS: Cluster 24, 28. | ST, GM, Nader | Client to confirm | Pending Client | HIGH
CC-3 | C-Code | C14 dual definition | Components: Genesys/Observe consolidation. Process: Agent/Tool Registry. EIS: Cluster 1, 2, 9c. | ST, GM, Nader | Client to confirm | Pending Client | HIGH
CC-4 | C-Code | C17/C18 scope conflict | Components: Data Classification. Process: Vendor Consolidation Audit. EIS: Cluster 12, 13. | ST, GM, Nader | Client to confirm | Pending Client | HIGH
P-1 | Personnel | Eric G. role undefined | Co-owner for Governance Portal and MLOps. No role/title documented. | ST, GM | SFS to confirm. Flagged "(role TBD)" | Pending Client | MEDIUM
P-2 | Personnel | Tony Grogan correction | Data Classification: Nader shows Chris Rodriguez; Thomas confirmed Tony Grogan. | GM corrected, ST Cl. 12 | CORRECTED in EIS. Nader draft needs update. | Corrected (EIS) | MEDIUM
GG-1 | Gov Gap | AI Model & Tooling Selection | No enterprise AI model/tooling evaluation process. $4.5M duplication precedent. | All documents | CRITICAL: Add standalone governance element | Open | CRITICAL
GG-2 | Gov Gap | EPMO & Portfolio Intel | 40-50 competing projects, no benefits tracking. McKiggan engagement required. | Synthesis, ST | Recommend initiative #113 or expand Cluster 29 | Open | HIGH
CR-1 | Consolidate | Offshore Team Collaboration | Symptom of tribal knowledge/SDLC gaps, not standalone AI opportunity. | ST | Roll into Cluster 20 or remove | Open | LOW
CR-2 | Consolidate | AI Infrastructure & Cost | Legitimate but too thin as standalone. | ST | Reposition within Cluster 11 | Open | LOW
CR-3 | Consolidate | SDLC Integration/Azure Migration | Platform engineering, not AI initiative. Redundancy with #094. | ST | Confirm #094 as canonical | Open | MEDIUM
IMMEDIATE ACTIONS (THIS WEEK)
# | Action | Owner | Deadline
1 | Confirm corrected C-code mappings (CC-1 to CC-4) | Nader Afshar / Thomas Blumer | 2026-03-01
2 | Confirm Eric G. role and org placement | SFS Leadership | 2026-03-01
3 | Confirm Tony Grogan as Data Classification lead | Thomas Blumer | 2026-03-01
4 | Add AI Model & Tooling Governance element (GG-1) | EIS + SFS Governance | 2026-03-07
5 | Determine EPMO initiative scope (GG-2) | Mike McKiggan + EIS | 2026-03-14