STELLANTIS FINANCIAL SERVICES

AI Readiness Assessment

Strategic Recommendations & Roadmap

From Assessment to Action: Transforming SFS into an AI-Ready Organization

January 2026

Prepared by Earley Information Science

Executive Summary	3

1.1 Assessment Findings Overview	4

1.2 Critical Gaps Requiring Immediate Attention	4

1.3 Organizational Strengths to Leverage	5

2.1 The Cost of Inaction	6

2.2 The Business Case for Action	6

2.3 The Window of Opportunity	7

Theme 1: Knowledge Architecture Foundation	16

Theme 2: Operational AI Enablement	17

Theme 3: Customer Experience Intelligence	18

Theme 4: Developer & Analyst Productivity	19

Theme 5: Data Platform Modernization	20

Theme 6: AI Governance Operationalization	20

Phase 1: Foundation (Q1 2026)	21

Phase 2: Quick Wins & Architecture (Q2 2026)	22

Phase 3: Operational Maturity (Q3 2026)	23

Phase 4: Scale & Optimize (Q4 2026)	24

6.1 AI Readiness Score Targets	25

6.2 Business Outcome Metrics	26

6.3 Leading Indicators	26

## Executive Summary

The AI Readiness Assessment conducted through 25+ stakeholder interviews reveals that Stellantis Financial Services stands at a critical inflection point. With an overall readiness score of 51%, SFS has established strong governance foundations but faces significant gaps in knowledge infrastructure, operational processes, and technical capabilities that must be addressed before AI initiatives can scale successfully.

| 51% Overall Readiness | 66% Governance (Strength) | 43% Knowledge Readiness | 43% Operational Readiness |
| --- | --- | --- | --- |

### The Core Challenge

SFS has the right intentions but lacks the foundational infrastructure for AI success. Across 12+ siloed systems, 75,080 EDW tables, and 95% untagged data, the organization faces a content and data architecture problem that no amount of AI technology investment can solve on its own. This assessment has identified 15 strategic themes spanning enterprise data foundation, AI governance, customer operations, testing, BI productivity, remarketing, conversational AI, integration, document intelligence, predictive analytics, knowledge management, digital properties, resource allocation, process maturity, and competitive positioning.

### The Strategic Opportunity

Industry benchmarks show 86% of financial services organizations with mature AI deployments report revenue lift. SFS can position itself as an industry leader by addressing foundational gaps while delivering quick wins. The End-of-Lease scaling event (14 to 100 agents by 2026) creates both urgency and a natural proving ground for AI-enabled efficiency. Customer service operations, with 90% payment-related calls representing 50,000+ monthly interactions, offer the highest ROI opportunity.

### Key Recommendations

- Establish unified data foundation with API catalog, knowledge graph, and data governance before scaling AI

- Address AI governance gap; no unauthorized AI users, which could create a compliance risk

- Activate already-purchased AI capabilities (Genesys tokens, Salesforce Einstein) to demonstrate ROI

- Deploy customer service automation targeting 90% payment-related calls

- Transform testing through AI augmentation to address 50% time spent on failure investigation

- Create AI Center of Excellence to coordinate 40-50 concurrent projects with only 20% capacity

1. Current State: What the Assessment Reveals

## 1.1 Assessment Findings Overview

The AI Readiness Assessment evaluated SFS across four domains: Knowledge Readiness, Operational Readiness, Technical Readiness, and Governance Readiness. The scoring methodology assessed 74 questions across these domains, with scores reflecting the maturity of current capabilities against industry best practices.

| Domain | Score | Max | Percentage | Status |
| --- | --- | --- | --- | --- |
| Knowledge Readiness | 39 | 90 | 43% | Early Stage |
| Operational Readiness | 43 | 100 | 43% | Early Stage |
| Technical Readiness | 42 | 85 | 49% | Gap |
| Governance Readiness | 63 | 95 | 66% | Strength |
| Overall | 187 | 370 | 51% | Early Stage |

## 1.2 Critical Gaps Requiring Immediate Attention

Six factors scored below 45%, representing foundational gaps that will undermine AI initiatives if not addressed:

### Applicability Mapping (35%)

Content does not indicate when or where it applies. Customer data is distributed across DeFy, EDW, Salesforce, Data Cloud without standardization. No mapping exists between content, products, tasks, or user roles that would enable AI to surface the right information in context.

### Knowledge Accessibility (40%)

Information is scattered across 12+ siloed systems: Azure/Fabric, TestRail, Genesys, Salesforce, SharePoint, Aspira, Shaw, Observe.AI, FICO, EDW, DeFi Solutions. Employees rely on tribal knowledge and specific individuals. Only 30-40% of enterprise integrations are documented.

### Knowledge Organization (40%)

No unified metadata schema exists across systems. Terminology varies by department. Only rudimentary data classifications exist, with 95% of data not tagged for AI consumption. Siloed taxonomies prevent cross-system navigation.

### Monitoring & Telemetry (40%)

No AI dashboards or performance monitoring infrastructure exists. Token consumption tracking is listed as a needed capability. Basic system monitoring exists but no AI-specific observability.

### Drift Monitoring (40%)

No production AI monitoring capabilities are operational. The AI Governance Policy includes incident response protocols but no drift detection. Manual processes identify issues after user complaints rather than proactively.

### Retrieval Performance (40%)

No systematic measurement or tuning processes exist. Limited metadata infrastructure constrains retrieval quality. No automated testing of AI retrieval accuracy.

## 1.3 Organizational Strengths to Leverage

The assessment also revealed significant strengths that provide a foundation for AI transformation:

### Governance Structure (80%)

The AI Governance Policy is comprehensive with clear RACI definitions. The AI Governance Committee is active, supported by AI Champions program (though broader representation needed), and should subsume the KM Governance Committee. Vendor assessment processes exist through the committee structure.

### Security & Compliance (70%)

Strong regulatory awareness exists with CFPB and FFIEC compliance built into processes. Data privacy considerations are integral to the approval workflow. The security team is engaged and preparing for bank launch requirements.

### Culture & Adoption (64%)

Universal enthusiasm for AI exists across all interviewed teams. Shadow AI usage (281 GPT users, 111 Gemini users) demonstrates pent-up demand. Teams are actively experimenting despite limited sanctioned tools. Management appears to favor a cautious, incremental approach to AI implementation that prioritizes small wins, which may inadvertently limit or delay exploration of larger-scale opportunities.

### Strategy & Investment (64%)

Executive champion is actively engaged. EIS engagement demonstrates commitment to doing AI correctly. Multiple AI investments have already been made (Genesys, Salesforce Einstein, Azure AI services) though not fully activated.

2. The "So What?": Why This Matters Now

## 2.1 The Cost of Inaction

Without addressing foundational gaps, SFS faces compounding challenges:

- Scaling Crisis: End-of-Lease operations growing from 14 to 80-100 agents by 2026 will overwhelm current knowledge-sharing approaches. Tribal knowledge cannot scale.

- Wasted Investment: Genesys AI tokens expire unused monthly; Salesforce Einstein remains paid but disabled; Observe AI duplicates Genesys capabilities at additional cost.

- Competitive Disadvantage: Industry benchmark shows 42-50% of financial services organizations have active AI deployments; SFS remains at proof-of-value stage.

- Shadow AI Risk: Ensure no unauthorized AI tool users, which could create a data exposure and compliance vulnerabilities in an environment preparing for bank launch.

- Technical Debt: Multiple ungoverned AI experiments create architectural fragmentation; expensive "pay by the drink" vendor models emerging without coordination.

## 2.2 The Business Case for Action

Industry benchmarks from NVIDIA and Genesys research provide ROI context:

| Capability | Industry Benchmark Impact |
| --- | --- |
| Voice Self-Service with Virtual Agents | 55-75% call automation, $295K+ annual value |
| Agent Copilot Auto-Summarization | 18-32% after-call work reduction, $204K+ annual value |
| Real-Time Agent Assistance | Improved first-call resolution |
| Predictive Engagement | Reduced delinquency through proactive outreach |

For SFS specifically, with 145,000 monthly inbound calls, 90% payment-related, and cost per call of $4.50,even modest automation rates translate to significant value while improving customer experience and enabling operations to scale.

## 2.3 The Window of Opportunity

Several factors create urgency for immediate action:

- End-of-Lease Scaling (2026-2027): Must establish data collection and automation capabilities before the growth curve begins.

- Salesforce Implementation: December 2025 deployment creates integration opportunities; Einstein activation depends on corporate approval.

- Azure Migration: Active migration from MuleSoft to Azure APIM creates architecture decision points; comprehensive API catalog opportunity.

- Genesys Platform: AI tokens purchased but expiring unused; professional services SOW pending approval; immediate activation opportunity.

- Bank Launch Preparation: Heightened regulatory scrutiny requires detailed AI governance before deployment in banking context.

3. Consolidated Findings & Recommendations

The following 15 themes represent the synthesis of 140+ individual findings from stakeholder interviews across all operational areas. Each theme identifies a systemic challenge, provides context through specific evidence, and offers actionable recommendations tailored to SFS's situation.

1. Enterprise Data Foundation Is Incomplete - Limiting AI Readiness

Finding: Critical data infrastructure gaps prevent effective AI implementation: only 30-40% of enterprise integrations are documented, customer data is fragmented across DeFy/EDW/Salesforce/Data Cloud, 75,080 EDW tables lack comprehensive cataloging, and Azure environment documentation is severely lacking compared to legacy MuleSoft. Recommendation: Establish unified data foundation before scaling AI initiatives - implement API catalog with governance framework, deploy knowledge graph for entity relationship mapping, create automated data quality monitoring, and complete data lineage visualization. This foundation enables all downstream AI applications while preventing fragmented, unsustainable implementations. Sources: Meeting with Cassidy and Salesforce team, Data Discovery with Bobby, Data II Bobby & Puru, Product Consideration Meeting, Infrastructure Larry and Puru

2. AI Governance Gap Creates Compliance Risk and Shadow IT

Finding: Despite 281 GPT users and 111 Gemini users operating outside approved channels, SFS lacks comprehensive AI governance framework. Missing elements include token consumption tracking, privacy impact assessments, bias detection, security standards for financial services, and cost allocation models. This creates regulatory exposure in a banking environment while limiting organizational learning from distributed AI experiments. Recommendation: Implement enterprise AI governance framework immediately - establish AI Center of Excellence, deploy usage monitoring with chargeback capabilities, create tiered tool approval process (enterprise ChatGPT/Claude for general use, specialized tools for technical teams), develop privacy-preserving implementation standards, and build decision rubrics for technology selection. This enables safe innovation velocity while maintaining compliance. Sources: Security, Infrastructure Larry and Puru, Danny End-of-Lease, Risk & BI Chuck, Internal Meeting, AI Nader

3. Customer Service Operations Offer Highest ROI AI Opportunity

Finding: 90% of 50,000 monthly customer service calls are payment-related, representing massive opportunity for deflection. End-of-lease operations must scale from 14 to 80-100 agents by 2026 with major growth in 2027. Collections manages 400 FTEs. Customer frustration signals (rage clicks, failed attempts) go undetected. Genesys AI capabilities remain underutilized despite purchased licenses. Recommendation: Prioritize customer-facing AI across three horizons: (1) Immediate - deploy payment-focused chatbot, activate Genesys AI for call transcription/summarization, implement real-time frustration detection; (2) Near-term - agent copilot for real-time knowledge surfacing, automated call classification for 2026 preparation; (3) Strategic - multi-modal AI agents with intelligent escalation, proactive intervention models using telematics data. ROI calculated through reduced hiring needs before end-of-lease scaling begins. Sources: Matt and UX team, Customer Care, Stakeholder meeting, Collections with Greg, Danny End-of-Lease, Infrastructure Larry and Puru, AI Nader, Project Update Week3

4. Testing Bottleneck Threatens Digital Transformation Timeline

Finding: 50% of automation engineer time spent investigating test failures rather than developing new tests. Manual QA team cannot keep pace with development velocity. 7,000+ PWC tests need distillation. API testing covers only 61 of 700+ endpoints. Azure migration and Salesforce implementation lack adequate test automation. Self-healing capabilities and intelligent test selection are absent. Recommendation: Transform testing through AI augmentation across SDLC: implement self-healing locator capabilities and AI-assisted failure analysis to reclaim 50% of maintenance time, deploy automated test generation from Gherkin specifications, establish predictive test selection based on code changes, accelerate API test coverage using specification-driven generation, and create AI-powered test impact analysis. Move testing support upstream to prevent downstream defects. Sources: Testing Deep Dive Swarupa/Stephen/Geeta/Tyler, Manual Testing - Corinne, Automated Testing Stephen, Project Update Week3, AI Nader

5. BI Team Productivity Constrained by Manual Processes

Finding: 10-day report turnaround time despite high demand and 40-50 project pipeline with only 20% capacity. Analysts spend excessive time on data discovery across disparate systems (SQL Server, EDW, SAS, multiple source systems), duplicate work due to inability to find existing reports, manual data quality validation, and repetitive SQL/SAS coding. PhD-level teams (Economics & Residuals, Risk Analytics) spend 25% of time on code development and data engineering rather than analysis. Recommendation: Deploy AI-powered BI acceleration suite: schema-aware SQL generation from natural language, automated report similarity detection to prevent duplication, pre-execution query optimization analysis, intelligent data source validation, and code generation assistance. Extend agentic data analyst capabilities (Phase 1 proof-of-concept) to generate code with full transparency for analyst review. Target 30-50% productivity improvement enabling backlog reduction without proportional headcount growth. Sources: BI Shandria, BI-Tricia, Data, Risk Mgt & AI Eric, Economics & Residuals Rene, BI TJ, Data Science & Fabric - Adam, Project Update Week3

6. Remarketing Operations Lack Intelligence Layer for Portfolio Maturity

Finding: As lease portfolio matures toward 10x volume growth, remarketing operates with manual pricing decisions (weekly discussions), uniform pricing rather than VIN-level optimization, limited channel optimization (auction vs. dealer vs. e-commerce), no demand sensing integration, and minimal reconditioning ROI analysis. Current systems cannot scale to handle maturity volumes while maximizing recovery rates. Recommendation: Build remarketing decision engine in phased approach: (1) Immediate - next-best-action recommendations within Salesforce, basic dealer chatbot, repair recommendation optimization; (2) Near-term - MVP pricing models at VIN-level, dealer scorecarding, demand sensing integration; (3) Medium-term - comprehensive multi-model engine integrating pricing/channel/transportation/timing decisions, bidding platform with demand forecasting, advanced telemetry incorporation for condition assessment. Target 2:1 ROI on reconditioning investments and optimize for portfolio scale. Sources: Remarketing - Dan, BI TJ, Economics & Residuals Rene, Danny End-of-Lease

7. Conversational AI Implementations Lack Production Rigor

Finding: Multiple conversational AI initiatives (dealer-facing, HR benefits, end-of-lease, customer service) progressing without comprehensive evaluation frameworks, automated testing, or quality monitoring. Teams using trial accounts rather than production infrastructure. No standardized approach to memory management, personality customization, or multi-agent orchestration. Risk of "GM $1 lease quote incident" scenarios when deploying dealer-facing without proper guardrails. Recommendation: Establish conversational AI excellence framework before scaling: implement 75+ test question evaluation with automated regression testing, deploy vector database automation replacing manual knowledge base updates, develop multi-agent orchestration patterns (LangGraph/LangChain/Crew AI), create platform portability strategy avoiding vendor lock-in, establish role-based personality customization standards, and design fast-track release process for information vs. infrastructure changes. Select one pilot use case for collaborative implementation demonstrating best practices end-to-end. Sources: BI Yu, Internal Meeting, AI Nader

8. Cross-System Integration Complexity Creates AI Implementation Barriers

Finding: Enterprise applications operate in silos - Genesys, Salesforce, EDW, NSF applications, dealer portals, OEM sites - preventing unified customer view and forcing users to navigate fragmented experiences. MuleSoft-to-Azure APIM migration underway but lacks comprehensive API catalog. Data exchange between systems (remarketing-to-collections handoff, dealer-finance-customer touchpoints) remains manual or poorly optimized. Recommendation: Establish integration excellence layer supporting AI applications: complete API catalog with governance during Azure migration, implement observability standards using Sentinel, develop centralized orchestration layer with token cost tracking, create unified customer 360-degree view integrating Salesforce/Jericho/support/financial systems, optimize critical workflows (collections-to-remarketing, dealer relationship handoffs), and ensure omnichannel consistency across web/mobile/voice/messaging. Position integration layer as AI enablement platform. Sources: Meeting with Cassidy and Salesforce team, Product Consideration Meeting, Infrastructure Larry and Puru, BI-Tricia, Danny End-of-Lease, AI Nader

9. Document Intelligence Opportunity Remains Untapped

Finding: Massive unstructured data volumes represent opportunity - underwriting teams manually process variable-format credit reports (1-10 pages), thousands work with policies/training materials/procedures lacking intelligent search, contract data extraction is manual, SharePoint contains years of knowledge without semantic access, and meeting transcripts/call recordings contain insights lost to manual review. Recommendation: Deploy comprehensive document intelligence pipeline: implement extraction for credit report standardization (immediate underwriting productivity gain), develop enterprise knowledge bot for policies/procedures (reduce HR/support burden), create AI-powered SharePoint search with summarization, establish automated meeting transcription and insight extraction, and build contract intelligence for origination documents. Leverage Azure AI Foundry document capabilities as enterprise document management matures. Sources: Stakeholder meeting, Matt and UX team, Infrastructure Larry and Puru, Collections with Greg, Data II Bobby & Puru, Internal Meeting

10. Portfolio Growth Demands Predictive and Prescriptive Analytics

Finding: Organization lacks sophisticated forecasting and optimization capabilities needed for portfolio maturity - economic residual forecasting requires PhD-level manual work, termination predictions need accuracy improvement for 20x volume planning, customer lifecycle analytics don't leverage 2B+ account value records, pricing models are reactive rather than predictive, and delinquency interventions are reactive rather than proactive with 2,500+ credit attributes underutilized. Recommendation: Build advanced analytics infrastructure: deploy ML Ops platform with model governance for banking compliance, implement predictive models for customer lifecycle (termination, upsell, satisfaction indicators), develop automated market intelligence platform monitoring automotive developments, create portfolio scenario analysis for risk management, establish real-time intelligence capabilities for fraud detection and operational monitoring, and optimize collections contact strategies using advanced credit attribute analysis. Ensure continuous learning systems incorporate outcomes into model refinement. Sources: Economics & Residuals Rene, BI TJ, Data Science & Fabric - Adam, Collections with Greg, Risk & BI Chuck, Risk Mgt & AI Eric, AI Nader

11. Knowledge Management and Training Systems Are Inadequate for Scale

Finding: Tribal knowledge not captured systematically, new employee onboarding is lengthy (analyst onboarding highlighted as pain point), process documentation is incomplete (blocker for project starts per EPMO), dealer education on new systems is minimal, and organizational learning from AI experiments isn't shared. As operations scale (end-of-lease 14 to 100 agents, collections 400 FTEs, testing team expansion), knowledge gaps will multiply. Recommendation: Leverage the KM Framework, especially the KM Maturity framework, the expertise location, the KM expertise succession planning (ensuring no-single-point-of-failures), the Content Lifecycle Management process, and adding an enterprise-wide search feature. Implement an AI-powered knowledge management ecosystem: create intelligent onboarding assistants for analysts/testers/agents with context-aware help, capture tribal knowledge from experienced team members into AI-accessible formats, develop training programs for AI-augmented workflows, establish cross-functional Center of Excellence sharing learnings and standardizing approaches, accelerate process documentation through interview analysis and automated workflow observation, and build dealer education portal with AI-powered guidance. Design systems that learn from usage patterns and continuously improve. Sources: Data, BI Shandria, Testing Deep Dive, Manual Testing - Corinne, Economics & Residuals Rene, EPMO - Mike, Remarketing - Dan, Data Science & Fabric – Adam, KM Framework

12. Website and Digital Properties Underperform Customer Expectations

Finding: Public website lacks basic search functionality, customer experience for non-registered users is suboptimal, A/B testing capabilities are absent, below-the-fold content goes unexplored, SFS-to-OEM site integration is fragmented, MySFS portal integration incomplete, and positioning remains service-focused rather than acquisition-focused despite potential for lease-end conversion, refinancing campaigns, and commercial lending growth. Recommendation: Transform digital properties into intelligent acquisition and retention channel: implement search functionality immediately, deploy customer-facing chatbot leveraging FAQ foundation, establish A/B testing framework for continuous optimization, integrate seamlessly with OEM sites and complete MySFS portal consolidation, develop offer/incentive engine showcasing promotions, implement CEO (Chat Engine Optimization) for AI assistant discoverability, create personalized content recommendations using Clarity analytics, and position site for lease-end-to-new-lease conversion and refinancing capture. Build comprehensive analytics to measure digital channel contribution to business outcomes. Sources: Web Site - Sana, Matt and UX team, Product Consideration Meeting

13. Strategic Resource Allocation Lacks Data-Driven Prioritization

Finding: 40-50 projects in pipeline with only 20% capacity, meaningful prioritization difficult due to political dynamics, discovery phase becoming backlogged, business case development inconsistent, benefits realization tracking incomplete, and resource allocation based on static monthly heat maps rather than dynamic optimization. AI governance committee evaluates vendor solutions without systematic framework. Project delays common due to undocumented business processes. Recommendation: Deploy AI-enhanced portfolio and resource management: implement objective project scoring against strategic criteria with AI-powered business case analysis, create resource optimization models incorporating dependencies/skills/velocity, automate discovery phase artifacts (requirements gathering, technical specifications, ARB documentation), establish standardized business case framework with comparative analysis from past projects, develop predictive capacity forecasting identifying constraint risks early, and create vendor AI solution evaluation framework assessing capabilities/integration/TCO. Enable executives with decision-support visualizations overcoming political prioritization reluctance. Sources: Product Consideration Meeting, EPMO - Mike, Internal Meeting, Risk & BI Chuck

14. Process Maturity Gap Slows Innovation Velocity

Finding: SFS implementing processes that took GMF 12+ years to develop, creating maturity curve compression opportunity. However, manual process documentation, inconsistent change management approaches, limited observability into operational workflows, and inadequate measurement frameworks slow progress. End-of-lease scaling, payments enterprise program (100+ identified challenges), and insurance platform migration all require process excellence. Recommendation: Accelerate process maturity through AI assistance: automate process documentation via interview analysis and workflow observation, develop standardized templates and artifacts reducing reinvention, implement digital adoption platform (DAP) with real-time process monitoring and proactive issue detection, create comprehensive observability across technology stack identifying optimization opportunities, establish automated KPI monitoring with intelligent alerting, and design change management programs specifically for AI tool adoption across growing populations. Build feedback loops ensuring continuous improvement based on operational data. Sources: EPMO - Mike, Matt and UX team, BI-Tricia, Danny End-of-Lease, Product Consideration Meeting

15. Competitive Positioning Requires Coordinated AI Strategy

Finding: Individual business units pursuing independent AI initiatives without coordination, expensive "pay by the drink" vendor models emerging, organization moving from cautionary to calculated innovation stance, but lack of unified strategy prevents systematic competitive advantage building. Current approach risks fragmented implementations, duplicated investments, and missed synergies while competitors potentially move faster with coordinated strategies. Recommendation: Establish enterprise AI strategy with coordinated execution: position SFS as automotive finance industry digital transformation leader through superior customer service automation and operational efficiency, build organizational muscle memory for AI adoption scaling across 2-4 year horizon, create reusable AI infrastructure and patterns preventing one-off solutions, develop vendor-ready posture enabling rapid best-of-breed adoption as market matures, establish measurement frameworks validating initiatives and revealing optimization opportunities, and calculate ROI demonstrating where AI investment offsets labor costs (end-of-lease scaling), reduces vendor dependencies (payment processing), and enables revenue growth (remarketing optimization, product expansion). Move from defensive AI exploration to offensive competitive differentiation. Sources: Internal Meeting, Project Update Week3, Stakeholder meeting, AI Nader, Risk & BI Chuck, EPMO - Mike, Product Consideration Meeting

- Strategic Recommendations: What SFS Should Do

Based on the assessment findings, stakeholder interviews, and industry benchmarks, we recommend six strategic themes that address both foundational gaps and immediate opportunities:

## Theme 1: Knowledge Architecture Foundation

| Gap Addressed | Knowledge Accessibility (40%), Knowledge Organization (40%), Applicability Mapping (35%) |
| --- | --- |
| Rationale | AI systems cannot effectively retrieve information that is unstructured, untagged, and scattered across silos. This is the foundational blocker that must be addressed for any AI initiative to succeed at scale. |

### Recommended Initiatives

- Unified Metadata Schema: Develop enterprise-wide metadata standards across EDW, Salesforce, SharePoint, and other content repositories. Include applicability indicators for products, tasks, and user roles.

- Content Inventory & Tagging: Systematic inventory of unstructured data assets with priority tagging for AI consumption. Target 99% of frequently accessed content tagged within 18 months (and 95% in 12 months).

- Accelerate API integration documentation and migration efforts to address the 30-40% integration gap outside MuleSoft's current footprint, supporting the 18-month Azure migration timeline.

- Cross-System Taxonomy: Develop controlled vocabulary and classification system that works across departmental boundaries. Address current siloed terminology that prevents cross-functional AI applications.

- Knowledge Graph Foundation: Map relationships across tables, databases, and data marts. Enable multi-hop reasoning and contextual retrieval.

- Content Component Model: Break monolithic documents into reusable components. Create templates for consistent structure.

### Expected Outcomes

- AI retrieval accuracy improvement from current inconsistent state to 80%+ relevance

- Analyst time reduction for data discovery (currently significant portion of work)

- Foundation for natural language query interfaces across 75,080 EDW tables

- Reduced duplicate report creation through similar report discovery

## Theme 2: Operational AI Enablement

| Gap Addressed | Drift Monitoring (40%), Retrieval Performance (40%), Operational Maturity (45%) |
| --- | --- |
| Rationale | AI governance policies exist but operational implementation lags. Without monitoring and feedback systems, AI deployments cannot be sustained or improved over time. |

### Recommended Initiatives

- AI Monitoring Dashboard: Build centralized visibility into AI system performance, token consumption, error rates, and user feedback across all AI implementations.

- Drift Detection Framework: Implement automated monitoring for AI output quality, accuracy, and consistency. Establish thresholds and alerting for model degradation.

- Feedback Loop Infrastructure: Connect insights from AI monitoring back to content improvement cycles. Enable continuous enhancement of knowledge bases.

- SME Workflow Integration: Define workflows for how subject matter experts contribute to and approve AI-consumed content. Protect SME time while ensuring content quality.

- Lifecycle Management System: Implement systematic content review cycles with end-to-end lifecycle management including creation, review, publish, update, and archive.

### Expected Outcomes

- Proactive identification of AI performance issues before user impact

- Continuous improvement of AI accuracy through structured feedback

- Reduced reliance on tribal knowledge through formalized SME contribution

- Audit-ready documentation of AI system behavior and changes

## Theme 3: Customer Experience Intelligence

| Gap Addressed | 50,000+ monthly customer calls (90% payment-related), End-of-Lease scaling from 14 to 80-100 agents, Collections 400 FTEs |
| --- | --- |
| Rationale | Customer service represents the highest ROI opportunity for AI investment. Addressing payment automation alone could generate $295K+ annual value while improving customer experience. |

### Recommended Initiatives

- Genesys AI Activation: Deploy already-purchased Genesys capabilities for call summarization, sentiment analysis, and agent assistance. Stop monthly token waste.

- Payment Automation Priority: Implement voice and chat automation for payment-related inquiries representing 90% of call volume. Target 30% deflection in first year.

- Agent Copilot Deployment: Real-time knowledge surfacing, next-best-action guidance, and automated call wrap-up to improve productivity and consistency.

- Self-Service Expansion: Deploy AI-powered chatbot for common questions on MySFS portal. Intelligent FAQ with escalation paths.

- Proactive Customer Engagement: Predictive analytics for proactive payment communication, excess mileage alerts, and lease-end preparation.

### Expected Outcomes

- $295K+ annual value from voice self-service (industry benchmark: 55-75% automation)

- $204K+ annual value from auto-summarization (18-32% after-call work reduction)

- Reduced wrongful repossessions through AI-assisted decision support

- Scalable operations for End-of-Lease growth without proportional headcount increase

## Theme 4: Developer & Analyst Productivity

| Gap Addressed | 40-50 projects with only 20% capacity, 50% automation engineer time on failure investigation, 10-day report turnaround |
| --- | --- |
| Rationale | Development and analytical teams are clamoring for AI assistance. Copilot is only available via Office365 without IDE integration. Schema-aware SQL generation could dramatically improve BI productivity. |

### Recommended Initiatives

- Schema-Aware SQL Generation: Deploy LLM with data dictionary context to generate SQL from natural language. BI team spends majority of time on SQL coding.

- GitHub Copilot Expansion: Enable IDE-integrated AI assistance for development and QA teams. Address current limitation of Copilot only through Office365.

- Test Automation Enhancement: AI-assisted test case generation, self-healing locators, and automated failure analysis to reclaim 50% maintenance time.

- Code Quality & Optimization: AI-powered code review, performance optimization suggestions, and standards compliance checking.

- Similar Report Discovery: AI-powered search across existing reports to reduce duplication and accelerate delivery.

### Expected Outcomes

- 30-50% productivity improvement for BI and Risk SQL development

- Accelerated test automation from 41% to 70%+ coverage

- Reduced IT remediation burden from poorly performing queries

- Faster delivery on 40-50 project backlog

## Theme 5: Data Platform Modernization

| Gap Addressed | Technical Foundation (44%), Integration & Orchestration (45%), 95% of data untagged |
| --- | --- |
| Rationale | 95% of data is not tagged for AI consumption. The natural language query pilot is limited to 25 tables. Azure migration creates opportunity for governance-by-design. |

### Recommended Initiatives

- Data Classification Initiative: Systematic tagging of data for AI consumption with PII identification using Microsoft Purview. Target 70%+ of frequently-accessed data classified.

- Unified Data Access Layer: Create consistent access patterns across Azure Fabric, Cosmos DB, Salesforce, and legacy systems. Enable AI systems to query across sources.

- Enterprise Vectorization Strategy: Move beyond pilot-stage RAG to enterprise embedding strategy with refresh processes and quality monitoring.

- Natural Language Query Platform: Expand from current 25-table pilot to enterprise capability across EDW. Build on agentic data analyst proof-of-concept.

- Real-Time Intelligence Activation: Deploy Fabric streaming capabilities for low-latency analytics and real-time decision support.

### Expected Outcomes

- AI-ready data foundation with 70%+ classification completeness

- Single source of truth replacing departmental shadow data practices

- Self-service analytics capability for business users

- Foundation for advanced AI use cases requiring multi-source data

## Theme 6: AI Governance Operationalization

| Gap Addressed | Cross-Functional Alignment (55%), prevent unauthorized AI users, policy-to-practice gap |
| --- | --- |
| Rationale | Strong governance policies exist but operational implementation lags, no process workflows to redirect users to the right place. Unauthorized AI usage creates compliance risk while blocking innovation in sanctioned channels. |

### Recommended Initiatives

- AI Center of Excellence: Establish centralized expertise, reusable components, and best practices. Address current fragmentation across Genesys, Salesforce, and Azure AI initiatives.

- Governance Operationalization: Move AI Governance Policy from documentation to operational workflows. Build approval processes, monitoring, and enforcement into daily operations.

- Unauthorized AI Remediation: Address 281 ChatGPT and 111 Gemini users with approved alternatives and policy enforcement. Convert shadow AI to governed AI.

- Cost Management Framework: Build token consumption tracking and chargeback capabilities. Enable business units to understand and manage AI costs.

- Vendor AI Evaluation Process: Systematic assessment of vendor AI offerings (Genesys vs. Salesforce vs. Azure) for each use case. Prevent lock-in while leveraging investments.

### Expected Outcomes

- Coordinated AI initiatives versus current fragmented approach

- Reduced compliance and security risk from shadow AI

- Predictable AI costs with business unit accountability

- Accelerated adoption through proven patterns and reusable components

- Implementation Roadmap: When to Act

The roadmap balances foundational work with quick wins to demonstrate value while building sustainable AI capabilities. Initiatives are sequenced based on dependencies, resource availability, and strategic impact.

## Phase 1: Foundation (Q1 2026)

Focus: Establish governance operations, activate purchased capabilities, begin knowledge architecture work.

1.1 Genesys AI Activation

Deploy already-purchased Genesys capabilities for call summarization, sentiment analysis, and agent assistance. Stop monthly token waste and demonstrate ROI. Timing: Weeks 1-8 ¦ Impact: High ¦ Owner: Ryan Miller/IT Ops

1.2 AI Governance Operationalization

Move AI Governance Policy to operational workflows. Establish approval processes, monitoring, and enforcement. Address unauthorized AI usage. Timing: Weeks 1-12 ¦ Impact: High ¦ Owner: AI Governance Committee

1.3 Unified Metadata Schema Design

Develop enterprise metadata standards across priority systems. Create applicability indicators for AI consumption. Timing: Weeks 4-12 ¦ Impact: Medium ¦ Owner: Bobby Goodwin/Data Team

1.4 BI Code Generation Pilot

Deploy schema-aware SQL generation for BI team. Target high-frequency query patterns for immediate productivity gain. Timing: Weeks 4-12 ¦ Impact: Medium ¦ Owner: BI Team/EIS

## Phase 2: Quick Wins & Architecture (Q2 2026)

Focus: Scale successful pilots, implement customer-facing automation, build data platform capabilities.

2.1 Payment Automation Deployment

Implement voice and chat automation for payment-related inquiries. Target 30% call deflection based on 90% payment-related call volume. Timing: Weeks 13-24 ¦ Impact: High ¦ Owner: Customer Service/Genesys

2.2 Test Automation Enhancement

Deploy AI-assisted test case generation and self-healing locators. Address 50% time spent on failure investigation. Timing: Weeks 13-20 ¦ Impact: Medium ¦ Owner: QA/EIS

2.3 Content Inventory & Tagging

Systematic inventory of unstructured data assets. Implement Purview for data classification. Target 50% of priority content tagged. Timing: Weeks 13-24 ¦ Impact: Medium ¦ Owner: Data Governance

2.4 AI Center of Excellence Launch

Establish CoE structure, staffing, and initial reusable components. Create support model for business unit AI initiatives. Timing: Weeks 16-24 ¦ Impact: High ¦ Owner: CDO/Ryan Miller

## Phase 3: Operational Maturity (Q3 2026)

Focus: Build monitoring infrastructure, expand developer tools, prepare for End-of-Lease scaling.

3.1 AI Monitoring Dashboard

Deploy centralized monitoring for token consumption, performance metrics, and cost allocation across all AI implementations. Timing: Weeks 25-32 ¦ Impact: High ¦ Owner: AI CoE/IT Ops

3.2 End-of-Lease AI Preparation

Implement call classification, data collection, and chatbot pilot for End-of-Lease operations scaling to 80-100 agents. Timing: Weeks 25-36 ¦ Impact: High ¦ Owner: Danny Rodriguez/AI CoE

3.3 GitHub Copilot Deployment

Enable IDE-integrated AI assistance for development teams. Establish usage policies and productivity measurement. Timing: Weeks 25-32 ¦ Impact: Medium ¦ Owner: Dev Teams/Security

3.4 Natural Language Query Expansion

Scale from 25-table pilot to broader EDW access. Build on agentic data analyst capabilities. Timing: Weeks 28-36 ¦ Impact: Medium ¦ Owner: Data/AI CoE

## Phase 4: Scale & Optimize (Q4 2026)

Focus: Expand successful implementations, optimize based on learnings, achieve industry benchmark performance.

4.1 Collections AI Augmentation

Deploy voice AI and predictive analytics for Collections 400 FTE operation. Leverage credit attribute analysis. Timing: Weeks 37-48 ¦ Impact: High ¦ Owner: Greg Shreve/AI CoE

4.2 Einstein Activation

Enable Salesforce Einstein capabilities post corporate approval. Integrate with existing Salesforce implementation. Alternatively, leverage Genesys AI to reduce costs while maintaining a cohesive, integrated solution architecture. Timing: Weeks 37-44 ¦ Impact: Medium ¦ Owner: Salesforce Team

4.3 Knowledge Graph Implementation

Deploy production-grade knowledge graph for enterprise search and AI retrieval across systems. Timing: Weeks 40-48 ¦ Impact: Medium ¦ Owner: Data/AI CoE

4.4 ROI Validation & 2027 Planning

Measure outcomes against industry benchmarks. Develop 2027 roadmap based on learnings and emerging opportunities. Timing: Weeks 44-48 ¦ Impact: High ¦ Owner: AI Governance Committee

6. Success Metrics: How to Measure Progress

Success metrics align with assessment factors, industry benchmarks, and business outcomes. Regular measurement enables course correction and demonstrates value to stakeholders.

## 6.1 AI Readiness Score Targets

| Domain | Current | Q2 Target | Q4 Target | Industry |
| --- | --- | --- | --- | --- |
| Knowledge Readiness | 43% | 55% | 65% | 70% |
| Operational Readiness | 43% | 55% | 65% | 70% |
| Technical Readiness | 49% | 60% | 70% | 75% |
| Governance Readiness | 66% | 75% | 80% | 85% |
| Overall | 51% | 62% | 70% | 75% |

## 6.2 Business Outcome Metrics

- Customer Service: Call deflection rate (target 30%), average handle time reduction (target 15%), first contact resolution improvement

- Developer Productivity: SQL generation adoption rate, test automation coverage (target 70%), code review cycle time reduction

- Cost Management: Token utilization rate (target 80%+), cost per AI interaction, ROI per use case

- Operational: Content tagging completeness (target 70%), retrieval accuracy (target 80%), monitoring coverage

## 6.3 Leading Indicators

- Weekly: Token consumption trends, error rates, user adoption metrics

- Monthly: Use case pipeline progress, governance compliance, cost variance

- Quarterly: Readiness score reassessment, stakeholder satisfaction, capability maturity

7. Conclusion: The Path Forward

Stellantis Financial Services stands at a pivotal moment. The AI Readiness Assessment reveals an organization with strong governance foundations (66%) and universal enthusiasm for AI adoption, but significant gaps in knowledge infrastructure (43%), operational processes (43%), and technical capabilities (49%) that must be addressed for AI initiatives to scale successfully. The 15 consolidated findings spanning enterprise data foundation through competitive positioning provide a comprehensive view of both challenges and opportunities.

The recommendations in this document address both the foundational gaps and the immediate opportunities. By pursuing the six strategic themes with the phased implementation roadmap, SFS can:

- Transform knowledge architecture to enable accurate AI retrieval across 12+ systems

- Activate already-purchased AI capabilities to stop waste and demonstrate ROI

- Build operational infrastructure for sustainable AI at scale

- Prepare for the 2026-2027 End-of-Lease scaling event with AI-enabled efficiency

- Position SFS as an industry leader in responsible AI adoption

### Critical Success Factors

- Executive Commitment: Sustained sponsorship from Ryan Miller and the AI Governance Committee

- Resource Allocation: Dedicated capacity for foundational work alongside quick wins

- Cross-Functional Collaboration: Breaking down silos between IT, business units, and data teams

- Measured Approach: Crawl-walk-run philosophy with continuous learning and adjustment

- External Partnership: Leveraging EIS expertise to accelerate capability building

The window of opportunity is now. With the End-of-Lease scaling event approaching, Salesforce implementation underway, and Azure migration creating architecture decision points, the decisions made in Q1-Q2 2026 will determine whether SFS builds a sustainable AI foundation or accumulates additional technical debt.

The recommendations in this document provide a clear path from assessment to action. SFS has the governance foundation, executive commitment, and business need to succeed. The next step is to begin execution with the Q1 2026 initiatives while building organizational capability for the journey ahead.