## 1. Governance Bodies
Entity | Type | Description | Lifespan | Composition (SFS) | Meeting Cadence | Outputs | Reporting To | Decision Authority
AI Governance Committee | Steering Committee / Council | Permanent advisory body providing strategic direction, socialization of AI initiatives, cross-BU opportunity sharing, executive sponsorship, and budget advocacy. Sets organizational AI vision and validates that working group decisions align with business strategy. | Ongoing (permanent) | Ryan Miller (CDO, Chair), Phil Maternowski (CIO), Chuck Berend (CRO), Mike Calaway (CISO), Larry Burgess (EA), Nader Afshar (AI PO), Greg Shreve (Collections), BU representatives (rotating) | Every 6 weeks | Strategic direction, policy endorsement, budget allocation, escalation resolution, cross-BU alignment | Executive Management / Stellantis Corporate | Ratifies Working Group recommendations on strategic/high-cost items; approves Tier 1 (Critical) AI deployments; resolves escalated cross-functional disputes
AI Governance Working Group | Work Team / Working Group | Permanent operational body making binding standards decisions, evaluating tools/platforms, establishing architecture policies, and managing governance transactions. Functions as the AI Architecture Review Board. This is the action-oriented engine of governance. | Ongoing (permanent) | Larry Burgess (EA, Co-Chair), Ryan Miller (CDO, Co-Chair), Nader Afshar (AI PO), Mike Calaway (CISO), Puru (Data/Infrastructure), Vik Chopra (IT Governance), Tony Grogan (Data Governance) | Weekly (convert current office hours) | Architecture standards, tool evaluations, platform decisions, risk tier assignments, governance transaction approvals (Tier 2-3), vendor assessments, decision log | AI Governance Committee | Makes binding decisions on architecture standards, Tier 2-3 approvals, tool sanctions/blocks; recommends to Committee on Tier 1 and strategic budget items
Shadow AI Remediation Task Force | Task Force (time-limited) | Cross-functional assembly to address hundreds of unauthorized AI users (clarified as ~10 heavy users via expense reports plus broader architectural scan data). Develops sanctioned tool alternatives, acceptable use enforcement, and migration path from shadow tools to governed alternatives. | 90 days (Q1-Q2 2026) | Mike Calaway (CISO, Lead), Larry Burgess (EA), Nader Afshar (AI PO), HR representative, Chuck Berend (Risk/BI perspective on Copilot ineffectiveness) | Bi-weekly | Sanctioned tool recommendation (Copilot replacement), acceptable use policy update, enforcement workflow (Zscaler/digital adoption platform), user migration plan, cost model | AI Governance Working Group | Recommends to Working Group; implements approved enforcement actions
Platform Rationalization Task Force | Task Force (time-limited) | Investigates and resolves the Genesys vs. Observe AI platform overlap ($4.5M annual duplication risk). Conducts detailed capability comparison, develops platform decision framework applicable to future vendor evaluations. | 60 days (Q1 2026) | Larry Burgess (EA, Lead), Nader Afshar (AI PO), Greg Shreve (Collections/Observe AI stakeholder), Genesys technical resource, Finance representative | Weekly | Capability comparison matrix, cost analysis, platform recommendation, migration plan (if applicable), reusable vendor evaluation framework | AI Governance Working Group | Recommends to Working Group for binding decision; Committee ratifies if cost impact exceeds threshold
Data Classification for AI Task Force | Task Force (time-limited) | Addresses the 95% structured data untagged for AI use and the 70% vs. 99% unstructured data classification gap. Develops field-level classification approach to unblock legitimate AI applications requiring governed data access. | 120 days (Q1-Q2 2026) | Tony Grogan (Data Governance, Lead), Mike Calaway (CISO), Bobby Goodwin (EDM), Vik Chopra (IT Governance), Puru (Infrastructure) | Weekly | Field-level classification methodology, priority data domain classification plan, Purview Data Map implementation roadmap, AI access expansion criteria | AI Governance Working Group | Recommends classification standards to Working Group for adoption; Committee endorses policy changes
AI Cost Management Working Team | Work Team (ongoing) | Develops and maintains AI cost attribution, chargeback models, and ROI measurement frameworks. Addresses self-funding requirement, token consumption tracking, and budget forecasting for consumption-based AI services. | Ongoing (permanent once established) | Finance representative (Lead), Larry Burgess (EA), Sajid Chida (Integration/API costs), Nader Afshar (AI PO), BU cost owners | Bi-weekly | Cost attribution model, chargeback framework, ROI measurement templates, monthly consumption reports, budget forecasting methodology | AI Governance Working Group → Committee (budget items) | Recommends cost models; Working Group approves methodology; Committee approves budget allocations
AI Champions / Subject Matter Interest Group | Subject Matter Interest Group | Community of AI practitioners across business units sharing best practices, creative solutions, and operational feedback. Provides bottom-up input to governance bodies and serves as change management conduit. | Ongoing (permanent) | Representatives from each BU (Collections, Customer Service, Risk/BI, Testing, Data, Digital), AI enthusiasts, power users of sanctioned tools | Monthly | Best practice sharing, use case ideation, adoption feedback, training needs identification, pilot results | Two-way communication to Working Group and Committee | Advisory only; escalates needs and ideas to Working Group

## 2. RACI Chart
Governance Entity | Tool Governance (Shadow AI, Sanctions) | Data Governance (Classification, PII) | Cost Governance (Attribution, ROI) | Architecture (Platform, Registry) | Regulatory (Compliance, Bias) | Process Governance (Intake, Lifecycle) | People / Knowledge (Skills, Training)
AI Governance Committee | I | I | A | I | A | A | I
AI Governance Working Group | A | A | A | A | C | A | C
Shadow AI Remediation TF | R | C | C | C | I | R | I
Platform Rationalization TF | C | I | R | R | I | C | I
Data Classification TF | I | R | I | C | C | I | I
AI Cost Management Team | I | I | R | C | I | C | I
AI Champions Group | C | I | I | I | I | C | C
CDO (Ryan Miller) | A | A | A | A | A | A | A
CISO (Mike Calaway) | R | R | C | C | R | C | I
EA (Larry Burgess) | C | C | C | R | C | R | C
AI PO (Nader Afshar) | C | C | C | R | C | R | C
Risk/Compliance (Chuck) | I | C | I | I | R | C | I
Data (Bobby Goodwin) | I | R | I | C | C | I | R
Finance | I | I | R | I | I | I | I
Procurement (Allison) | C | I | C | C | I | C | I
RACI Legend:
R | Responsible (performs the work)
A | Accountable (owns the outcome)
C | Consulted (input sought)
I | Informed (kept aware)

## 3. Gaps Analysis
# | Governance Domain | Current State | Gap Description | Target State | Severity | Owner | Remediation Action | Timeline
1 | Tool Governance | Copilot is only sanctioned chatbot; universally rejected for coding by Risk/BI teams. Hundreds of unauthorized AI tool instances detected. | No sanctioned alternative to Copilot for coding; no self-service tool request process; no evaluation checklist; enforcement only ~75% effective via Zscaler. | Approved coding-capable AI tool (Claude/ChatGPT Enterprise); formal request/approval workflow; digital adoption platform intercepting unauthorized access with redirect to approved tools. | Critical | Mike Calaway / Shadow AI TF | Shadow AI Remediation Task Force: evaluate Claude Enterprise or ChatGPT Enterprise as Copilot alternative; implement DAP-based interception; update AUP. | 90 days
2 | Data Governance | ~95% structured data untagged for AI at field level; 70% unstructured data classified (target 99%). 5-tier classification system exists. | No column-level Data Map scanning blocks Fabric AI Foundry, compliant model training, and governed chatbot implementations. AI restricted to Public/Internal data only. | Field-level classification for priority data domains; Purview Data Map scanning operational; clear AI access expansion criteria tied to demonstrated governance controls. | Critical | Tony Grogan / Data Classification TF | Data Classification Task Force: implement Purview Data Map for priority domains (EDW core tables first); establish field-level PII tagging; define AI access expansion roadmap. | 120 days
3 | Cost Governance | No AI budget line exists. Genesys tokens expiring unused ($15K/month committed). No chargeback model. Self-funding mandate from CFO. | Cannot forecast AI spend; no ROI framework per use case; vendor pricing lock-in risk ('drug dealer model'); no mechanism to attribute costs to BUs; licensed capabilities wasting. | AI consumption tracking via APIM; BU chargeback model; standardized ROI framework; budget forecasting capability; activated licensed AI capabilities. | Critical | Finance / AI Cost Management Team | AI Cost Management Team: build token consumption dashboard; develop chargeback model; create ROI template; activate Genesys tokens with governance clearance. | 60 days (framework), ongoing
4 | Architecture | No AI agent registry. Platform duplication: Genesys + Observe AI = $4.5M overlap. No platform decision framework. No MCP/A2A standards. | Cannot govern what you cannot see; duplicate spending; ad hoc platform decisions; no reference architecture for AI implementations. | Agent Registry (simple spreadsheet initially, formalize over time); platform decision framework; reference architectures for common AI patterns; MCP implementation for usage tracking. | High | Larry Burgess / Platform TF | Platform Rationalization TF: Genesys vs. Observe AI comparison; Working Group: establish Agent Registry; develop platform decision criteria. | 60-90 days
5 | Regulatory | AI Governance Policy v1.0 exists (3 months old). Champion-challenger methodology in Risk (Rene/Mark Segarra). No AI incident response playbook. | Policy not pressure-tested; no formalized bias testing for AI; no human-in-the-loop requirements documented; no AI-specific incident response; cyber insurance AI coverage unclear. | Pressure-tested governance workflows; formalized fairness/bias assessment process; AI incident response playbook; human-in-the-loop requirements by risk tier; AI insurance coverage confirmed. | High | Chuck Berend / Legal | Working Group: develop AI incident response playbook; formalize bias testing requirements (building on Rene's champion-challenger); Committee: engage cyber insurance review. | 90-120 days
6 | Process Governance | AI Steering Committee meets every 6-10 weeks. All requests go through same process regardless of risk. 'Book club' approach. No structured decision logging. | Cadence too slow for execution velocity; no tiered review process; no fast-track for low-risk; governance perceived as bottleneck; no working group authority defined. | Three-tier governance structure operational; risk-tiered review process (Tier 1-4); Working Group meets weekly with decision authority; structured decision logging; clear escalation paths. | High | Ryan Miller / Larry Burgess | Immediate: convert office hours to weekly Working Group sessions; define RACI between tiers; implement risk-tiering framework; establish decision log template. | 30 days (structure), 60 days (operational)
7 | People / Knowledge | AI expertise concentrated in Adam Ruthford (Fabric/AI), Bobby Goodwin (data lineage). Skills vary dramatically by team. No AI training program. | Single points of failure; no knowledge transfer plan; no adoption maturity assessment by team; no AI training curriculum; variable readiness across BUs. | Cross-training programs for critical AI knowledge; tiered training curriculum by role; adoption maturity assessment; knowledge capture for key person risk mitigation. | Medium | Bobby Goodwin / HR | Working Group: commission skills assessment; develop tiered training plan; prioritize knowledge capture for highest bus-factor risks (Adam, Bobby). | 90-120 days
8 | Procurement | Allison serves as informal gate ('nothing gets signed without her'). No formal vendor AI evaluation framework. Licensed capabilities going unused. | Ad hoc vendor evaluation; no standard assessment criteria for AI-specific considerations; procurement not formally in governance committee; activated capabilities blocked by governance delays. | Formal vendor AI evaluation checklist (security, data access, vendor stability, SOC, cost/value); procurement integrated into governance workflow; fast-track for activating already-licensed capabilities. | High | Larry Burgess / Procurement | Working Group: develop vendor evaluation checklist (Larry's criteria); fast-track governance clearance for already-purchased capabilities (Genesys AI, Einstein, Fabric AI Foundry). | 45 days

## 4. Priorities & Risks
Priority | Initiative | Rationale | Risk If Delayed | Dependencies | Quick Win? | Owner | Target Completion
P1 | Establish Three-Tier Governance Structure | Governance velocity is the #1 shared concern between Larry and Ryan. Current 6-10 week cadence blocks execution. Working Group needs weekly decision authority. | Continued paralysis; shadow AI grows; licensed capabilities waste; competitors pull ahead; talent frustration | Ryan/Larry alignment on authority delegation | Yes | Ryan Miller / Larry Burgess | 2 weeks
P2 | Activate Already-Licensed AI Capabilities | Genesys AI tokens, Einstein, Fabric AI Foundry are paid for but dormant. Fastest path to demonstrating ROI and building organizational AI muscle. | Direct financial waste continues; credibility of future AI investment requests undermined; opportunity cost of delayed capability | Governance structure (P1); risk tier assignment per capability | Yes | Nader Afshar / Working Group | 30-45 days
P3 | Shadow AI Remediation | Hundreds of unauthorized AI instances create uncontrolled data exposure and compliance risk. Root cause: Copilot inadequacy. Must provide approved alternative. | Regulatory exposure escalates; data exfiltration incidents; employees continue emailing code from personal devices; audit findings | Governance structure (P1); sanctioned tool evaluation | Partial | Mike Calaway / Shadow AI TF | 90 days
P4 | Genesys vs. Observe AI Platform Decision | $4.5M annual duplication cost. Decision stalled by resource constraints. Detailed capability comparison needed. | Ongoing $4.5M annual waste; architectural fragmentation deepens; integration complexity multiplies; vendor lock-in on both sides | Platform TF formation; Working Group decision authority | No | Larry Burgess / Platform TF | 60 days
P5 | AI Agent Registry | Cannot govern what you cannot see. No visibility into deployed AI agents across Genesys, Salesforce, Azure. Policy requires approval but not ongoing cataloging. | Rogue agents; unknown data access; incident response blind spots; duplicate capabilities; untracked costs | Governance structure (P1); inventory of current AI touchpoints | Yes | Nader Afshar / EA team | 30 days (v1 spreadsheet)
P6 | Data Classification for AI Access | 95% structured data untagged blocks most valuable AI use cases. Current AI restricted to Public/Internal only. Field-level classification required. | AI remains limited to low-value use cases; Fabric AI Foundry stays blocked; cannot build governed chatbots accessing real business data | Purview Data Map capability; resource allocation | No | Tony Grogan / Data Classification TF | 120 days
P7 | AI Cost Management Framework | No AI budget line. Self-funding mandate. Token consumption unpredictable. No BU attribution. Vendor pricing lock-in risk. | Budget surprises; cannot validate ROI; low-value use cases subsidize high-value; CFO loses confidence in AI investment | APIM deployment; BU cost owner identification | Partial | Finance / AI Cost Mgmt Team | 60 days (framework)
P8 | AI Incident Response Playbook | No playbook for AI-specific incidents. Policy v1.0 not pressure-tested. Regulatory scrutiny increasing in financial services. | Delayed/inadequate incident response; regulatory notification failures; reputational damage | Policy v1.0 review; CISO/Legal collaboration | Yes | Mike Calaway / Legal | 45 days

## 5. Working Agendas
Governance Body | Meeting # | Agenda Topic | Objective | Expected Output | Responsible | Duration (min)
AI Governance Committee | 1 (Kickoff) | Charter Ratification & Governance Structure Approval | Formally adopt three-tier governance structure; define Committee vs. Working Group authority | Signed charter; RACI approval; decision authority matrix | Ryan Miller | 60
AI Governance Committee | 1 | Shadow AI Briefing & Remediation Direction | Review shadow AI data (hundreds of instances); approve remediation approach; authorize tool evaluation | Remediation direction approved; budget for tool evaluation | Mike Calaway | 30
AI Governance Committee | 2 | Platform Rationalization Decision | Review Working Group recommendation on Genesys vs. Observe AI; approve or redirect | Platform decision ratified; migration plan authorized (if applicable) | Larry Burgess | 45
AI Governance Committee | 2 | AI Budget & Cost Framework Review | Review AI cost management framework; approve chargeback methodology; set FY26 AI budget guardrails | Chargeback model approved; budget parameters set | Finance | 30
AI Governance Committee | 3 | Quarterly AI Portfolio Review | Review all active AI initiatives, adoption metrics, risk posture, and ROI performance | Portfolio health assessment; resource reallocation if needed | Nader Afshar | 60
AI Working Group | 1 (Kickoff) | Operating Model & Decision Authority | Define Working Group operating procedures: decision logging, voting, escalation triggers, agenda management | Operating procedures document; decision log template; escalation criteria | Larry Burgess | 45
AI Working Group | 1 | Agent Registry Design | Define registry fields, initial population approach, maintenance responsibility | Registry template (spreadsheet v1); population plan | Nader Afshar | 30
AI Working Group | 2 | Risk Tiering Framework Adoption | Review and adopt 4-tier risk classification for AI governance transactions | Risk tiering framework approved; example classifications for current initiatives | Working Group | 45
AI Working Group | 3 | Sanctioned Tool Evaluation Criteria | Define evaluation checklist for AI tools (building on Larry's criteria: inventory, fit-for-purpose, tech stack, data, vendor stability, SOC, cost) | Vendor evaluation checklist; sanctioned tool requirements | Larry Burgess | 30
AI Working Group | 4 | Licensed Capability Fast-Track Review | Fast-track governance review for Genesys AI, Einstein, Fabric AI Foundry activation | Go/no-go per capability; conditions/monitoring requirements | Nader Afshar | 45
AI Working Group | 5 | Governance Transaction Intake Process | Define standard intake form, routing logic, and SLA by risk tier | Intake form template; routing decision tree; SLA targets by tier | Mike Calaway | 30
AI Working Group | Ongoing | Standing Agenda: Decision Review & Action Tracking | Review pending decisions, track open actions, process new governance transactions | Updated decision log; action items with owners/dates | Co-Chairs | 15
Shadow AI TF | 1 | Current State Assessment | Reconcile data sources (expense reports vs. architectural scans); map actual unauthorized usage | Accurate shadow AI inventory; user interview findings; root cause analysis | Mike Calaway | 60
Shadow AI TF | 2 | Tool Evaluation & Recommendation | Evaluate Claude Enterprise, ChatGPT Enterprise, and other alternatives against Copilot gaps | Comparison matrix; cost model; recommendation to Working Group | Nader Afshar | 60
Shadow AI TF | 3 | Enforcement Workflow Design | Design DAP-based interception workflow; update Zscaler rules; define exception/request process | Enforcement workflow diagram; exception request form; communication plan | Mike Calaway | 45
Platform TF | 1 | Capability Comparison: Genesys vs. Observe AI | Detailed feature-by-feature comparison across transcription, QA scoring, agent assist, analytics | Capability matrix with scoring | Larry Burgess | 90
Platform TF | 2 | Cost & Architecture Analysis | Full TCO comparison; integration assessment; migration complexity estimation | TCO model; architecture impact assessment; migration effort estimate | Finance + EA | 60
Platform TF | 3 | Recommendation Development | Synthesize findings into platform recommendation with migration plan | Recommendation document for Working Group review | Larry Burgess | 45
Data Classification TF | 1 | Priority Domain Identification | Identify highest-value data domains for AI access; map to use cases blocked by classification gaps | Prioritized domain list; use case dependency map | Tony Grogan | 60
Data Classification TF | 2 | Purview Data Map Implementation Plan | Design implementation approach for field-level classification starting with priority domains | Implementation plan; resource requirements; timeline | Tony Grogan / Vik | 60
AI Cost Management Team | 1 (Kickoff) | Cost Baseline and Attribution Model Design | Establish current AI spend inventory across Genesys, Salesforce, Fabric, and Azure; define BU attribution methodology | AI spend inventory; draft attribution model; identified cost owners per BU | Finance Lead | 60
AI Cost Management Team | 2 | Token Consumption Dashboard Development | Design and deploy dashboard tracking Genesys AI token usage, Fabric capacity units, API call volumes, and Copilot licensing | Dashboard specification; data source mapping; prototype deployment | Finance Lead / Larry Burgess | 45
AI Cost Management Team | 3 | ROI Framework per Use Case | Develop standardized ROI measurement template linking AI investment to business outcomes (call deflection, productivity, cycle time) | ROI template; baseline metrics per active use case; measurement cadence | Finance Lead / Nader Afshar | 45
AI Cost Management Team | 4 | Chargeback Model and Budget Forecasting | Finalize BU chargeback methodology; build quarterly AI budget forecast model; establish variance reporting | Approved chargeback model; forecast template; variance thresholds for escalation | Finance Lead | 45
AI Cost Management Team | Ongoing | Standing Agenda: Spend Review and Forecast Update | Review actual vs. forecast AI spend; flag variances; update ROI tracking per use case; report to Working Group | Updated spend report; variance analysis; ROI scorecard for Committee review | Finance Lead | 30
AI Champions Group | 1 (Kickoff) | Community Launch and Charter Review | Introduce AI Champions program purpose, expectations, and communication channels; identify BU representatives; establish feedback mechanisms | Confirmed membership roster; communication plan; shared channel (Teams/SharePoint); initial needs inventory | Nader Afshar | 60
AI Champions Group | 2 | Use Case Ideation Workshop | Structured brainstorming of AI opportunities from BU perspectives; prioritize based on feasibility and business impact; identify candidates for Working Group intake | Prioritized use case backlog; top 3 candidates submitted to Working Group for intake triage | BU Representatives | 60
AI Champions Group | 3 | AI Tool Adoption Feedback and Training Needs | Gather frontline feedback on sanctioned AI tools (Copilot, approved alternatives); identify training gaps; surface adoption barriers and workarounds | Adoption feedback report; training needs assessment; barrier analysis for Working Group | BU Representatives | 60
AI Champions Group | 4 | AI Success Stories and Lessons Learned | Showcase successful AI implementations from across BUs; share lessons learned from pilots; build organizational confidence and cross-pollinate ideas | Presentation deck of wins/lessons; updated best practices repository; nominations for Committee showcase slot | Rotating BU Presenter | 60
AI Champions Group | Ongoing | Standing Agenda: Updates, Feedback, and Cross-BU Sharing | Governance updates from Working Group; new tool announcements; open floor for BU challenges, ideas, and adoption feedback; training calendar review | Monthly feedback summary to Working Group; updated adoption metrics; training attendance tracking | Nader Afshar | 45

## 6. Charter Summary
Element | AI Governance Committee | AI Governance Working Group | Task Forces (Shadow AI, Platform, Data Classification) | AI Cost Management Team | AI Champions Group
Purpose | Strategic oversight, cross-BU alignment, budget advocacy, policy endorsement | Operational decision-making on AI standards, architecture, tool selection, governance transactions | Time-boxed investigation and resolution of specific governance gaps with defined deliverables | Ongoing AI cost visibility, attribution, ROI measurement, and budget forecasting | Community of practice for AI practitioners; bottom-up feedback and best practice sharing
Scope | All AI initiatives enterprise-wide; Tier 1 (Critical) approvals; budget allocation; escalation resolution | Architecture standards; Tier 2-3 approvals; tool evaluation/sanctioning; vendor assessment; governance transactions | Shadow AI: Remediate unauthorized usage, evaluate alternatives. Platform: Genesys vs. Observe AI. Data: Field-level classification. | Token/consumption tracking; BU chargeback; ROI frameworks; vendor cost modeling | Use case ideation; adoption feedback; training needs; cross-BU learning
Success Criteria | AI portfolio delivering measurable ROI; risk posture maintained; cross-BU initiatives coordinated; governance not perceived as bottleneck | Governance transactions processed within SLA by tier; licensed capabilities activated; shadow AI reduced 80%+; decision log maintained | Shadow AI: Approved alternative deployed, unauthorized usage <5%. Platform: Decision made, savings realized. Data: Priority domains classified. | AI costs attributed to BUs; ROI validated per use case; budget forecast accuracy within 15%; waste eliminated | Adoption metrics improving; training completion >80%; use case pipeline growing; cross-BU collaboration evident
Meeting Cadence | Every 6 weeks | Weekly (convert current office hours to working sessions) | Shadow AI TF: Bi-weekly (90 days). Platform TF: Weekly (60 days). Data TF: Weekly (120 days). | Bi-weekly | Monthly
Decision Authority | Ratifies Working Group strategic recommendations; approves Tier 1 deployments; resolves escalations; allocates budget | Makes binding decisions on standards and Tier 2-3 items; recommends to Committee on Tier 1 and strategic/budget items | Recommends to Working Group; implements approved actions within defined scope | Recommends cost models; Working Group approves methodology; Committee approves budget allocations | Advisory only; escalates needs to Working Group
Escalation Path | Unresolved items to executive management / Stellantis corporate | Items exceeding authority (Tier 1, budget threshold, cross-BU conflict) to Committee | Scope changes, timeline risks, resource gaps to Working Group co-chairs | Budget overruns, forecast misses to Working Group then Committee | Unaddressed needs to Working Group via representative
Key Risks | Insufficient executive attendance; 'rubber stamp' instead of engaged oversight; cadence too slow for urgent decisions | Resource overload on weekly members; decision fatigue; scope creep from task forces; lack of business unit input | Timeline slippage; resource competition; deliverables not actionable; political resistance to platform decisions | Finance disengagement; cost data inaccessible from vendor systems; chargeback model too complex for adoption | Low participation; perceived as 'extra' work; feedback not acted upon; champion burnout